## Sheet1
Project Name | Milestone Name | Owner Name | Start Date | End Date | Milestone Status | Milestone ID | Owner ID | Project ID | Created Time | Duration | Actual Time Taken | Milestone Completion Mode | Milestone ID String | Project ID String
Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | Uday Desai | 2024-01-09 09:30 | 2024-03-22 19:00 | Upcoming | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-01-09 15:40 | 74 | 70 | On Time | 7.4981e+17 | 7.4981e+17
NMDSC - Zoho Connect | Milestone Two-Implementation completion of Zoho Connect | Prableen Kaur | 2024-03-11 | 2024-03-29 23:59 | Upcoming | 7.4981e+17 | 792886644 | 7.4981e+17 | 2024-03-06 10:20 | 19 | 8 | On Time | 7.4981e+17 | 7.4981e+17
Juspay - Zoho Desk & Zoho SalesIQ - PA | Milestone Three-Annual maintenance charges - Post Go-Live Application support for Zoho Desk & Zo | Uday Desai | 2024-04-01 | 2025-03-31 23:59 | Upcoming | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-03-12 19:26 | 365 | -13 | On Time | 7.4981e+17 | 7.4981e+17
CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | Vignesh R | 2024-02-01 | 2024-03-15 | Overdue | 7.4981e+17 | 704175602 | 7.4981e+17 | 2024-01-16 14:48 | 44 | 47 | Late | 7.4981e+17 | 7.4981e+17
CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | Stuti S. Kulshrestha | 2024-03-13 | 2024-04-09 23:59 | Upcoming | 7.4981e+17 | 808004288 | 7.4981e+17 | 2024-01-16 14:48 | 28 | 6 | On Time | 7.4981e+17 | 7.4981e+17
CEEW - Zoho ONE - ERP Implementation | Milestone Ten-Implementation of Zoho People - HRMS System - Retrofit Implementation - Phase 2 | Kiran Shrivastav | 2024-08-29 | 2024-09-26 23:59 | Upcoming | 7.4981e+17 | 791842987 | 7.4981e+17 | 2024-01-16 14:48 | 29 | -163 | On Time | 7.4981e+17 | 7.4981e+17
CEEW - Zoho ONE - ERP Implementation | Milestone Seven-Implementation of Zoho Creator - Vendor Portal - Phase 2 | Sai Krishna | 2024-06-05 | 2024-07-02 23:59 | Upcoming | 7.4981e+17 | 753339779 | 7.4981e+17 | 2024-01-16 14:48 | 28 | -78 | On Time | 7.4981e+17 | 7.4981e+17
Dr Reddy’s - Zoho CRM, Desk, SalesIQ | Milestone Three-1. Completion of Configuration, Customization2. Solution Demo3. User acceptanc | Dharanidharan C | 2024-03-06 | 2024-04-06 23:59 | Upcoming | 7.4981e+17 | 701371504 | 7.4981e+17 | 2024-01-31 18:06 | 32 | 13 | On Time | 7.4981e+17 | 7.4981e+17
IIFL Samasta Zoho Creator Score Card Enhancement | Milestone One-Implementation of Score Card Enhancement | Tanu Gupta | 2024-02-12 | 2024-02-21 23:59 | Overdue | 7.4981e+17 | 790157522 | 7.4981e+17 | 2024-02-16 14:25 | 10 | 36 | Late | 7.4981e+17 | 7.4981e+17
TMSB - Next-Gen Learning Transformation with Zoho Creator Enhancement | Milestone One-Advance Payment for the Learning Transformation with Zoho Creator Enhancement | Mahantesh | 2024-02-20 | 2024-02-23 23:59 | Overdue | 7.4981e+17 | 708232745 | 7.4981e+17 | 2024-02-20 16:47 | 4 | 28 | Late | 7.4981e+17 | 7.4981e+17
Machani Dedicated Resource extension | Milestone Two-Dedicated Resource for April 2024 | Mohan Kumar | 2024-04-01 | 2024-04-30 23:59 | Upcoming | 7.4981e+17 | 778473538 | 7.4981e+17 | 2024-02-20 17:10 | 30 | -13 | On Time | 7.4981e+17 | 7.4981e+17
Machani Dedicated Resource extension | Milestone Four-Dedicated Resource for Jun 2024 | Mohan Kumar | 2024-06-01 | 2024-06-30 23:59 | Upcoming | 7.4981e+17 | 778473538 | 7.4981e+17 | 2024-02-20 17:10 | 30 | -74 | On Time | 7.4981e+17 | 7.4981e+17
SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | Waheeba Khan | 2024-01-29 | 2024-03-29 | Upcoming | 7.4981e+17 | 671373250 | 7.4981e+17 | 2024-01-29 19:10 | 61 | 50 | On Time | 7.4981e+17 | 7.4981e+17
TMSB - Next-Gen Learning Transformation with Zoho Creator Enhancement | Milestone Two- Zoho Creator Existing system improvisation | Uday Desai | 2024-03-01 | 2024-04-01 | Upcoming | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-02-20 16:47 | 32 | 18 | On Time | 7.4981e+17 | 7.4981e+17
Accorian - Zoho CRM | Milestone Two-Implementation of Zoho CRM | Supril Jain | 2024-01-11 | 2024-03-25 | Upcoming | 7.4981e+17 | 756836914 | 7.4981e+17 | 2024-01-10 12:29 | 75 | 68 | On Time | 7.4981e+17 | 7.4981e+17
Stanzen _Zoho Creator_Segregation of material & Process Cost_CR | Milestone One-Advance Payment for CR 6 - Segregation of material & Process Cost | Uday Desai | 2024-03-11 | 2024-03-11 23:59 | Overdue | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-03-12 10:23 | 1 | 8 | Late | 7.4981e+17 | 7.4981e+17
IIFL SAMASTA -Zoho Creator_Helpdesk CR | Milestone One-Customization and Development of Change Request for Zoho Help Desk | Uday Desai | 2023-11-28 | 2023-12-08 23:59 | Overdue | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-03-12 10:33 | 11 | 112 | Late | 7.4981e+17 | 7.4981e+17
CEEW - Zoho ONE - ERP Implementation | Milestone One-Advance Payment for Project Initiation | Mahantesh | 2024-01-16 | 2024-01-16 | Completed | 7.4981e+17 | 708232745 | 7.4981e+17 | 2024-01-16 14:48 | 1 | 8 | Late | 7.4981e+17 | 7.4981e+17
SPERA - Zoho Creator | Milestone One-Advance Payment for Project Initiation - Zoho Creator | Mahantesh | 2024-01-25 | 2024-01-25 23:59 | Completed | 7.4981e+17 | 708232745 | 7.4981e+17 | 2024-01-29 19:10 | 1 | 8 | Late | 7.4981e+17 | 7.4981e+17
Prodevans - Zoho Projects | Milestone One-Advance Payment for Project Initiation | Mahantesh | 2024-02-29 | 2024-02-29 23:59 | Completed | 7.4981e+17 | 708232745 | 7.4981e+17 | 2024-02-29 21:41 | 1 | 5 | Late | 7.4981e+17 | 7.4981e+17
iDatalytics - Zoho Devt(NMSDC)- Roll Out | 4. Connections (Higher Logic) | Deji Akinyemi | 2024-03-12 | 2024-08-15 | Upcoming | 7.4981e+17 | 828527327 | 7.4981e+17 | 2024-03-12 22:01 | 157 | 7 | On Time | 7.4981e+17 | 7.4981e+17
RERA Consultants LLP - Zoho CRM, Books, People, Collabrative Apps, Sign, Contracts | Milestone Three-Annual maintenance charges - Post Go-Live Application support for Zoho CRM, Zoho | Uday Desai | 2024-05-27 | 2025-05-26 23:59 | Upcoming | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-03-13 14:18 | 365 | -69 | On Time | 7.4981e+17 | 7.4981e+17
Juspay - Zoho Desk & Zoho SalesIQ - PA | Milestone Two-Implementation of Zoho SalesIQ & Zoho Desk | Uday Desai | 2024-03-13 | 2024-03-29 23:59 | Upcoming | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-03-12 19:26 | 17 | 6 | On Time | 7.4981e+17 | 7.4981e+17
RERA Consultants LLP - Zoho CRM, Books, People, Collabrative Apps, Sign, Contracts | Milestone Two-Implementation of Zoho CRM, Projects, Books, People, Contract, Sign, Workdrive, | Uday Desai | 2024-03-13 | 2024-05-14 23:59 | Upcoming | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-03-13 14:18 | 63 | 6 | On Time | 7.4981e+17 | 7.4981e+17
CEEW - Zoho ONE - ERP Implementation | Milestone Eight-Implementation of Zoho Creator - Asset Management - Phase 2 | Sai Krishna | 2024-07-03 | 2024-07-30 23:59 | Upcoming | 7.4981e+17 | 753339779 | 7.4981e+17 | 2024-01-16 14:48 | 28 | -106 | On Time | 7.4981e+17 | 7.4981e+17
Accorian - Zoho CRM | Milestone Four-Annual maintenance charges Application Support – Zoho CRM | Uday Desai | 2024-03-04 | 2025-03-03 23:59 | Upcoming | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-01-10 12:29 | 365 | 15 | On Time | 7.4981e+17 | 7.4981e+17
Prodevans - Zoho CRM | Milestone Three-Annual maintenance charges - Post Go-Live Application support for Zoho CRM | Anusha V | 2024-02-01 | 2025-01-31 23:59 | Upcoming | 7.4981e+17 | 795545761 | 7.4981e+17 | 2024-01-16 14:48 | 366 | 47 | On Time | 7.4981e+17 | 7.4981e+17
Prodevans - Zoho CRM | Milestone Two-Implementation of Zoho CRM | Anusha V | 2024-01-17 | 2024-02-29 | Overdue | 7.4981e+17 | 795545761 | 7.4981e+17 | 2024-01-16 14:48 | 44 | 62 | Late | 7.4981e+17 | 7.4981e+17
TMSB - Next-Gen Learning Transformation with Zoho Creator Enhancement | Milestone Three-UI / UXEnhancement & WhatsAppIntegration | Uday Desai | 2024-03-04 | 2024-04-12 23:59 | Upcoming | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-02-20 16:47 | 40 | 15 | On Time | 7.4981e+17 | 7.4981e+17
CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Five-Implementation of Zoho Expense | Kiran Shrivastav | 2024-03-25 | 2024-04-03 23:59 | Upcoming | 7.4981e+17 | 791842987 | 7.4981e+17 | 2024-02-20 16:46 | 10 | -6 | On Time | 7.4981e+17 | 7.4981e+17
Machani Dedicated Resource extension | Milestone Six-Dedicated Resource for Aug 2024 | Mohan Kumar | 2024-08-01 | 2024-08-31 23:59 | Upcoming | 7.4981e+17 | 778473538 | 7.4981e+17 | 2024-02-20 17:10 | 31 | -135 | On Time | 7.4981e+17 | 7.4981e+17
Accorian - Zoho CRM | Milestone Three-Data Migration on Zoho CRM application | Supril Jain | 2024-02-01 | 2024-04-01 | Upcoming | 7.4981e+17 | 756836914 | 7.4981e+17 | 2024-01-10 12:29 | 61 | 47 | On Time | 7.4981e+17 | 7.4981e+17
IIFL SAMASTA- Admin Module CR | Milestone One-Advance payment for Admin Module Change Request | Mahantesh | 2024-02-20 | 2024-03-15 | Overdue | 7.4981e+17 | 708232745 | 7.4981e+17 | 2024-02-20 16:47 | 25 | 28 | Late | 7.4981e+17 | 7.4981e+17
IIFL SAMASTA - IMS Enhancement 3.5 | Milestone Two-Zoho Creator: Customization, Configuration, Testing and Go-Live of IMS enhancement | Selva Bharathi | 2024-02-21 | 2024-03-20 | Upcoming | 7.4981e+17 | 701368573 | 7.4981e+17 | 2024-02-20 16:46 | 29 | 27 | On Time | 7.4981e+17 | 7.4981e+17
Stanzen Engineering - CR 5 | Milestone One-Zoho Implementation Service - CR# 5 Bills Auto Create and push to Zoho Books | Vignesh R | 2024-02-14 | 2024-03-15 | Overdue | 7.4981e+17 | 704175602 | 7.4981e+17 | 2024-02-16 14:25 | 31 | 34 | Late | 7.4981e+17 | 7.4981e+17
STARAGILE - Zoho Desk AMC | Milestone One-AMC for Software application support – Zoho Desk(Yearly Billing) | Uday Desai | 2024-01-30 | 2024-01-30 23:59 | Overdue | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-01-31 13:27 | 1 | 49 | Late | 7.4981e+17 | 7.4981e+17
JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | Waheeba Khan | 2024-01-02 | 2024-01-02 | Completed | 7.4981e+17 | 671373250 | 7.4981e+17 | 2024-01-02 18:02 | 1 | 8 | Late | 7.4981e+17 | 7.4981e+17
Prodevans - Zoho CRM | Milestone One-Advance Payment for Project Initiation | Uday Desai | 2024-01-16 | 2024-01-16 | Completed | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-01-16 14:48 | 1 | 8 | Late | 7.4981e+17 | 7.4981e+17
CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone One-Advance Payment for Project Initiation | Mahantesh | 2024-02-19 | 2024-02-20 23:59 | Completed | 7.4981e+17 | 708232745 | 7.4981e+17 | 2024-02-20 16:46 | 2 | 12 | Late | 7.4981e+17 | 7.4981e+17
Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | Supril Jain | 2024-01-30 | 2024-03-29 | Completed | 7.4981e+17 | 756836914 | 7.4981e+17 | 2024-01-29 19:10 | 60 | 42 | On Time | 7.4981e+17 | 7.4981e+17
NMDSC - Zoho Connect | Milestone Four-AMC | Prableen Kaur | 2024-03-25 | 2024-04-30 | Upcoming | 7.4981e+17 | 792886644 | 7.4981e+17 | 2024-03-06 10:20 | 37 | -6 | On Time | 7.4981e+17 | 7.4981e+17
RERA Consultants LLP - Zoho CRM, Books, People, Collabrative Apps, Sign, Contracts | Milestone One-Advance Payment for Project Initiation | Uday Desai | 2024-03-12 | 2024-03-13 23:59 | Overdue | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-03-13 14:18 | 2 | 7 | Late | 7.4981e+17 | 7.4981e+17
Stanzen _Zoho Creator_Segregation of material & Process Cost_CR | Milestone Two-Zoho Creator_Segregation of material & Process Cost_CR6_ Completion of Customiza | Uday Desai | 2024-03-11 | 2024-03-22 23:59 | Upcoming | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-03-12 10:23 | 12 | 8 | On Time | 7.4981e+17 | 7.4981e+17
AMC - VAlign | Infifresh 01-01-2024 to 31-12-2024 | Mohammed Yusha | 2024-01-02 | 2024-12-31 | Upcoming | 7.4981e+17 | 701373265 | 7.4981e+17 | 2024-01-02 17:39 | 365 | 77 | On Time | 7.4981e+17 | 7.4981e+17
CEEW - Zoho ONE - ERP Implementation | Milestone Twelve-Post Go-Live Application Support - Zoho ONE | Stuti S. Kulshrestha | 2024-11-01 | 2025-10-31 23:59 | Upcoming | 7.4981e+17 | 808004288 | 7.4981e+17 | 2024-01-16 14:48 | 365 | -227 | On Time | 7.4981e+17 | 7.4981e+17
CEEW - Zoho ONE - ERP Implementation | Milestone Six-Implementation of Zoho Analytics - Phase 1 | Achyuth T M | 2024-05-08 | 2024-06-04 23:59 | Upcoming | 7.4981e+17 | 708853094 | 7.4981e+17 | 2024-01-16 14:48 | 28 | -50 | On Time | 7.4981e+17 | 7.4981e+17
AMC - VAlign | FARM INDIA IMPEX ¦ Books, Creator, People, Payroll & Analytics ¦ 8-12-23 to 7-12-24 | Maninder Singh | 2023-12-08 | 2024-12-07 23:59 | Upcoming | 7.4981e+17 | 782721491 | 7.4981e+17 | 2024-01-24 10:05 | 366 | 102 | On Time | 7.4981e+17 | 7.4981e+17
AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | Waheeba Khan | 2023-11-27 | 2024-11-26 23:59 | Upcoming | 7.4981e+17 | 671373250 | 7.4981e+17 | 2024-02-09 12:10 | 366 | 113 | On Time | 7.4981e+17 | 7.4981e+17
TMSB - Next-Gen Learning Transformation with Zoho Creator Enhancement | Milestone Four-Implementation of RoadMap and aligned modules | Uday Desai | 2024-03-18 | 2024-04-30 23:59 | Upcoming | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-02-20 16:47 | 44 | 1 | On Time | 7.4981e+17 | 7.4981e+17
Prodevans - Zoho Projects | Milestone Three-AMC for Software support charges (Yearly Billing) - Zoho Projects (50 Hours) | Irshad Pasha | 2024-03-15 | 2025-03-14 23:59 | Upcoming | 7.4981e+17 | 701341459 | 7.4981e+17 | 2024-02-29 21:41 | 365 | 4 | On Time | 7.4981e+17 | 7.4981e+17
Machani Dedicated Resource extension | Milestone Three-Dedicated Resource for May 2024 | Mohan Kumar | 2024-05-01 | 2024-05-31 23:59 | Upcoming | 7.4981e+17 | 778473538 | 7.4981e+17 | 2024-02-20 17:10 | 31 | -43 | On Time | 7.4981e+17 | 7.4981e+17
CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Four-Implementation of Zoho Payroll | Kiran Shrivastav | 2024-03-14 | 2024-03-29 | Upcoming | 7.4981e+17 | 791842987 | 7.4981e+17 | 2024-02-20 16:46 | 16 | 5 | On Time | 7.4981e+17 | 7.4981e+17
Right Horizons Financial Services Pvt Ltd. - Zoho CRM, Creator, Analytics | Milestone Two-System study of Creator, Analytics, CRM | Dharanidharan C | 2024-02-15 | 2024-03-29 | Upcoming | 7.4981e+17 | 701371504 | 7.4981e+17 | 2024-02-14 12:26 | 44 | 33 | On Time | 7.4981e+17 | 7.4981e+17
Machani Dedicated Resource extension | Milestone One-Dedicated Resource for March 2024 | Mohan Kumar | 2024-03-01 | 2024-03-29 | Upcoming | 7.4981e+17 | 778473538 | 7.4981e+17 | 2024-02-20 17:10 | 29 | 18 | On Time | 7.4981e+17 | 7.4981e+17
NMDSC - Zoho Connect | Milestone Three-RPA BOT Implementation completion | Prableen Kaur | 2024-03-11 | 2024-03-22 23:59 | Upcoming | 7.4981e+17 | 792886644 | 7.4981e+17 | 2024-03-06 10:20 | 12 | 8 | On Time | 7.4981e+17 | 7.4981e+17
IIFL Samasta: Shop Keeper Onboarding CR | Milestone One-Configuration, Development, Testing and Go-Live of Shopkeeper Onboarding CR | Anusha V | 2024-03-05 | 2024-03-07 23:59 | Overdue | 7.4981e+17 | 795545761 | 7.4981e+17 | 2024-03-11 15:05 | 3 | 14 | Late | 7.4981e+17 | 7.4981e+17
Airowire - Zoho Analytics | Milestone One-Advance payment for project initiation - Zoho Analytics | Uday Desai | 2024-01-08 | 2024-02-01 | Completed | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-01-09 15:40 | 25 | 2 | On Time | 7.4981e+17 | 7.4981e+17
Stanzen_Zoho_Creator Change Request 4 | Milestone One-Implementation of Zoho Creator Change Request 4 | Vignesh R | 2024-01-03 | 2024-01-18 23:59 | Completed | 7.4981e+17 | 704175602 | 7.4981e+17 | 2024-01-24 12:31 | 16 | 30 | Late | 7.4981e+17 | 7.4981e+17
Right Horizons Financial Services Pvt Ltd. - Zoho CRM, Creator, Analytics | Milestone One-Advance payment | Mahantesh | 2024-02-13 | 2024-02-13 23:59 | Completed | 7.4981e+17 | 708232745 | 7.4981e+17 | 2024-02-14 12:26 | 1 | 18 | Late | 7.4981e+17 | 7.4981e+17
CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | Tanu Gupta | 2024-02-26 | 2024-03-29 | Upcoming | 7.4981e+17 | 790157522 | 7.4981e+17 | 2024-02-20 16:46 | 33 | 22 | On Time | 7.4981e+17 | 7.4981e+17
Juspay - Zoho Desk & Zoho SalesIQ - PA | Milestone One-Advance Payment for Project Initiation | Uday Desai | 2024-03-12 | 2024-03-13 23:59 | Overdue | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-03-12 19:26 | 2 | 7 | Late | 7.4981e+17 | 7.4981e+17
CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Three-Implementation of Zoho People | Kiran Shrivastav | 2024-02-29 | 2024-03-29 | Upcoming | 7.4981e+17 | 791842987 | 7.4981e+17 | 2024-02-20 16:46 | 30 | 19 | On Time | 7.4981e+17 | 7.4981e+17
IIFL Samasta_ AMC_Support Tickets | Milestone One-Support Service Requests for Zoho Applications | Uday Desai | 2023-12-30 | 2024-12-29 23:59 | Upcoming | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-01-19 16:13 | 366 | 80 | On Time | 7.4981e+17 | 7.4981e+17
CEEW - Zoho ONE - ERP Implementation | Milestone Five-Implementation of Zoho Expense - Employee Expense & Claims / Reimbursements | Stuti S. Kulshrestha | 2024-04-10 | 2024-05-07 23:59 | Upcoming | 7.4981e+17 | 808004288 | 7.4981e+17 | 2024-01-16 14:48 | 28 | -22 | On Time | 7.4981e+17 | 7.4981e+17
CEEW - Zoho ONE - ERP Implementation | Milestone Eleven-Implementation of Zoho Analytics - Reports & Dashboards for Phase 2 | Achyuth T M | 2024-09-27 | 2024-10-25 23:59 | Upcoming | 7.4981e+17 | 708853094 | 7.4981e+17 | 2024-01-16 14:48 | 29 | -192 | On Time | 7.4981e+17 | 7.4981e+17
Genesis IT - Zoho Books AMC | Milestone One-AMC for Software application support – Zoho Books (Yearly Billing) | Uday Desai | 2024-01-31 | 2024-01-31 23:59 | Overdue | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-01-31 18:06 | 1 | 48 | Late | 7.4981e+17 | 7.4981e+17
AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | Waheeba Khan | 2023-12-29 | 2024-12-28 23:59 | Upcoming | 7.4981e+17 | 671373250 | 7.4981e+17 | 2024-02-15 15:19 | 366 | 81 | On Time | 7.4981e+17 | 7.4981e+17
TMSB - Next-Gen Learning Transformation with Zoho Creator Enhancement | Milestone Five-Testing -Internal Testing, UATimprovisation, Bug fixes andUser Training | Uday Desai | 2024-05-02 | 2024-05-10 23:59 | Upcoming | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-02-20 16:47 | 9 | -44 | On Time | 7.4981e+17 | 7.4981e+17
Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | Dharanidharan C | 2024-02-01 | 2024-03-29 | Upcoming | 7.4981e+17 | 701371504 | 7.4981e+17 | 2024-01-31 13:27 | 58 | 47 | On Time | 7.4981e+17 | 7.4981e+17
Machani Dedicated Resource extension | Milestone Five-Dedicated Resource for July 2024 | Mohan Kumar | 2024-07-01 | 2024-07-31 23:59 | Upcoming | 7.4981e+17 | 778473538 | 7.4981e+17 | 2024-02-20 17:10 | 31 | -104 | On Time | 7.4981e+17 | 7.4981e+17
CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | Sai Krishna | 2024-02-14 | 2024-03-22 | Upcoming | 7.4981e+17 | 753339779 | 7.4981e+17 | 2024-01-16 14:48 | 38 | 34 | On Time | 7.4981e+17 | 7.4981e+17
Prodevans - Zoho Projects | Milestone Two-Implementation of Zoho Projects | M S Satya | 2024-03-01 | 2024-03-29 | Upcoming | 7.4981e+17 | 789497933 | 7.4981e+17 | 2024-02-29 21:41 | 29 | 18 | On Time | 7.4981e+17 | 7.4981e+17
AMC - VAlign | DEFSPACE_AMC_Zoho Books_09-02-2024 to 08-02-2025 | Rishikesh Gogha | 2024-02-09 | 2025-02-08 23:59 | Upcoming | 7.4981e+17 | 745115006 | 7.4981e+17 | 2024-03-06 10:06 | 366 | 39 | On Time | 7.4981e+17 | 7.4981e+17
Dr Reddy’s - Zoho CRM, Desk, SalesIQ | Milestone Two-1. Completion of Configuration, Customization2. Solution Demo3. User acceptanc | Dharanidharan C | 2024-02-05 | 2024-03-28 | Upcoming | 7.4981e+17 | 701371504 | 7.4981e+17 | 2024-01-31 18:06 | 53 | 43 | On Time | 7.4981e+17 | 7.4981e+17
Dr Reddy’s - Zoho CRM, Desk, SalesIQ | Milestone One-Advance payment for Zoho project initiation [Zoho Desk & Zoho SalesIQ, Zoho CRM | Mahantesh | 2024-01-01 | 2024-01-01 23:59 | Overdue | 7.4981e+17 | 708232745 | 7.4981e+17 | 2024-01-31 18:06 | 1 | 78 | Late | 7.4981e+17 | 7.4981e+17
Accorian - Zoho CRM | Milestone One-Advance payment for project initiation | Mahantesh | 2024-01-10 | 2024-02-29 | Completed | 7.4981e+17 | 708232745 | 7.4981e+17 | 2024-01-10 12:29 | 51 | 14 | On Time | 7.4981e+17 | 7.4981e+17
Ocimum Botanicals - Zoho Projects Implementation | Milestone One-Advance Payment | Mahantesh | 2024-02-01 | 2024-02-29 23:59 | Completed | 7.4981e+17 | 708232745 | 7.4981e+17 | 2024-01-31 13:27 | 29 | 1 | On Time | 7.4981e+17 | 7.4981e+17
IIFL SAMASTA - IMS Enhancement 3.5 | Milestone One-Advance Payment for IMS Enhancement 3.5 Zoho creator Change request | Uday Desai | 2024-02-21 | 2024-02-23 23:59 | Completed | 7.4981e+17 | 43003637 | 7.4981e+17 | 2024-02-20 16:46 | 3 | 13 | Late | 7.4981e+17 | 7.4981e+17