## Sheet1
Task ID | Task Name | Owner | Priority | Start Date | Due Date | Created Time | Status | Is Overdue | Completion Percentage | Project Name | Milestone Name | Project ID | Milestone ID | Parent Task ID | Created By ID | Owner IDs | Task Delay Time | Task Completion Mode | Actual Time Taken | Time Spent So Far | Duration_1 | Duration Unit | Rate Per Hour | Clarity Level | QC Owner
7.4981e+17 | Create Partial Invoice | Shavi Thakur | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 18:26 | To Do | Yes | 0% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Four-Financial Accounting Management System | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 3 | Late | 4 | 4 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | CEEW -Daily Team Catchup | Stuti S. Kulshrestha | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 09:41 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 3 | Late | 4 | 4 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Auto populate Business Description and References | Pavan S | None | 2024-03-16 14:15 | 2024-03-16 18:30 | 2024-03-16 14:11 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 845599619 | 845599619 | 2 | Late | 3 | 3 | 4.25 | hrs |  | Not Clear
7.4981e+17 | OEM and Prod Category Reports | Achyuth T M | High | 2024-03-15 09:30 | 2024-03-22 19:00 | 2024-03-15 10:27 | In Progress | No | 0% | Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | -4 | On Time | 4 | 4 | 6 | days
7.4981e+17 | Map App status with Zoho | Vikram Pai V | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 13:24 | To Do | Yes | 0% | iDATALYTCS UI PATH | None | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 845596686 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Auto populating fields based on the User input | Kalyanasundaram L,Pavan S | None | 2024-03-16 09:30 | 2024-03-16 19:00 | 2024-03-16 12:18 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 819676542845599619 | 2 | Late | 3 | 3 | 1 | days |  | Clear
7.4981e+17 | Weekly project status creation WE03/15 | Supreeth R Kalluraya | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 13:44 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 788577227 | 788577227 | 3 | Late | 4 | 4 | 1 | days |  | Clear
7.4981e+17 | Change Public Key to Oauth in Custom API | Anusuyadevi V | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 09:28 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Validate Aggregate Reports from CRM | Christina Santos | High | 2024-03-15 09:30 | 2024-03-18 19:00 | 2024-03-15 21:27 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 825341377 | 0 | On Time | 4 | 4 | 2 | days
7.4981e+17 | Zoho Not Working properly Call issue | Monik Chettiyar | None | 2024-03-15 19:00 | 2024-03-15 19:00 | 2024-03-15 17:26 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 3 | Late | 4 | 4 | 0 | days
7.4981e+17 | Transfer Order PO Add to Existing PO ( Line Item Add option & Rate revise Option Required) | Sachin Patil | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 12:57 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Status change of the general info subsection and push data into the audit log | Twinkle Gupta | None | 2024-03-13 09:30 | 2024-03-15 19:00 | 2024-03-15 10:31 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 848014979 | 848014979 | 0 | Late | 3 | 3 | 3 | days |  | Clear
7.4981e+17 | Domain Verification | M S Satya | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 09:58 | Development | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | HESPL Targets Execution Issue | Sai Krishna,Tanu Gupta | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 17:24 | To Do | Yes | 0% | AMC - VAlign | HESPL AMC - 2023 - 24 | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779790157522 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Call regarding IT issues | Kiran Shrivastav | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 15:38 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Business Description | Subash Samuthirapandiyan | None |  |  | 2024-03-14 21:13 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 770263143 | 770263143 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Creating Issue Document | Vignesh R | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 14:01 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | SMS notification to RM/RL/BM/BSM on external vendor Action | Anusha V | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-14 16:06 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Re: Issue related to the Auto Check-out_Zoho People_Ozone | Kiran Shrivastav | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-14 17:55 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Account deletion and adding in payroll - Request by Renuka | Kiran Shrivastav | None | 2024-03-14 09:30 | 2024-03-15 19:00 | 2024-03-14 13:51 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 3 | Late | 5 | 5 | 2 | days
7.4981e+17 | Total Number of Board Members field disable and Count | Pavan S | None | 2024-03-14 13:00 | 2024-03-14 14:00 | 2024-03-14 13:00 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 845599619 | 845599619 | 4 | Late | 5 | 5 | 1 | hrs |  | Not Clear
7.4981e+17 | Side Progress Bar dynamic Tick mark | Mallesh M S,Rahul S S | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 11:57 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 778475418 | 778475418830176551 | 4 | Late | 5 | 5 | 1 | days |  | Clear
7.4981e+17 | ZOHO BOOKS TRAINING | Rishikesh Gogha | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 16:49 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Client Meetings and Review | Achyuth T M,Rishikesh Gogha | High | 2024-03-14 09:30 | 2024-03-21 19:00 | 2024-03-14 16:58 | In Progress | No | 0% | Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094745115006 | -3 | On Time | 5 | 5 | 6 | days
7.4981e+17 | External Meeting with Durian Team (Customer Support) on 14 Mar 24 | Sachin Patil | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 15:22 | To Do | Yes | 0% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Zoho SalesIQ for delivering omnichannel engagement | Tanu Gupta | High | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 10:56 | In Progress | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Compilation of QuerySheet of all clients | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 09:36 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288844784545 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Phonepe zoho Call on url mismatch | Sai Krishna | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-14 09:19 | Done | No | 100% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 1 | Late | 2 | 2 | 1 | days |  | Clear
7.4981e+17 | Demo Preparation | Devaraju S J | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 09:55 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Feedback By Kris - Correction in the UI and Fields | Mallesh M S,Supreeth R Kalluraya,Kalyanasundaram L,Pavan S | None | 2024-03-04 09:30 | 2024-04-03 19:00 | 2024-03-13 21:26 | In Progress | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 7.784754187885772E35 | -16 | On Time | 15 | 15 | 23 | days
7.4981e+17 | Internal Meeting | M S Satya | None | 2024-03-13 09:30 | 2024-03-15 19:00 | 2024-03-13 23:30 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 3 | Late | 6 | 6 | 3 | days |  | Clear
7.4981e+17 | ZOho Recruit - Vedor Module Setup | Monik Chettiyar | None |  |  | 2024-03-14 11:02 | To Do | No | 0% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Approval Process issue | Nikita Srivastava | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 09:45 | In Progress | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Changes the Allocated percentage from the View allocation page | Vignesh R | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 17:28 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | Invoice Not Reflecting in Zoho Books | Swetha K | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 16:25 | In Progress | Yes | 0% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Ozone Entertainments ¦ Weekly Scrum Meeting | Rishikesh Gogha | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 16:34 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | CPL Complaint flow Demo | Ranjana Poojari,Anusha V | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 16:59 | In Progress | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 778475421795545761 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | CEEW ¦ Confirmation on Resource Re-allocation View | Tanu Gupta | High | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 14:43 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 5 | Late | 6 | 6 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Dc Status Report - Need Gate Entry raised & Gate entry Balance Qty | Sachin Patil | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 15:14 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Boldfit ¦ Weekly Status Call | Rishikesh Gogha | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 14:35 | To Do | Yes | 0% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 5 | Late | 6 | 6 | 1 | days |  | Not Clear
7.4981e+17 | Client call for servetel calling issu | Tanu Gupta | High | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 12:07 | To Do | Yes | 0% | (BoldFit) Sasvat_Zoho One | Milestone Four-Implementation of Zoho CRM Application | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 5 | Late | 6 | 6 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Zoho Recruit Revamp Team call1234567890 | Kiran Shrivastav | None | 2024-02-20 09:30 | 2024-02-29 19:00 | 2024-03-13 09:25 | In Progress | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 18 | Late | 28 | 28 | 8 | days
7.4981e+17 | Create Stock Adj Records for FG and Raw Material Saperately | Shavi Thakur | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 18:28 | To Do | Yes | 0% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Four-Financial Accounting Management System | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 6 | Late | 7 | 7 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Branch master create and integrate | Tanu Gupta | Medium | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 13:59 | Development Complete | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 6 | Late | 7 | 7 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Changes in Project Discovery | Mohammed Yusha,Tanu Gupta | High | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 16:30 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265790157522 | 1 | Late | 2 | 2 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Type of Investors | unassigned | None |  |  | 2024-03-12 21:37 | Ready for QC | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 770263143 | - |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | ZOho CRM Template creation for USD | unassigned | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 17:23 | To Do | Yes | 0% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | - | 6 | Late | 7 | 7 | 1 | days |  | Clear
7.4981e+17 | Zoho Payroll to ZOho people Employee Data Sync Error | Monik Chettiyar | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 15:05 | To Do | Yes | 0% | AMC - VAlign | FARM INDIA IMPEX ¦ Books, Creator, People, Payroll & Analytics ¦ 8-12-23 to 7-12-24 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Requirement gathering & Customer Meeting | P Renuka Choudhary,Naveen M,Manish | None |  |  | 2024-03-13 13:33 | To Do | No | 0% | Sales Activities | None | 7.4981e+17 | 7.4981e+17 |  | 829366386 | 765907894,829366386,833052784 |  | On Time |  | 0 | 0 | days |  | Not Clear
7.4981e+17 | Proposal Preparation | P Renuka Choudhary,Naveen M | None |  |  | 2024-03-13 13:21 | In Progress | No | 0% | Sales Activities | None | 7.4981e+17 | 7.4981e+17 |  | 829366386 | 765907894,829366386 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Client Call on feedback points | Sai Krishna,Aishwarya T,Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 11:04 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779,772989157,808004288,844784545 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | Bulk message feasibility check | Rajesh Shindagi | Medium | 2024-03-13 09:30 | 2024-03-15 19:00 | 2024-03-13 10:10 | In Progress | Yes | 10% | StaffDocs | None | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 3 | Late | 6 | 6 | 3 | days |  | Clear | Dharanidharan C
7.4981e+17 | Develop Bot to migrate exceptional data given by Zoho | Prableen Kaur | None | 2024-03-25 09:30 | 2024-03-26 19:00 | 2024-03-12 19:14 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 792886644 | 792886644 | -8 | On Time | -6 | -6 | 2 | days
7.4981e+17 | Journey Setup in MA, Testing & Support Team Sessions | Anusha V | High | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-12 14:30 | To Do | Yes | 0% | QUICK HEAL - Zoho CRM & Zoho Marketing Automation | Milestone One-Advance Payment for Project Initiation | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | add client script to fetch the subform fields | Nikita Srivastava | None |  |  | 2024-03-13 15:34 | To Do | No | 0% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Daily stand-up call with Mellow team | Deepa Hireholi | None |  |  | 2024-03-13 12:29 | To Do | No | 0% | V-Align Marketing Activites | None | 7.4981e+17 | 7.4981e+17 |  | 800651184 | 800651184 |  | On Time |  | 0 | 0 | days |  | Not Clear
7.4981e+17 | Worked on building the project assigned to us by trainer | Amrutha H V | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 10:08 | In Progress | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 845600661 | 845600661 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Multi SSF OMS V2 - Mindspark Product | Ayush Singh | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 09:24 | In Progress | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Invoice Creation and opening balance/S | Shiwani Kumari | None |  |  | 2024-03-12 13:56 | To Do | No | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Write script to create empty columns in the modules | Vikram Pai V | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 16:28 | To Do | Yes | 0% | iDATALYTCS UI PATH | None | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 845596686 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | ZOho Approval Process | Monik Chettiyar | None | 2024-03-13 19:00 | 2024-03-13 19:00 | 2024-03-13 13:16 | To Do | Yes | 0% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 5 | Late | 6 | 6 | 0 | days
7.4981e+17 | Reference - Function Creation for Insert record - Recertification Process | Amrutha H V | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 11:33 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 778475418 | 845600661 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | Payment knock-off solution Demo | Waheeba Khan | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 11:26 | To Do | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Demo Preparation | Devaraju S J | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 09:45 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | CTW ¦ Schedule for Zoho Desk Training Session and Weekly Scrum Meetings | Tanu Gupta | High | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 16:28 | Discovery Phase | Yes | 0% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Daily meeting updations | Mary Nisha | High | 2024-03-13 09:30 | 2024-04-30 19:00 | 2024-03-13 18:19 | In Progress | No | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | -43 | On Time | 6 | 6 | 35 | days
7.4981e+17 | Real-time TAT, call AVG, customer rating, spare process status, complaints, and so on | Siddharth Sharma | None |  |  | 2024-03-13 10:22 | To Do | No | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Create Digital Badge Landing Page | unassigned | None | 2024-03-12 09:30 | 2024-03-19 19:00 | 2024-03-12 21:51 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | - | -1 | On Time | 7 | 7 | 6 | days
7.4981e+17 | Issues and Clarification | Vignesh R | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 18:34 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Daily Scrum Call with samasta | Swetha K | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 10:34 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Revised - Gantt Chart | Mohammed Yusha | None | 2024-03-12 09:30 | 2024-03-13 19:00 | 2024-03-12 10:44 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 5 | Late | 7 | 7 | 2 | days |  | Clear
7.4981e+17 | Books -Expense Gantt Chart Updation | Stuti S. Kulshrestha | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 11:04 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Add Business Information section in audit log page and its sub sections | Maninder Singh | None | 2024-03-12 09:30 | 2024-03-13 19:00 | 2024-03-12 10:59 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 782721491 | 782721491 | 5 | Late | 7 | 7 | 2 | days |  | Clear
7.4981e+17 | Business Information forms validation | Pavan S | None | 2024-03-12 09:30 | 2024-03-12 14:00 | 2024-03-12 09:45 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 845599619 | 845599619 | 6 | Late | 7 | 7 | 4.5 | hrs |  | Not Clear
7.4981e+17 | Leads Module automations and workflows Review | Dharanidharan C | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-11 19:22 | To Do | Yes | 0% | Right Horizons Financial Services Pvt Ltd. - Zoho CRM, Creator, Analytics | None | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Entertainment Application & Reimbursement Approval For HOD - Issue | Mohammed Yusha | None | 2024-03-11 09:30 | 2024-03-12 19:00 | 2024-03-11 16:49 | To Do | Yes | 0% | Mitsubishi Elevator: Zoho Creator | Sales Module | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 6 | Late | 8 | 8 | 2 | days |  | Clear
7.4981e+17 | Bills - Related List | Rishikesh Gogha | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-12 10:02 | To Do | Yes | 0% | AMC - VAlign | DEFSPACE_AMC_Zoho Books_09-02-2024 to 08-02-2025 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | MA setup for Quickheal | Anusha V | High | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-12 09:34 | To Do | Yes | 0% | QUICK HEAL - Zoho CRM & Zoho Marketing Automation | Milestone One-Advance Payment for Project Initiation | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Certification Staffer-Dashboard Creation and other Field creations | Aman Kumar | None |  |  | 2024-03-11 17:14 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Demo Preparation | Waheeba Khan,Devaraju S J | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 09:44 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 671373250,844783967 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Test CSAT/DSAT scores needs to be delete | Tanu Gupta | Medium | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 17:44 | Done | No | 100% | AMC - VAlign | Synup Digital Pvt Ltd - Zoho CRM & Desk ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | OLL BOM | Ranjana Poojari | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 10:13 | Done | No | 100% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 3 | Late | 4 | 4 | 1 | days |  | Clear
7.4981e+17 | Automation of Create Customer in Creator and Books - Custom API | Anusuyadevi V | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 09:29 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Test use Case for Documents | Waheeba Khan | None |  |  | 2024-03-11 17:08 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Communicate Roll out plan to users | Dharanidharan C,Hiren Vakharia | None | 2024-03-11 09:30 | 2024-03-19 19:00 | 2024-03-11 14:24 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504,811424903 | -1 | On Time | 8 | 8 | 7 | days
7.4981e+17 | Deletion of UAT test records | Dharanidharan C | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-11 14:18 | To Do | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Updated Email Templates Configuration in CRM | Dharanidharan C | None | 2024-03-11 19:00 | 2024-03-19 19:00 | 2024-03-11 14:08 | In Progress | No | 30% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | -1 | On Time | 8 | 8 | 6 | days
7.4981e+17 | Internal Meetings and Discussions | Aman Kumar | None |  |  | 2024-03-11 11:30 | In Progress | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Requirements call/ effort hours estimation - 3.75 | Swetha K | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 10:13 | To Do | Yes | 0% | IIFL SAMASTA - IMS Enhancement 3.5 | Milestone Two-Zoho Creator: Customization, Configuration, Testing and Go-Live of IMS enhancement | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Scheduler for auth token for expense creation | Siddharth Sharma | None |  |  | 2024-03-11 09:04 | To Do | No | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Feb Month Payroll | Kiran Shrivastav | None | 2024-03-08 09:30 | 2024-03-11 19:00 | 2024-03-08 17:14 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 7 | Late | 11 | 11 | 2 | days
7.4981e+17 | Davinci - Button to fetch the data form Books and update in CRM for bulk records | Ayush Singh | None |  |  | 2024-03-11 12:10 | In Progress | No | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Inventory Selection Form - Fields customizaton | Supril Jain | None | 2024-03-06 09:30 | 2024-03-12 19:00 | 2024-03-11 12:29 | Development | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 6 | Late | 13 | 13 | 5 | days
7.4981e+17 | HTML dynamic View Resource allocation view and update | Mohammed Yusha,Tanu Gupta | High | 2024-03-11 09:30 | 2024-03-12 19:00 | 2024-03-11 09:36 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 1 | Late | 3 | 3 | 2 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Going through the roadmap of full stack development | Vikram Pai V | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 10:10 | To Do | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 845596686 | 845596686 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Women's Day Celebration/S | Shiwani Kumari | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 18:28 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Issue in production | Vignesh R | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 10:51 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Create Comms Method for Service Interruptions or Enhancements to Active Users | Christ Bellarmine | None | 2024-03-08 09:30 | 2024-03-15 19:00 | 2024-03-10 09:03 | To Do | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 | 3 | Late | 11 | 11 | 6 | days
7.4981e+17 | Set User Roles and Permissions | Selva Bharathi | None | 2024-03-26 09:30 | 2024-03-26 19:00 | 2024-03-08 21:52 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 701368573 | -8 | On Time | -7 | -7 | 1 | days
7.4981e+17 | Create Step by Step Training Materials for Internal Use | Dharanidharan C | None | 2024-03-11 09:30 | 2024-03-19 19:00 | 2024-03-08 20:39 | To Do | No | 50% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 701371504 | -1 | On Time | 8 | 8 | 7 | days
7.4981e+17 | User Issue Resolution | M S Satya | None | 2024-03-08 09:30 | 2024-03-15 19:00 | 2024-03-11 13:18 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 3 | Late | 11 | 11 | 6 | days |  | Clear
7.4981e+17 | Preparation of opening Template and Demo | Devaraju S J | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 11:49 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 7 | Late | 8 | 8 | 1 | days |  | Clear
7.4981e+17 | Internal discussion for issue with phonepe url | Sai Krishna,Tanu Gupta | High | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 10:08 | In Progress | Yes | 0% | Namma Sampradaya_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 753339779,790157522 | 7 | Late | 8 | 8 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | r&d the webtab | Nikita Srivastava | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 16:10 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | AWS and Java project understanding for MBE search | Anas Ahmed | None |  |  | 2024-03-08 15:03 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Data and Document mapping for RMSDC | Supreeth R Kalluraya | None | 2024-03-08 09:30 | 2024-03-15 19:00 | 2024-03-08 13:57 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 788577227 | 788577227 | 3 | Late | 11 | 11 | 6 | days |  | Clear
7.4981e+17 | Zoho Books PPT Review | Stuti S. Kulshrestha | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 10:05 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Develop Pricing Matrix for Application form, subscription service, GI and Checkmate | Kris Oswold | None | 2024-01-18 09:30 | 2024-03-12 19:00 | 2024-03-07 22:53 | In Progress | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 824545238 | 6 | Late | 61 | 61 | 39 | days
7.4981e+17 | Upload GI & RMSDC Wave1 Documents to Teams Drive | Albert Diaz | None | 2024-03-08 09:30 | 2024-03-11 19:00 | 2024-03-07 21:59 | To Do | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 809116687 | 7 | Late | 11 | 11 | 2 | days
7.4981e+17 | Perform Data Migration of Sample Supplier's Data from Adaptone to Zoho Development env | Christ Bellarmine,Prableen Kaur | None | 2024-03-07 09:30 | 2024-03-11 19:00 | 2024-03-07 21:49 | In Progress | Yes | 80% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486,792886644 | 7 | Late | 12 | 12 | 3 | days
7.4981e+17 | Perform data transformation based on pre-defined rules | unassigned | None | 2024-02-28 09:30 | 2024-03-07 19:00 | 2024-03-07 21:13 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | - | 0 | Late | 9 | 9 | 7 | days
7.4981e+17 | Management & Controls Section- Creation of fields in HTML | Aman Kumar | None |  |  | 2024-03-07 20:35 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Weekly Scrum Meeting - Mar 2024 | Mohammed Yusha,Vignesh R,Sai Krishna,Tanu Gupta | High | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 14:02 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,704175602,753339779,790157522 | 11 | Late | 12 | 12 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | For the probation extension- The correct review date | Kiran Shrivastav | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 09:30 | To Do | Yes | 0% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Mail follow-up with clients and Zoho Team for various projects (Gofibo, Verto, CTW, Ozone) | Tanu Gupta | High | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 14:18 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Working on creating a PPT for the assignment assigned by Uday Sir | Vikram Pai V | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 12:55 | Done | No | 100% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 845596686 | 845596686 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Zoho CLI & Call Connectivity issue#5974 | Monik Chettiyar | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-08 11:42 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | Used Budget Back Updating and Testing | Ranjana Poojari | None |  |  | 2024-03-08 10:28 | Done | No | 100% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Management and Control Section Form Creation | Kalyanasundaram L,Amrutha H V | None |  |  | 2024-03-08 09:35 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 819676542,845600661 |  | On Time |  | 0 | 0 | days |  | Clear | Selva Bharathi
7.4981e+17 | Application Form - Creator Development | Kalyanasundaram L,Pavan S,Amrutha H V | None | 2024-03-01 09:30 | 2024-03-08 19:00 | 2024-03-08 09:24 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542,845599619,845600661 | 10 | Late | 18 | 18 | 6 | days |  | Clear
7.4981e+17 | Drilldown option to understand the customer name & product name | Vishnu D A,Nirmalkrishnan H | None | 2024-03-07 09:30 | 2024-03-07 10:30 | 2024-03-07 12:48 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 838472289 | 838472289,840979277 | 11 | Late | 12 | 12 | 1 | hrs |  | Not Clear
7.4981e+17 | Connecting Catalyst to Nodejs and uploading on serverless architecture | Anas Ahmed | None |  |  | 2024-03-08 09:55 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Ownership Details: Company | Subash Samuthirapandiyan | None |  |  | 2024-03-07 20:01 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 770263143 | 770263143 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Zoho crm custom button code changes | Monik Chettiyar | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 17:28 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | Date correction ¦ Danish Appointment letter | Monik Chettiyar | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-07 12:23 | Done | No | 100% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | ZOho Desk Api INtgration Curl Testing | Monik Chettiyar | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-07 12:18 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | NMSDC Daily standup meeting Evening | Maninder Singh | None | 2024-03-08 09:30 | 2024-04-30 19:00 | 2024-03-08 10:58 | To Do | No | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | -43 | On Time | 11 | 11 | 38 | days
7.4981e+17 | Working on creation of presentation given by Uday sir | Vikram Pai V | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 09:45 | Done | No | 100% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 845596686 | 845596686 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Review Summary Page - Dynamic | Aman Kumar,Twinkle Gupta | None | 2024-03-12 09:30 | 2024-03-13 19:00 | 2024-03-07 19:14 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 839251991,848014979 | 5 | Late | 7 | 7 | 2 | days
7.4981e+17 | Pushing Data from Subsection form to Certificate(MBE Search) Module | Subash Samuthirapandiyan | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-07 15:37 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 770263143 | 6 | Late | 7 | 7 | 1 | days |  |  | Selva Bharathi
7.4981e+17 | Working on UAT Feedbacks | Nirmalkrishnan H | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 10:32 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 840979277 | 840979277 | 10 | Late | 11 | 11 | 1 | days |  | Clear | Siddharth Sharma
7.4981e+17 | Zoho expensess Training | Devaraju S J | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 19:14 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | RMSDC Data Analysing/Mapping/Transforming/Creating exception report | Prableen Kaur | None | 2024-02-19 09:30 | 2024-03-28 19:00 | 2024-03-07 15:57 | In Progress | No | 0% | iDATALYTCS UI PATH | None | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | -10 | On Time | 29 | 29 | 29 | days
7.4981e+17 | KRI Dashboard Changes Support | Anusha V | None | 2024-03-06 09:30 | 2024-03-26 19:00 | 2024-03-07 15:10 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | -14 | On Time | 7 | 7 | 15 | days
7.4981e+17 | Mark vendor as active | Swetha K | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 11:57 | Done | No | 100% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | If it is a key account : A task to visit the customer every 15 days A task to call every week | M S Satya | None | 2024-03-04 09:30 | 2024-03-15 19:00 | 2024-03-07 09:26 | In Progress | Yes | 10% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 3 | Late | 15 | 15 | 10 | days |  | Clear
7.4981e+17 | BikenBikers - Internal call with Manish regarding Zoho Inventory feasibilities | Tanu Gupta,Manish | High | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-06 20:43 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522,833052784 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Video manuals for bank upload & phonePe upload | Sai Krishna,Tanu Gupta | High | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 20:31 | In Progress | Yes | 10% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 753339779,790157522 | 12 | Late | 13 | 13 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Creating Test Leads and deals | Ayush Singh | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-07 09:18 | QA level 1 Completed | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 12 | Late | 13 | 13 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Zoho CRM& Books Integration Flow Call | Stuti S. Kulshrestha | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 15:34 | Done | No | 100% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Deals, Account and Contact Imports | Ayush Singh | None | 2024-03-05 09:30 | 2024-03-06 19:00 | 2024-03-06 13:30 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 12 | Late | 14 | 14 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Zoho People New Form for file management | Monik Chettiyar | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 10:52 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Configuration of deal stages and task automation for these stages | M S Satya | None | 2024-03-04 09:30 | 2024-03-08 19:00 | 2024-03-06 09:58 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 10 | Late | 15 | 15 | 5 | days |  | Clear | Dharanidharan C
7.4981e+17 | New Joiner Leave balance Issue | Kiran Shrivastav | None | 2024-03-06 09:30 | 2024-03-07 19:00 | 2024-03-06 09:30 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 11 | Late | 13 | 13 | 2 | days
7.4981e+17 | Updating the Reporting hierarchy manually in the emp master is tedious. | Siddharth Sharma | None |  |  | 2024-03-07 09:05 | To Do | No | 0% | Agappe - Zoho CRM Revamp Project | Milestone Two-Implementation of Zoho CRM - Sales & Service Management Application | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Inventory Enabling for non inventory Items | Rishikesh Gogha | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-06 10:11 | Done | No | 100% | AMC - VAlign | DEFSPACE_AMC_Zoho Books_09-02-2024 to 08-02-2025 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Multiple COA Pushing to Zoho Expense and creaating new Policy for Operation team | Rishikesh Gogha | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-06 10:03 | To Do | Yes | 0% | Airowire - Zoho Expense | None | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Data Migration Flow | Stuti S. Kulshrestha | None | 2024-03-07 09:30 | 2024-03-08 19:00 | 2024-03-07 10:22 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 10 | Late | 12 | 12 | 2 | days |  | Clear
7.4981e+17 | Meeting (with Durian Team) to integrate new Guwahati Store campaign WordPress form with Zoho CRM | Sachin Patil | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 17:41 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Validation on Sales Return and Sales Return Items(Audit) | Sachin Patil | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 15:10 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-26 09:30 | 2024-03-15 19:00 | 2024-03-06 13:29 | Done | No | 100% | Machani Dedicated Resource extension | Milestone One-Dedicated Resource for March 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | -4 | On Time | 15 | 15 | 15 | days
7.4981e+17 | While conversion of Lead to Deal, Positions and products are coming on quick view, which should only come while engagement type is Products | Aishwarya T | None |  |  | 2024-03-06 12:34 | To Do | No | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 |  | On Time |  | 0 | 0 | days |  | Clear | Irshad Pasha
7.4981e+17 | Client call for testing of scorecard and related queries | Tanu Gupta | High | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-06 09:29 | In Progress | Yes | 10% | IIFL Samasta Zoho Creator Score Card Enhancement | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 13 | Late | 14 | 14 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Internal meeting with Team lead | Omprakash Kumar | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-03-05 13:57 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 845321609 | 845321609 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | MBE_Search_API | Omprakash Kumar | None | 2024-02-27 09:30 | 2024-03-11 19:00 | 2024-03-05 13:44 | In Progress | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 845321609 | 845321609 | 7 | Late | 21 | 21 | 10 | days
7.4981e+17 | Release/Demo of Application Submission Process | Selva Bharathi,Supreeth R Kalluraya | None | 2024-02-23 09:30 | 2024-03-20 19:00 | 2024-03-04 21:35 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573,788577227 | -2 | On Time | 25 | 25 | 19 | days
7.4981e+17 | Documents Report Creation | Mallesh M S,Aman Kumar,Pavan S | None | 2024-03-04 09:30 | 2024-03-07 19:00 | 2024-03-04 21:35 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 778475418,839251991,845599619 | 11 | Late | 15 | 15 | 4 | days
7.4981e+17 | Creation of Email Templates | Mallesh M S | None | 2024-03-05 09:30 | 2024-03-06 19:00 | 2024-03-04 21:35 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 778475418 | 12 | Late | 14 | 14 | 2 | days
7.4981e+17 | Automation - Storing and Populate Data | Mallesh M S,Kalyanasundaram L | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 21:35 | Ready for QC | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 778475418,819676542 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Summary Form UI | Rahul S S | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-04 21:35 | Ready for QC | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 830176551 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | Applicant Dashboard Dynamic | Mallesh M S | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 21:35 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 778475418 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | SMS Template Configuration on Installation Templates | unassigned | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 13:21 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 840979277 | - | 12 | Late | 13 | 13 | 1 | days |  | Clear
7.4981e+17 | Custom Bill Integration & Purchase Management | Mohammed Yusha | None | 2024-03-05 09:30 | 2024-03-06 19:00 | 2024-03-05 19:27 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Three-Order Management System | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 1 | Late | 3 | 3 | 2 | days |  | Clear
7.4981e+17 | Integration of ZOHO Books and ZOHO CRM | Devaraju S J | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 18:37 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Check working of Invoice Subform (Invoice Items) Cancel | Sachin Patil | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 19:42 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | Feasibility Check - Field Depenancy on New Fields | Sachin Patil | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 19:34 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | Zoho Payroll training to Jyothi | Kiran Shrivastav | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 20:26 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | ER2 OLL BOM | Kalyanasundaram L | None | 2024-03-05 09:30 | 2024-03-08 19:00 | 2024-03-05 11:17 | In Progress | Yes | 10% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 10 | Late | 14 | 14 | 4 | days |  | Clear
7.4981e+17 | CPC AMC Feb-24 | Sai Krishna | None | 2024-02-01 09:30 | 2024-02-29 19:00 | 2024-03-04 14:27 | To Do | Yes | 0% | AMC - VAlign | Columbia Pacific Communities | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 18 | Late | 47 | 47 | 21 | days
7.4981e+17 | Client Visit 19-Feb | Sai Krishna | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-03-04 14:05 | Done | No | 100% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 14 | Late | 15 | 15 | 1 | days |  | Clear
7.4981e+17 | Feasibility Check for Enhancement in Lead Generator App | Anusha V | None | 2024-03-06 09:30 | 2024-03-26 19:00 | 2024-03-07 09:43 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | -14 | On Time | 7 | 7 | 15 | days
7.4981e+17 | Business Aquisation | Subash Samuthirapandiyan | None |  |  | 2024-03-06 21:23 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 770263143 | 770263143 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Atlas Distribution -D | Devaraju S J | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 18:49 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Issue in TCS SO and Invoice flow | Vignesh R | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 14:05 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Zoho People Page setup in Zoho Creator for Invoice and Requisition form | Aishwarya T | None | 2024-03-05 09:30 | 2024-03-15 19:00 | 2024-03-05 16:12 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | -1 | On Time | 10 | 10 | 9 | days |  | Clear | Sai Krishna
7.4981e+17 | Hands on experience on serverless architecture | Mohak Tripathi | None |  |  | 2024-03-05 13:38 | In Progress | No | 10% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 843614429 | 843614429 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Knowledge Transfer MBE search through Catalayst | Mohak Tripathi | None |  |  | 2024-03-05 13:27 | In Progress | No | 10% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 843614429 | 843614429 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Correct bugs on text search | Anas Ahmed | None |  |  | 2024-03-05 10:27 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Approval Master Set up configuration | Sai Krishna,Aishwarya T | None | 2024-03-04 09:30 | 2024-03-15 19:00 | 2024-03-04 17:59 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 3 | Late | 15 | 15 | 10 | days |  | Clear | Sai Krishna
7.4981e+17 | SO Bonded Flow Changes & PO Location Updations | Waheeba Khan,Ranjana Poojari,Anusha V | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-03-05 19:24 | In Progress | Yes | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 671373250,778475421,795545761 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Zoho Books Solutioning - A& C | Supril Jain,Stuti S. Kulshrestha | None | 2024-03-05 11:00 | 2024-04-30 13:00 | 2024-03-05 17:12 | Done | No | 100% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 756836914,808004288 | -55 | On Time | 2 | 2 | 382 | hrs
7.4981e+17 | Support for Issue on email forwarding and ticket notification | Tanu Gupta | High | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-05 12:26 | Done | No | 100% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | TDS amount round off to higher digit | Swetha K | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-05 10:00 | Done | No | 100% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 3 | Late | 4 | 4 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Task Allocation Meeting with Shiwani | Stuti S. Kulshrestha,Shiwani Kumari | None |  |  | 2024-03-05 09:38 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288,844784545 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Sick leave | Nikita Srivastava | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-05 09:14 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Review Meeting with CEO-D | Devaraju S J | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 19:03 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Phone Number Change OTP Verification.->Select Profile-> Verify OTP | Sai Krishna | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-03-04 14:11 | Done | No | 100% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 12 | Late | 13 | 13 | 1 | days |  | Clear
7.4981e+17 | Creation of Email Templates and notifications | Twinkle Gupta | None | 2024-03-21 09:30 | 2024-03-28 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -10 | On Time | -2 | -2 | 6 | days
7.4981e+17 | Creation of Dashboard for update requested | Twinkle Gupta | None | 2024-03-22 09:30 | 2024-03-26 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -8 | On Time | -3 | -3 | 3 | days
7.4981e+17 | User Roles and Permission setup | Twinkle Gupta | None | 2024-03-25 09:30 | 2024-03-29 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -11 | On Time | -6 | -6 | 5 | days
7.4981e+17 | Creation of Email Templates | Twinkle Gupta | None | 2024-03-22 09:30 | 2024-03-22 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -4 | On Time | -3 | -3 | 1 | days
7.4981e+17 | Completion of Management Employee Form | Aman Kumar | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-04 21:27 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 839251991 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | SLA Rules And Escalation Notifications | Twinkle Gupta | None | 2024-03-11 09:30 | 2024-03-14 19:00 | 2024-03-04 21:27 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | 4 | Late | 8 | 8 | 4 | days
7.4981e+17 | View , Update comment , old inputs for owner wise | Maninder Singh | None | 2024-03-06 09:30 | 2024-03-12 19:00 | 2024-03-04 21:27 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 782721491 | 6 | Late | 13 | 13 | 5 | days
7.4981e+17 | UI-View Old Inputs/ New Inputs Comparision | Rahul S S | None | 2024-03-06 09:30 | 2024-03-07 19:00 | 2024-03-04 21:27 | QC Passed | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 830176551 | 11 | Late | 13 | 13 | 2 | days
7.4981e+17 | RMSDC Allocation Logic | Twinkle Gupta | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-04 21:27 | Development Complete | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Completion of reports required for Application Allocation | Twinkle Gupta | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-04 21:27 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Validation for application allocation notifications with required email templates | Aman Kumar | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-04 21:27 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 839251991 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Creation of Form and of Zip code allocation | Twinkle Gupta | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-04 21:27 | QC Passed | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Filed level validation in Task | Vignesh R | None | 2024-03-04 09:30 | 2024-03-06 19:00 | 2024-03-05 23:01 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 12 | Late | 15 | 15 | 3 | days |  | Clear
7.4981e+17 | offer letter error | Monik Chettiyar | None | 2024-03-05 19:00 | 2024-03-05 19:00 | 2024-03-05 13:32 | To Do | Yes | 0% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 13 | Late | 14 | 14 | 0 | days
7.4981e+17 | Email Customization and HTML Attachment template customization | Aishwarya T,Ayush Singh | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 20:07 | In Progress | Yes | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772989157,772908679 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Copy-Paste functionality | Avinash Sah | None |  |  | 2024-03-04 15:01 | In Progress | No | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Page for Purchase Reqisition | Aishwarya T | None | 2024-03-01 09:30 | 2024-03-15 19:00 | 2024-03-04 12:25 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | -8 | On Time | 7 | 7 | 11 | days |  | Clear | Sai Krishna
7.4981e+17 | UAT Support(Milestone 4) | Shavi Thakur | None | 2024-03-01 17:30 | 2024-03-04 17:30 | 2024-03-03 21:29 | To Do | Yes | 0% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Three-Order Management System | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 14 | Late | 18 | 18 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Sampling Document | Devaraju S J | None | 2024-03-01 19:00 | 2024-03-01 19:00 | 2024-03-01 18:23 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 17 | Late | 18 | 18 | 0 | days
7.4981e+17 | Geographic Market Select One Functionality | Avinash Sah | None |  |  | 2024-03-01 12:52 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Fixing bugs and correcting copy paste | Anas Ahmed | None |  |  | 2024-03-04 10:51 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Unique customer met ( based on a minimum of 130 high-potential customers per month | Siddharth Sharma | None |  |  | 2024-03-04 08:53 | To Do | No | 0% | Agappe - Zoho CRM Revamp Project | Milestone Two-Implementation of Zoho CRM - Sales & Service Management Application | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Balance Qty - Push to GRN Qty, Balance Qty and Order Qty, and GRN Bl Qyt will be hiddedn and Qty have edit access, and Validation If Qty is greater than bl qty then show alert | Aishwarya T | None | 2024-02-28 09:30 | 2024-03-01 19:00 | 2024-03-01 10:33 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 6 | Late | 9 | 9 | 3 | days |  | Clear | Sai Krishna
7.4981e+17 | Business Group and Designation and GRN button on PO and auto update of po details in GRN module | Sai Krishna,Aishwarya T | None | 2024-02-27 09:30 | 2024-02-29 19:00 | 2024-03-01 10:26 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 7 | Late | 10 | 10 | 3 | days |  | Clear | Sai Krishna
7.4981e+17 | Hide Payment schedule from purchase requisition form and Hide Place of supply field (Text Field) from purchase requisition form,and Make a lookup field from state master module in Purchase Requisition and Vendor Onboarding Form | Sai Krishna,Aishwarya T | None | 2024-02-27 09:30 | 2024-02-29 19:00 | 2024-03-01 10:19 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 7 | Late | 10 | 10 | 3 | days |  | Clear | Sai Krishna
7.4981e+17 | Scrum Call WE 29/02/2024 | Stuti S. Kulshrestha | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 15:08 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 7 | Late | 8 | 8 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Changes In Invoice template. | Basavaraj Patil | None | 2024-02-05 09:30 | 2024-03-08 19:00 | 2024-03-01 17:00 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | None | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 10 | Late | 43 | 43 | 25 | days |  | Clear | Waheeba Khan
7.4981e+17 | requirement gathering - System study session 1 | Dharanidharan C,Achyuth T M | None |  |  | 2024-03-01 12:48 | To Do | No | 0% | Right Horizons Financial Services Pvt Ltd. - Zoho CRM, Creator, Analytics | Milestone Two-System study of Creator, Analytics, CRM | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504,708853094 |  | On Time |  | 0 | 0 | days
7.4981e+17 | UAT release 2 and updates | Dharanidharan C | None | 2024-02-01 09:30 | 2024-02-29 19:00 | 2024-03-01 12:40 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 18 | Late | 47 | 47 | 21 | days |  | Clear
7.4981e+17 | Bank Integration ISSSUE | Rishikesh Gogha | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-03-04 10:23 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Zoho Books Templates and Request for Clarifications - Regarding | Rishikesh Gogha | None |  |  | 2024-03-04 09:47 | To Do | No | 0% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Dhyan Ventures - Zoho Books & Inventory Demo call | Tanu Gupta | High | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-02 15:46 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | In the Sales Order, Invoice and Check Sheet is created for sales order then not allow to add or update item | Sachin Patil | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-01 19:32 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | Zoho Desk Accounts issue on tickets module | Monik Chettiyar | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 20:32 | Done | No | 100% | AMC - VAlign | Non AMC Project Tasks | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Import Customer Address Details to Zoho Creator | Sachin Patil | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-02-29 19:38 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 17 | Late | 19 | 19 | 2 | days |  | Clear
7.4981e+17 | Customer Weekly Standup Meeting | Vignesh R | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-29 14:57 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Change status of TE - 202400191 and TE - 202400190 | Maninder Singh | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-01 13:03 | Done | No | 100% | AMC - VAlign | EI - Zoho One Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | #6018 Issue with Chat Leads in CRM for Sales Team | Maninder Singh | Low | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-01 09:32 | Done | No | 100% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Create IRP | Devaraju S J | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 17:55 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 18 | Late | 19 | 19 | 1 | days
7.4981e+17 | ZOHO Expense: Training for sales team | Rishikesh Gogha | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-03-01 09:55 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 18 | Late | 19 | 19 | 1 | days
7.4981e+17 | Changes in Item master and sub category and quote line items | Tanu Gupta | High | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 21:35 | Development | Yes | 90% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 18 | Late | 19 | 19 | 1 | days
7.4981e+17 | Creating and correcting UI according to the Search | Anas Ahmed | None |  |  | 2024-02-29 19:35 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | PDF generation and image issue | Anas Ahmed | None |  |  | 2024-02-29 19:31 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | MBE Search - UI creation for data | Anas Ahmed | None |  |  | 2024-02-29 19:27 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Field validation for data types | Anas Ahmed | None |  |  | 2024-02-29 18:58 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Bug fix for all level in Tree Structure | Anas Ahmed | None |  |  | 2024-02-29 18:46 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Component Form for each node | Anas Ahmed | None |  |  | 2024-02-29 18:39 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Accumulating Data | Anas Ahmed | None |  |  | 2024-02-29 18:31 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Resignation process flow – need review from our HR team | Kiran Shrivastav | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-02-29 14:21 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 19 | 19 | 2 | days
7.4981e+17 | HQ location basis attendance Report | Kiran Shrivastav | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-02-29 14:18 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 19 | 19 | 2 | days
7.4981e+17 | Sick leave is not added for new employees | Kiran Shrivastav | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-02-29 14:18 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 19 | 19 | 2 | days
7.4981e+17 | Service Order "Deliver To" Pushing | Siddharth Sharma | None |  |  | 2024-02-29 09:22 | To Do | No | 0% | AMC - VAlign | Agappe Tickets | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Zoho Creator - Support for Ticket creation for Quote 207 and 201Zoho Desk - Zoho CRM and Zoho Contact Issue (With zoho support team) | Tanu Gupta | High | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 23:47 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 19 | Late | 20 | 20 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Airowire/S | Shiwani Kumari | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 18:24 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Client call (Deepak & Shanti & Ashwini) for Item master | Mohammed Yusha,Tanu Gupta | High | 2024-02-28 09:30 | 2024-02-29 19:00 | 2024-02-28 15:57 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Trimble/S | Shiwani Kumari | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 09:39 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Usage Report Implementation & Admin Dashboard - Analytics | Anusha V | High | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-27 21:53 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Update the Task details for all the year in month wise | Vignesh R | None | 2024-02-27 09:30 | 2024-02-28 19:00 | 2024-02-28 10:41 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 19 | Late | 21 | 21 | 2 | days |  | Clear
7.4981e+17 | Enhancements in Project Discovery and Budget Proposal | Mohammed Yusha,Tanu Gupta | High | 2024-02-26 09:30 | 2024-02-29 19:00 | 2024-02-26 19:34 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 14 | Late | 18 | 18 | 4 | days |  | Clear | Mohammed Yusha
7.4981e+17 | #5994 Restrict Survey at User Level | Tanu Gupta | High | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-26 19:24 | Done | No | 100% | AMC - VAlign | Synup Digital Pvt Ltd - Zoho CRM & Desk ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | SLA Configurations | Shavi Thakur,Tanu Gupta | High | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-26 19:05 | Done | No | 100% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 773081417,790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | TDS and sales entries | Devaraju S J | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 18:31 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | terms clarification ¦ Investment Declaration | Rishikesh Gogha | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-29 09:49 | To Do | Yes | 0% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | PO Versions | unassigned | None | 2024-02-27 09:30 | 2024-02-28 19:00 | 2024-02-29 09:23 | In Progress | Yes | 0% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778475421 | - | 19 | Late | 21 | 21 | 2 | days
7.4981e+17 | DN and CN Books Integration | Vaikuntam Chowdary | None | 2024-02-21 09:30 | 2024-02-22 19:00 | 2024-02-28 19:02 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 25 | Late | 27 | 27 | 2 | days
7.4981e+17 | User Manual Creation for Production Order | Kalyanasundaram L | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 09:49 | In Progress | Yes | 10% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 19 | Late | 20 | 20 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Budget - Clarity Client Meeting & Solution Discussion | Mohammed Yusha | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-27 19:17 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | #5298 Mr. Rajkumar Nahar is able to view the leads of other regions apart from North 2 region. Please limit his access only to view the leads for North region. Kindly treat this message as urgent. | Maninder Singh | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-27 16:25 | In Progress | Yes | 0% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Auto Tagging and Manual Tagging, Automate Rule once customer is tagged | Anusuyadevi V | None | 2024-02-27 09:30 | 2024-02-28 19:00 | 2024-02-28 20:45 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Airowire: Zoho Books Queries | Rishikesh Gogha | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-28 09:41 | To Do | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Re: ZB query related to Bank entry | Rishikesh Gogha | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-28 09:31 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | ZOho Desk API Code Creation for Update thirty party | Monik Chettiyar | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-27 19:22 | In Progress | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Employee CTC Add in Zoho payroll | Kiran Shrivastav | None | 2024-02-27 09:30 | 2024-03-01 19:00 | 2024-02-27 18:58 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 21 | 21 | 4 | days
7.4981e+17 | Update Item Category and Inventory COA from Books to Creator | Sachin Patil | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-27 18:46 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 20 | Late | 21 | 21 | 1 | days |  | Clear
7.4981e+17 | Probation Section add in Employee Form | Kiran Shrivastav | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 19:40 | To Do | Yes | 0% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Client Script for when Engagemnt type is Product, check box will be checked automatically | Aishwarya T | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-29 10:40 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 20 | Late | 21 | 21 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | Email alert required if there's any revision in the estimate to the deal owner | M S Satya | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-29 09:00 | To Do | Yes | 0% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 19 | Late | 20 | 20 | 1 | days |  | Clear
7.4981e+17 | Ozone expenses -D | Devaraju S J | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 18:03 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Trimble Information-D | Devaraju S J | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-28 09:37 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Training with Rishi | Shiwani Kumari | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-27 09:33 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Vendor Management Progress call with client | Sai Krishna,Aishwarya T | None | 2024-02-26 09:30 | 2024-03-15 19:00 | 2024-02-26 18:34 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 3 | Late | 22 | 22 | 15 | days |  | Clear | Sai Krishna
7.4981e+17 | Zoho Books Custom Function | Monik Chettiyar | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-29 00:03 | Done | No | 100% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | RA & HO Admin only should have edit access to PAF, PCF & PRF. Also, RA should have edit access after submitting the PAF only once a clarification or change request in PAF has been raised by any of the stakeholders through the workflow. | Swetha K | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-28 19:33 | Done | No | 100% | IIFL SAMASTA- Admin Module CR | Milestone One-Advance payment for Admin Module Change Request | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 16 | Late | 17 | 17 | 1 | days
7.4981e+17 | Dashboard Sharing and data restriction based on hierarchy | Achyuth T M | None | 2024-02-27 09:30 | 2024-02-29 19:00 | 2024-02-28 18:23 | Done | No | 100% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 12 | Late | 15 | 15 | 3 | days |  | Clear
7.4981e+17 | Client Call regarding user access and quote queries | Tanu Gupta | High | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-28 09:41 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 20 | Late | 21 | 21 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Email Notification - Email template once the order converted to the Sale order | Ayush Singh | None | 2024-02-12 09:30 | 2024-02-14 19:00 | 2024-02-27 17:07 | Done | No | 100% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 22 | Late | 25 | 25 | 3 | days
7.4981e+17 | ER2 MFC BOM | Kalyanasundaram L | None | 2024-02-19 09:30 | 2024-02-20 19:00 | 2024-02-27 08:40 | In Progress | Yes | 10% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 27 | Late | 29 | 29 | 2 | days |  | Clear | Selva Bharathi
7.4981e+17 | Vendor Management Demo + Books Integration | Stuti S. Kulshrestha | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 11:45 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 10 | Late | 11 | 11 | 1 | days |  | Clear
7.4981e+17 | Zoho Recruit Offer Letter 1 Rupees Error | Monik Chettiyar | None |  |  | 2024-02-23 21:26 | To Do | No | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Report Creation - Zoho CRM For Lead Module Data Uplode | Monik Chettiyar | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-23 21:11 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 40 | Late | 41 | 41 | 1 | days
7.4981e+17 | Push Payment Received back to Creator | Shavi Thakur | None | 2024-02-22 12:30 | 2024-02-22 15:00 | 2024-02-22 21:03 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 0 | Late | 1 | 1 | 2.5 | hrs
7.4981e+17 | Budget Used Back Updation and Changes | Ranjana Poojari | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-26 09:24 | Done | No | 100% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Automation -D | Devaraju S J | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 18:08 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | Portal Validation and creation | Aishwarya T | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-26 09:58 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 6 | Late | 7 | 7 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | RE: POI month update | Kiran Shrivastav | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 18:32 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Zoho Expense: Requirement Gathering | Rishikesh Gogha | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-23 09:38 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Import-Bills-D | Devaraju S J | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 18:25 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Zoho CLI & Call Connectivity issue in zoho desk and crm | Monik Chettiyar | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-26 11:21 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-22 09:30 | 2024-02-23 19:00 | 2024-02-26 09:49 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 10 | Late | 12 | 12 | 2 | days
7.4981e+17 | Field Level Changes & Schedular Functionality for WH PO Locations | Anusha V | None | 2024-02-14 09:30 | 2024-02-15 19:00 | 2024-02-23 21:26 | To Do | Yes | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 32 | Late | 34 | 34 | 2 | days
7.4981e+17 | Employee profile update for Archana and Arfath | Kiran Shrivastav | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-23 12:38 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | Entertainment Approval Issue & Client Meeting | Mohammed Yusha | None | 2024-02-22 09:30 | 2024-02-23 19:00 | 2024-02-22 18:35 | Done | No | 100% | Mitsubishi Elevator: Zoho Creator | Sales Module | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 2 | 2 | 2 | days |  | Clear
7.4981e+17 | Flow testing (Quote linked with zoho books, P&L, Revise quotation) | Tanu Gupta | High | 2024-02-23 09:30 | 2024-02-26 19:00 | 2024-02-26 10:08 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 2 | Late | 6 | 6 | 2 | days
7.4981e+17 | BetterPlace : Statement of Account Error | Rishikesh Gogha | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-26 09:36 | To Do | Yes | 0% | AMC - VAlign | Betterplace | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | R& D and Study | Stuti S. Kulshrestha | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 17:11 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 24 | Late | 25 | 25 | 1 | days |  | Clear
7.4981e+17 | Client Visit on 22-Feb-2024 | Vignesh R | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-23 09:50 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | TSD Revision | Tanu Gupta | High | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 23:21 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 790157522 | 790157522 | 25 | Late | 26 | 26 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Internal API Testing Using Postman | Vaikuntam Chowdary | None |  |  | 2024-02-23 18:41 | In Progress | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Create the custom button "Create Quote" in deal module and insert the data in quotes | Nikita Srivastava | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 17:54 | Development | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | Requirement Gathering Session 1 | Sai Krishna,Aishwarya T | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-02-23 16:11 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 41 | Late | 42 | 42 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Ocimum System Testing | M S Satya | None | 2024-02-22 09:30 | 2024-02-23 19:00 | 2024-02-22 18:16 | In Progress | Yes | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 24 | Late | 26 | 26 | 2 | days
7.4981e+17 | Vendor and Customer Creator and Books Integration | Sachin Patil | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 19:09 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 25 | Late | 26 | 26 | 1 | days |  | Clear
7.4981e+17 | Testing & Demos | Anusha V | High | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-22 09:39 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Masters Customization | Anusha V | High | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-22 09:33 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Sending Invite to Portal Users and Internal Users in Bulk | Kalyanasundaram L | None | 2024-02-21 09:30 | 2024-02-22 19:00 | 2024-02-22 09:52 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 25 | Late | 27 | 27 | 2 | days |  | Clear | Selva Bharathi
7.4981e+17 | Sync Inventory Details to Zoho Creator(Inventory) from Zoho Books | Sachin Patil | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-21 19:47 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 26 | Late | 27 | 27 | 1 | days |  | Clear
7.4981e+17 | Requirement gathering of Ozone Inc/S | Shiwani Kumari | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 09:35 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Changes in approval flow for Quotation | Tanu Gupta | High | 2024-02-21 09:30 | 2024-02-23 19:00 | 2024-02-21 11:01 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 5 | Late | 8 | 8 | 3 | days
7.4981e+17 | Weighted avg to get resource rates | Tanu Gupta | High | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-21 09:34 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 790157522 | 790157522 | 16 | Late | 17 | 17 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Go Live (Full Launch) MBE's W.2 | unassigned | None | 2024-03-11 09:30 | 2024-03-15 19:00 | 2024-02-20 22:42 | To Do | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | - | 3 | Late | 8 | 8 | 5 | days
7.4981e+17 | Client meeting for progress demo | Vignesh R,Tanu Gupta | High | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-21 15:58 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 704175602,790157522 | 2 | Late | 3 | 3 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Import Chart of accounts-D | Devaraju S J | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 18:06 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Requirement Gathering-D | Devaraju S J | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-22 09:33 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | 2-Wheeler & 4-Wheeler testing and modifications | Vaikuntam Chowdary | None | 2024-02-16 09:30 | 2024-02-20 19:00 | 2024-02-21 09:29 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 27 | Late | 32 | 32 | 3 | days |  | Clear
7.4981e+17 | Meeting Module - Validation as per Meeting Type and From date | Ayush Singh | None | 2024-02-20 09:30 | 2024-02-21 19:00 | 2024-02-21 19:44 | QA level 1 Completed | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 26 | Late | 28 | 28 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Create Brands, Brands Edition and Spare Masters Module | Nikita Srivastava | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 10:12 | Development | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Sync Composite Items to Zoho Creator(BOM) from Zoho Books | Sachin Patil | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 19:30 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 27 | Late | 28 | 28 | 1 | days |  | Clear
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-20 14:15 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Zoho Peojects and Zoho WOrkspace Integration | M S Satya | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-21 09:24 | In Progress | Yes | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | Meeting with Manish/S | Shiwani Kumari | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 18:34 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | zoho crm leads and deals module | Monik Chettiyar | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 13:18 | Done | No | 100% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Support Meeting | Monik Chettiyar | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-21 11:26 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | Page Creation For Internal User | Mallesh M S | None | 2024-02-15 09:30 | 2024-03-14 19:00 | 2024-02-21 10:33 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 4 | Late | 33 | 33 | 21 | days |  | Clear
7.4981e+17 | Zoho Recruit Revamp Team call | Kiran Shrivastav | None | 2024-02-20 09:30 | 2024-02-29 19:00 | 2024-02-20 13:59 | In Progress | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 18 | Late | 28 | 28 | 8 | days
7.4981e+17 | Create invoice template. | unassigned | None | 2024-02-06 09:30 | 2024-02-20 19:00 | 2024-02-19 18:09 | In Progress | Yes | 10% | Atlas - Zoho Creator - P & I, And OMS | None | 7.4981e+17 | 7.4981e+17 |  | 781564441 | - | 27 | Late | 42 | 42 | 11 | days |  | Clear
7.4981e+17 | PR to PO conversion function | Aishwarya T | None | 2024-02-19 09:30 | 2024-02-20 19:00 | 2024-02-19 19:04 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 16 | Late | 18 | 18 | 2 | days |  | Clear | Sai Krishna
7.4981e+17 | Approval process setup for debit notes | Sai Krishna,Aishwarya T | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-19 12:02 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 26 | Late | 27 | 27 | 1 | days |  | Clear
7.4981e+17 | Field level automation for purchase order | Aishwarya T | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 11:58 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 28 | Late | 29 | 29 | 1 | days |  | Clear
7.4981e+17 | Solution Demo | Sai Krishna,Aishwarya T | None | 2024-03-18 09:30 | 2024-03-20 19:00 | 2024-02-19 11:51 | To Do | No | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | -2 | On Time | 1 | 1 | 3 | days |  | Clear
7.4981e+17 | Field level automation for vendor onboarding form | Sai Krishna,Aishwarya T | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-19 11:21 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 33 | Late | 34 | 34 | 1 | days |  | Clear
7.4981e+17 | Tax Master | Aishwarya T | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-19 10:41 | Development Complete | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 34 | Late | 35 | 35 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Support Meeting | Monik Chettiyar | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 19:08 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | I-5-I414 cyber-ready/corporate plus issue | Prableen Kaur | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 18:33 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Enquiries coming from the website's 'Welcome Pop up' should not be converted into this deal | Sachin Patil | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 18:45 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Go betterplce kpi dashboard discussion | Nikita Srivastava | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 17:31 | In Progress | Yes | 0% | AMC - VAlign | Better Place Support Activity | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | Second 2nd Communication to Wave 1 and 2 Corp Members and RMSDC's | Stefan Bradham | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 04:43 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 836353936 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Client call | Mohammed Yusha,Tanu Gupta | High | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-19 09:33 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Invoice Sheet Preparations | Mary Nisha | None | 2024-02-20 09:30 | 2024-02-23 19:00 | 2024-02-20 10:50 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 24 | Late | 28 | 28 | 4 | days |  | Clear
7.4981e+17 | Zoho Recruit - Calendar Issue | Kiran Shrivastav | None | 2024-02-19 09:30 | 2024-02-22 19:00 | 2024-02-19 22:06 | In Progress | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 25 | Late | 29 | 29 | 4 | days
7.4981e+17 | Sync Chart of Account to Zoho Creator from Zoho Books | Sachin Patil | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 19:00 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 28 | Late | 29 | 29 | 1 | days |  | Clear
7.4981e+17 | Reports/S | Shiwani Kumari | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 18:40 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Reassign the efforts based on the un-utilized efforts | Vignesh R | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-16 20:05 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 26 | Late | 27 | 27 | 1 | days |  | Clear
7.4981e+17 | Tree Structure Development | unassigned | None |  |  | 2024-02-16 19:46 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176551 | - |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Demo Session 2/S | Shiwani Kumari | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 18:22 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | Zoho Projects New Changes | Rajesh Shindagi | None | 2024-02-16 09:30 | 2024-02-29 19:00 | 2024-02-18 14:11 | In Progress | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 18 | Late | 32 | 32 | 10 | days
7.4981e+17 | Client Meeting With Deepak On 16-02-24 | Mohammed Yusha,Tanu Gupta | High | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 19:32 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Create Sub-task under Activities | Vignesh R,Tanu Gupta | High | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-02-16 19:02 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 704175602,790157522 | 17 | Late | 18 | 18 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Resource Reallocation | Vignesh R,Tanu Gupta | High | 2024-02-20 09:30 | 2024-02-21 19:00 | 2024-02-16 18:51 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 704175602,790157522 | 26 | Late | 28 | 28 | 2 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Demo session questions and pending work-D | Devaraju S J | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 18:22 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | Vendor RM Approval - In finance report RM approval status need to update in report columns | Swetha K | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 13:08 | Done | No | 100% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 20 | Late | 21 | 21 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Client Meeting For Project Budget | Mohammed Yusha,Vignesh R,Tanu Gupta | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 19:47 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,704175602,790157522 | 4 | Late | 5 | 5 | 1 | days |  | Clear
7.4981e+17 | Master Data Templates | Mohammed Yusha,Rishikesh Gogha | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 18:26 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 701373265,745115006 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Internal Meeting-D | Devaraju S J | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 18:37 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Solutioning Incoming payments | Anusuyadevi V | None | 2024-02-16 09:30 | 2024-02-20 19:00 | 2024-02-19 11:13 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 8 | Late | 13 | 13 | 3 | days
7.4981e+17 | RCM is selected but in books reverse charge is not applied | Swetha K | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 09:31 | To Do | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 28 | Late | 29 | 29 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | External Meeting with Stellar Team for Discuss on Desk | Sachin Patil | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 19:21 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Unrealized gain/loss/S | Shiwani Kumari | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 18:15 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Manual Journal/S | Shiwani Kumari | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 18:11 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Zoho Desk ¦ user login user issue not raise it to zoho support and meeting | Monik Chettiyar | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-15 18:52 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | Contacts data migrations | Mary Nisha | None | 2024-02-15 09:30 | 2024-02-16 19:00 | 2024-02-15 15:56 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 31 | Late | 33 | 33 | 2 | days |  | Clear
7.4981e+17 | Exit Process testing | Kiran Shrivastav | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 09:27 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Support request on Re:[## 27462 ##] Admin access for Payroll Module | Kiran Shrivastav | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 13:09 | Done | No | 100% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | Payment Schedule form, Tax Master, Good Receipt Note, Payment Terms | Aishwarya T | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 19:02 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 15 | Late | 16 | 16 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Purchase Order form | Aishwarya T | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 18:58 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 15 | Late | 16 | 16 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | How to handle multicurrency in Banking/S | Shiwani Kumari | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:27 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Portal User Access UAT Preparation and Video Manual | Dharanidharan C | None | 2024-01-22 09:30 | 2024-02-20 19:00 | 2024-02-13 16:19 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 27 | Late | 57 | 57 | 22 | days |  | Clear
7.4981e+17 | Portal member Dashboard - Checkmate Page | Dharanidharan C,Mallesh M S | None | 2024-01-22 09:30 | 2024-02-16 19:00 | 2024-02-13 16:16 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504,778475418 | 31 | Late | 57 | 57 | 20 | days |  | Clear
7.4981e+17 | Approval Process - Budget Master - Budget Versions | Ranjana Poojari | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:00 | Done | No | 100% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | Call with Haqdarshak on Zoho recruit Revamp | Kiran Shrivastav | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 16:20 | To Do | Yes | 0% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Re: Implementation of Automatic Absence Notification Emails for Employees | Kiran Shrivastav | None | 2023-11-30 09:30 | 2023-11-30 19:00 | 2024-02-13 17:46 | Done | Yes | 10% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 109 | Late | 110 | 110 | 1 | days |  | Clear
7.4981e+17 | Issues in Zing Hr & CPL Modules | Anusha V | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-16 07:23 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | Un realized gain or loss-D | Devaraju S J | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 18:17 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Resolve the issue with multiple GSTIN of a Vendor in Bills | Tanu Gupta | High | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 20:49 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Ango Procurement Call - IMPLEMENTATION OF INVENTORY MANAGEMENT SOFTWARE WITH INTEGRATION FOR SALES SOFTWARE AND E-COMMERCE | Tanu Gupta | Medium | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 20:41 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Testing of use case for 90+ to 0-90 criteria | Tanu Gupta | Medium | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:41 | In Progress | Yes | 10% | IIFL Samasta Zoho Creator Score Card Enhancement | Milestone One-Implementation of Score Card Enhancement | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 790157522 | 790157522 | 34 | Late | 35 | 35 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Customer Master Automation | Anusuyadevi V | None | 2024-02-12 09:30 | 2024-02-13 19:00 | 2024-02-13 09:28 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Five-Payment for April 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 3 | 3 | 2 | days
7.4981e+17 | Client Meeting | Nikita Srivastava | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 18:02 | To Do | Yes | 0% | AMC - VAlign | Better Place Support Activity | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Unable to modify fields in Demo module on CRM | Nikita Srivastava | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 17:29 | Done | No | 100% | AMC - VAlign | Better Place Support Activity | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Zoho Project Standard App Demo To Ozone | Mohammed Yusha,Tanu Gupta | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 17:42 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | RPA meeting-D | Devaraju S J | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:27 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Unbounded Flow Implementation & Testing | Anusha V | None | 2024-02-14 09:30 | 2024-02-15 19:00 | 2024-02-15 15:06 | To Do | Yes | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 32 | Late | 34 | 34 | 2 | days
7.4981e+17 | COA, Item Master, Tax Master and Vendor Masters Integration to Zoho Book | Vaikuntam Chowdary | None | 2024-02-12 09:30 | 2024-02-13 19:00 | 2024-02-15 09:30 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 34 | Late | 36 | 36 | 2 | days
7.4981e+17 | Inventory Management iin Zoho Books-D | Devaraju S J | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 17:57 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Status Closed Flow,Testing & Client call | Anusha V | High | 2024-02-12 09:30 | 2024-02-20 19:00 | 2024-02-14 09:05 | In Progress | Yes | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 27 | Late | 36 | 36 | 7 | days
7.4981e+17 | Go / No Go Decision | Kris Oswold | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-15 19:23 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 824545238 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Compliance verification report - While creating bill getting ITC ineligble for the user | Swetha K | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 09:29 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 32 | Late | 33 | 33 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Order Management Issue ¦ #1 | Swetha K | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 19:37 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Sales Management-D | Devaraju S J | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:27 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Discrepancy in SSF 2023 for Asian Christian School ¦ School code: 207682 | Swetha K | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:43 | To Do | Yes | 0% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 35 | Late | 36 | 36 | 1 | days
7.4981e+17 | Configuration of Returns Module and Fields | Rajesh Shindagi | None | 2024-02-12 09:30 | 2024-02-14 19:00 | 2024-02-12 16:26 | In Progress | Yes | 0% | Dr Reddy’s - Zoho CRM, Desk, SalesIQ | Milestone One-Advance payment for Zoho project initiation [Zoho Desk & Zoho SalesIQ, Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 33 | Late | 36 | 36 | 3 | days
7.4981e+17 | Configuration of Product Module and Fields | Rajesh Shindagi | None | 2024-02-12 09:30 | 2024-02-14 19:00 | 2024-02-12 16:26 | To Do | Yes | 0% | Dr Reddy’s - Zoho CRM, Desk, SalesIQ | Milestone One-Advance payment for Zoho project initiation [Zoho Desk & Zoho SalesIQ, Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 33 | Late | 36 | 36 | 3 | days
7.4981e+17 | Sales Management - A | Akshay Parameshwara Hegde | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:34 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784261 | 844784261 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Sales Management/S | Shiwani Kumari | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:23 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 35 | Late | 36 | 36 | 1 | days
7.4981e+17 | Re-alignment of In-Progess Follow Email Template | Sachin Patil | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:32 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Hide, Show, Enabled and Disabled Check Sheet Fields | Sachin Patil | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:01 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Issues and Clarification in Bills | Vignesh R | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 21:10 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | Zoho Purchase and Inventory | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 35 | Late | 36 | 36 | 1 | days |  | Clear
7.4981e+17 | Active Data Migration Accounts status updation (active) | Mary Nisha | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 18:23 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 33 | Late | 34 | 34 | 1 | days |  | Clear
7.4981e+17 | Email replies and solution searching and fesiability check | M S Satya | None | 2024-02-12 09:30 | 2024-02-16 19:00 | 2024-02-13 10:29 | In Progress | Yes | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 31 | Late | 36 | 36 | 5 | days
7.4981e+17 | Zoho Desk Call log Issue not getting updated in zoho | Monik Chettiyar | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 19:11 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Check Mismatch in on test Qty in Inventory report | Vignesh R | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 21:32 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Production Activity Log Enabled/Disabled Fields and Validation | Sachin Patil | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 19:23 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Validation on Quanity Check - Allow to add accepted qty greater than or equal to zero and Accepted qty not empty | Sachin Patil | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 19:11 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | #5926 CRM changes Requirement .Chnages permission for Email, Mobile,Lead source, and Lead Channel field in leads module | Maninder Singh | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 14:23 | Done | No | 100% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-01 09:30 | 2024-02-15 19:00 | 2024-02-14 10:56 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 19 | 19 | 11 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-01 09:30 | 2024-02-15 19:00 | 2024-02-14 10:56 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 19 | 19 | 11 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-01 09:30 | 2024-02-15 19:00 | 2024-02-14 10:56 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 19 | 19 | 11 | days
7.4981e+17 | Create page for vendor registration | Aishwarya T | None | 2024-02-13 09:30 | 2024-02-28 19:00 | 2024-02-13 15:24 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 1 | Late | 17 | 17 | 12 | days |  | Clear | Sai Krishna
7.4981e+17 | Vendor Onboarding form | Aishwarya T | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 10:31 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 16 | Late | 17 | 17 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Invoice API Creation for Create/Update using PostMan | Vaikuntam Chowdary | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-12 12:21 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 41 | Late | 42 | 42 | 1 | days
7.4981e+17 | Performance Assessment-D | Devaraju S J | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 18:43 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | ICAC - PDF - Columns hide and shows if data is empty and customization | Ayush Singh | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-09 21:36 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 46 | Late | 47 | 47 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Reporting Tag A | Akshay Parameshwara Hegde | None | 2024-02-09 19:00 | 2024-02-09 19:00 | 2024-02-09 18:51 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784261 | 844784261 | 0 | Late | 1 | 1 | 0 | days
7.4981e+17 | Client Visit 09-Feb-2024 | Vignesh R | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 18:42 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 38 | Late | 39 | 39 | 1 | days
7.4981e+17 | Budget Master | Ranjana Poojari | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 12:14 | Done | No | 100% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778475421 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Escalation work, Mails to Zoho Support team | Kiran Shrivastav | None | 2024-02-08 09:30 | 2024-02-29 19:00 | 2024-02-09 14:03 | In Progress | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 18 | Late | 40 | 40 | 16 | days
7.4981e+17 | Issue in Production Activity Log | Vignesh R | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 00:17 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 38 | Late | 39 | 39 | 1 | days
7.4981e+17 | Zoho CRM Data Import | Monik Chettiyar | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-12 01:17 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Create Sales Invoice report in analytics | Nikita Srivastava | None | 2024-02-09 09:30 | 2024-02-12 19:00 | 2024-02-09 12:12 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774653652 | 774653652 | 28 | Late | 32 | 32 | 2 | days |  | Clear
7.4981e+17 | Create the Purchase Order report in analytics | Nikita Srivastava | None | 2024-02-08 09:30 | 2024-02-12 19:00 | 2024-02-08 18:35 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774653652 | 774653652 | 0 | Late | 5 | 5 | 3 | days |  | Clear
7.4981e+17 | Kt - Business Description | Nawaz Sharief | None |  |  | 2024-02-08 13:57 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 841115370 | 841115370 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Workflow To create Deal | Nikita Srivastava | None | 2024-02-12 09:30 | 2024-02-13 19:00 | 2024-02-12 10:17 | In Progress | Yes | 0% | Accorian - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 774653652 | 34 | Late | 36 | 36 | 2 | days
7.4981e+17 | User Profiles and permission | Ayush Singh | None |  |  | 2024-02-08 20:34 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 |  | On Time |  | 0 | 0 | days |  | Clear | Dharanidharan C
7.4981e+17 | Date format update | Kiran Shrivastav,Monik Chettiyar | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 18:58 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987,792262192 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | Date issue while converting to Pdf | Mary Nisha | High | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-02-12 11:30 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 11 | Late | 12 | 12 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Create New Form 'Upload Load Calculation' for update Item Details from Import (Min Qty, Max Qty, Re-Order Level, Order Qty) | Sachin Patil | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 18:48 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Facebook Ads Leads Directed to Rakhi in CRM | Maninder Singh | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 14:49 | Done | No | 100% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Zoho Books Training Demo 1 | Waheeba Khan,Rishikesh Gogha,Tanu Gupta,Devaraju S J,Akshay Parameshwara Hegde,Shiwani Kumari | High | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 19:29 | In Progress | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 671373250,745115006,790157522,844783967,844784261,844784545 | 38 | Late | 39 | 39 | 1 | days
7.4981e+17 | Weekly Meeting | Mohammed Yusha,Tanu Gupta | Medium | 2024-02-07 09:30 | 2024-02-28 19:00 | 2024-02-08 19:23 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 0 | Late | 22 | 22 | 16 | days
7.4981e+17 | Data templates explanation | Rishikesh Gogha | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-12 10:00 | To Do | Yes | 0% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 38 | Late | 39 | 39 | 1 | days
7.4981e+17 | Found,Not_Found Flow | Anusha V | High | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-09 19:45 | In Progress | Yes | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 45 | Late | 46 | 46 | 1 | days
7.4981e+17 | Data Validation Functionality during Import | Anusha V | High | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-09 19:38 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | #5911 Dashboard visibility | Tanu Gupta | High | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 23:35 | Done | No | 100% | AMC - VAlign | HAPPY RELIABLE SURGERIES PRIVATE LIMITED - Zoho CRM and Zoho Form ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Item creation-D | Devaraju S J | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 18:37 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Change request in lead assignment_08 Feb | Maninder Singh | High | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 11:41 | Done | No | 100% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Setup Users (Members Success) | Leahanne Thomas | None | 2024-02-07 09:30 | 2024-02-09 19:00 | 2024-02-07 21:53 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 811824969 | 30 | Late | 33 | 33 | 3 | days
7.4981e+17 | ABMPL-Zoho Creator Internal KT and Internal Testing | Vaikuntam Chowdary | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-07 10:29 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 41 | Late | 42 | 42 | 1 | days |  | Clear
7.4981e+17 | Client Call regarding Scorecard Enhancements and Incentive Calculation Module | Tanu Gupta | High | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:35 | Done | No | 100% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Inventory & RTO Workflow Check | Mohammed Yusha | None | 2024-02-06 09:30 | 2024-02-07 19:00 | 2024-02-06 19:02 | In Progress | Yes | 0% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Inventory and RTO Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 40 | Late | 42 | 42 | 2 | days |  | Clear
7.4981e+17 | Custom Profile for few roles | Tanu Gupta | High | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 19:01 | Done | No | 100% | AMC - VAlign | Infifresh 01-01-2024 to 31-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | On user input of vendor dynamic populate gst rate | Swetha K | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 12:06 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 40 | Late | 41 | 41 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Customer Master Update API Documentation | Anusuyadevi V | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-07 10:42 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Client call for issue in Bulk PO approval | Tanu Gupta | High | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 21:08 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Vendor/S | Shiwani Kumari | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 18:44 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Catchup with Sunil regarding ChatGPT integration | Prableen Kaur | None | 2024-02-05 09:30 | 2024-02-09 19:00 | 2024-02-06 17:51 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 11 | Late | 16 | 16 | 5 | days
7.4981e+17 | Support request : Fwd: ZOHO people corrections | Kiran Shrivastav | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 22:00 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 18 | Late | 19 | 19 | 1 | days
7.4981e+17 | Support request FW: New KRA request | Kiran Shrivastav | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 18:53 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 18 | Late | 19 | 19 | 1 | days
7.4981e+17 | Vaibhav kumar filed access issue | Nikita Srivastava | None |  |  | 2024-02-06 18:14 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Create Production Flow Chart | Vignesh R | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 18:42 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 42 | Late | 43 | 43 | 1 | days
7.4981e+17 | Configuration of roles and permissions wrt Modules | Dharanidharan C | None | 2024-02-06 09:30 | 2024-02-20 19:00 | 2024-02-05 17:06 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 2 | Late | 17 | 17 | 11 | days
7.4981e+17 | Company Set up | Devaraju S J | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:19 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Client Meet 07/02/23 | M S Satya | None |  |  | 2024-02-07 18:40 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | CEEW Flowchart | Sai Krishna,Aishwarya T | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 16:07 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 29 | Late | 30 | 30 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Changes in PO Vs Invoice reports | Vignesh R | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 22:21 | In Progress | Yes | 10% | Vestian Global_Zoho Creator | Milestone Two-Zoho Creator – Procurement &Billing Management System.3. Completion of Config | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 41 | Late | 42 | 42 | 1 | days |  | Clear
7.4981e+17 | Mark Lead as Junk | unassigned | None |  |  | 2024-02-06 19:55 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 701371504 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Verifying the meeting scheduled by the Lead under open activities | unassigned | None |  |  | 2024-02-06 19:54 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 701371504 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Create a New Lead | unassigned | None |  |  | 2024-02-06 19:54 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 701371504 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | COA - A | Akshay Parameshwara Hegde | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 18:40 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784261 | 844784261 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Create Master for Store Address Remove Single Line field from item Master | Sachin Patil | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 16:47 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | If PI is not available in stock inventory at the time of approval then '0' should be updated | unassigned | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 19:03 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | - | 41 | Late | 42 | 42 | 1 | days
7.4981e+17 | ABMPL KT | Shavi Thakur | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:21 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 41 | Late | 42 | 42 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Lookup Search | Selva Bharathi | None | 2024-02-05 19:00 | 2024-02-05 19:00 | 2024-02-05 18:30 | Development Complete | Yes | 80% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573 | 42 | Late | 43 | 43 | 0 | days |  | Clear
7.4981e+17 | E2 E Testing | Selva Bharathi | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-05 18:19 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573 | 33 | Late | 34 | 34 | 1 | days |  | Clear
7.4981e+17 | Keyword Search | Selva Bharathi | None | 2024-02-06 19:00 | 2024-02-06 19:00 | 2024-02-05 18:17 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573 | 41 | Late | 42 | 42 | 0 | days |  | Clear
7.4981e+17 | Changes and Issues in Dashboard | Vignesh R | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 12:58 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 40 | Late | 41 | 41 | 1 | days
7.4981e+17 | Tasks Customization as per Template | M S Satya | None |  |  | 2024-02-07 10:18 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Company Setup | Shiwani Kumari | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:19 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Zoho Trial Account Deletion Request | Monik Chettiyar | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-06 01:46 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Zoho People Plus Admin Account closure for duplicate account in Zoho | Monik Chettiyar | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-06 01:29 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Hide, Show, Enabled and Disabled Purchase Indent fields | Sachin Patil | None | 2024-02-05 09:30 | 2024-02-06 19:00 | 2024-02-05 19:15 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 35 | Late | 37 | 37 | 2 | days
7.4981e+17 | Email trigger template changes | Swetha K | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 19:00 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 38 | Late | 39 | 39 | 1 | days
7.4981e+17 | Vendor Bill with PO and Without PO - Alert message on cancel bill | Swetha K | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 14:32 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 42 | Late | 43 | 43 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Data fetch From EHV for RHR | Anusha V | High | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-06 09:32 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Email for Donor Declaration | Sai Krishna,Tanu Gupta | High | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 20:44 | In Progress | Yes | 10% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 753339779,790157522 | 42 | Late | 43 | 43 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Staragile ticket | Nikita Srivastava | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 20:34 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Option for Portal User to Update Informations in portal | Dharanidharan C | None | 2024-02-06 09:30 | 2024-02-20 19:00 | 2024-02-02 17:18 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 2 | Late | 17 | 17 | 11 | days
7.4981e+17 | Need to re align the fields of deal module, Need to update the expected revenue field to current year total amount | Aishwarya T | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 15:42 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 45 | Late | 46 | 46 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | The 'On-Hold' option add into the ticket status. When the 'On-Hold' option is chosen, no actions should be triggered. | Sachin Patil | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 18:54 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-25 09:30 | 2024-02-02 19:00 | 2024-02-02 10:48 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 17 | Late | 26 | 26 | 7 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-25 09:30 | 2024-02-02 19:00 | 2024-02-02 10:48 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 17 | Late | 26 | 26 | 7 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-02-02 10:36 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-02-02 10:36 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | ZOHO Sign Lookup and related list in the submittal | Ayush Singh | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 20:36 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 46 | Late | 47 | 47 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Once Reject Discounted Invoice Approval Record by Store Manager, Invoice Need to Cancelled | Sachin Patil | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 19:33 | To Do | Yes | 0% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 46 | Late | 47 | 47 | 1 | days |  | Clear
7.4981e+17 | Vendor Finance Manager approval - row 53 | Swetha K | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 19:09 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 45 | Late | 46 | 46 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Zoho CRM to Zoho Inventory Integratioin Issue | Vaikuntam Chowdary | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-02 18:33 | In Progress | Yes | 10% | Karam Safety_Zoho ONE | None | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 46 | Late | 47 | 47 | 1 | days |  | Clear
7.4981e+17 | Error while computing Volume Discount in OMS | Swetha K | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 09:30 | Done | No | 100% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | #5896 Surgery Button Issue | Tanu Gupta | High | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-04 22:11 | Done | No | 100% | AMC - VAlign | HAPPY RELIABLE SURGERIES PRIVATE LIMITED - Zoho CRM and Zoho Form ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Email updates, Internal meeting with Supril for crm queries, minor issue in JC | Tanu Gupta | High | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 19:34 | QA Completed | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 46 | Late | 47 | 47 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Testing Dashboard Counts and Email Notifications | unassigned | High | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-02-01 18:16 | In Progress | Yes | 0% | Prodevans - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 795545761 | - | 49 | Late | 50 | 50 | 1 | days
7.4981e+17 | Call with Pansheel and victor for Probation Workflows and Fellow extension workflows | Kiran Shrivastav | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 09:23 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 45 | Late | 46 | 46 | 1 | days
7.4981e+17 | Additional Department ¦ MIS | Kiran Shrivastav | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 12:41 | Done | No | 100% | AMC - VAlign | Neelgund Developers LLP ¦ Zoho People, Recruit & Payroll ¦ 19-10-2023 ¦ 18-10-2024 | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Changes in Certified Value Calculation | Vignesh R | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 20:27 | In Progress | Yes | 10% | Vestian Global_Zoho Creator | Milestone Two-Zoho Creator – Procurement &Billing Management System.3. Completion of Config | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 46 | Late | 47 | 47 | 1 | days |  | Clear
7.4981e+17 | Client Meet at office | unassigned | None |  |  | 2024-02-02 11:16 | Done | No | 100% | Ocimum Botanicals - Zoho Projects Implementation | None | 7.4981e+17 | 7.4981e+17 |  | 789497933 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Create Page fore Inventory For Scanning QR code and make changes in Contract Price master. | Basavaraj Patil | None | 2024-01-15 09:30 | 2024-01-17 19:00 | 2024-02-02 17:16 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 61 | Late | 64 | 64 | 3 | days |  | Clear | Waheeba Khan
7.4981e+17 | Demo On Sales Order and Invoice. | Basavaraj Patil | None | 2024-01-23 09:30 | 2024-02-02 19:00 | 2024-02-02 16:50 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 45 | Late | 56 | 56 | 9 | days |  | Not Clear | Waheeba Khan
7.4981e+17 | Import Rack Master , HASN Master - Client Visit | Basavaraj Patil | None | 2024-01-16 09:30 | 2024-02-02 19:00 | 2024-02-02 16:41 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 45 | Late | 63 | 63 | 14 | days |  | Clear | Waheeba Khan
7.4981e+17 | Item Master Creation | Anusuyadevi V | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 21:21 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Changes in Equipment Purchase Order Template | Vishnu D A,Nirmalkrishnan H | Medium |  |  | 2024-02-02 13:46 | To Do | No | 10% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 838472289 | 838472289,840979277 |  | On Time |  | 0 | 6 | hrs |  | Clear | Siddharth Sharma
7.4981e+17 | : Error in Invoice and Invoice Annexure School Code-3219234 | Swetha K | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 16:25 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Machani Onsite visit(22-25JAN) | Rishikesh Gogha | None | 2024-01-22 09:30 | 2024-01-26 19:00 | 2024-02-01 11:12 | To Do | Yes | 0% | AMC - VAlign | Machani Tamarind Tree Post Go-Live support | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 52 | Late | 57 | 57 | 5 | days
7.4981e+17 | Redemption Category Flow | Vaikuntam Chowdary | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-02-01 09:17 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 47 | Late | 48 | 48 | 1 | days |  | Clear
7.4981e+17 | Implement and Test new use case for refund entry | Tanu Gupta | High | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 21:50 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Fetched the laterest recod in crm by delgue | Nikita Srivastava | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 18:47 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Vendor Bill with PO and Without PO- Alert message need to redefined | Swetha K | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-01-31 18:33 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 45 | Late | 46 | 46 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Product Master Sync Er2 Series | Ranjana Poojari | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 10:02 | Done | No | 100% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 1 | Late | 2 | 2 | 1 | days |  | Clear
7.4981e+17 | Service Call Feedbacks - Swamy/Shivaji | Supril Jain | None | 2024-01-30 09:30 | 2024-02-02 19:00 | 2024-02-01 09:27 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 35 | Late | 39 | 39 | 4 | days |  | Clear
7.4981e+17 | CRM Board of Directors updation | Mary Nisha | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-31 14:33 | Development Complete | Yes | 0% | VSINTERCONNECT CR for Estore | Milestone Two-Development, UAT & Go Live of Estore CR | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 56 | Late | 57 | 57 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | RCA for Corporate Plus Tags/ CyberReady issue | Prableen Kaur | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-31 17:54 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | sql query r &d | Nikita Srivastava | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 22:54 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Zoho Recruit Letter Corrections | Monik Chettiyar | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 10:59 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 48 | Late | 49 | 49 | 1 | days
7.4981e+17 | WordPress Form Integartion with CRM And Deal Owner Assign (Vadodara and Chandigarh) | Sachin Patil | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 18:37 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | New Master File data upload in Accounts,Contacts along with alias concept | Dharanidharan C | None | 2024-01-29 09:30 | 2024-01-30 19:00 | 2024-01-29 17:36 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 14 | Late | 16 | 16 | 2 | days |  | Clear
7.4981e+17 | Client Meeting to Discuss on Sprint | Anusuyadevi V | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-31 09:46 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Project Management Review Meeting | Mohammed Yusha,Vignesh R,Tanu Gupta | High | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-30 20:27 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,704175602,790157522 | 2 | Late | 4 | 4 | 2 | days |  | Clear
7.4981e+17 | Zoho Creator - Resolved various issues share by Verto Team | Tanu Gupta | High | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-30 20:13 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 47 | Late | 49 | 49 | 2 | days |  | Clear | Supril Jain
7.4981e+17 | Email & Domain Authentication for Zoho CRM | Anusha V | High | 2024-01-25 09:30 | 2024-02-07 19:00 | 2024-01-29 09:34 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 40 | Late | 54 | 54 | 10 | days
7.4981e+17 | Jespay Client Meeting & Internal Solution On Issue | Mohammed Yusha | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 19:42 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Timeout alert | Avinash Sah | None | 2024-01-29 09:30 | 2024-01-30 19:00 | 2024-01-29 19:06 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 | 48 | Late | 50 | 50 | 2 | days |  | Clear
7.4981e+17 | Internal Meetings and Discussion | M S Satya | None | 2024-01-22 09:30 | 2024-01-31 19:00 | 2024-01-29 10:26 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 47 | Late | 57 | 57 | 8 | days |  | Clear
7.4981e+17 | New enhancement call on Zoho help desk | Swetha K | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 19:03 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 48 | Late | 49 | 49 | 1 | days
7.4981e+17 | Interview and Onboarding process | Waheeba Khan | None |  |  | 2024-01-30 12:02 | To Do | No | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Synup ¦ Zoho Desk ¦ Mandate fields discussion | Mohammed Yusha,Tanu Gupta | High | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 21:35 | Done | No | 100% | AMC - VAlign | Synup Digital Pvt Ltd - Zoho CRM & Desk ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Make changes in website page for Make a donation | Sai Krishna,Tanu Gupta | High | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 21:26 | In Progress | Yes | 10% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 790157522 | 753339779,790157522 | 49 | Late | 50 | 50 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Refund Test Cases | Anusuyadevi V | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 19:10 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | service engineer dashboard | Supril Jain | None | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-31 09:30 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 36 | Late | 38 | 38 | 2 | days |  | Clear
7.4981e+17 | Vendor Requestion for Pan automation flow devlopment | Mary Nisha | High | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 14:39 | QA level 1 Completed | Yes | 10% | Educational Initiatives - P&I CR | None | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 48 | Late | 49 | 49 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Zoho CRM-API Documentation | Aman Kumar | None |  |  | 2024-01-30 19:01 | Done | No | 100% | LONGITUDE - AMC - Zoho People, Zoho Payroll & Zoho CRM | None | 7.4981e+17 | 7.4981e+17 |  | 839251991 | 839251991 |  | On Time |  | 0 | 3 | days
7.4981e+17 | Updated the view of "My Records" for all modules as favorites, ensuring users see only their relevant records. | Aishwarya T | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 15:03 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Import DS File | Vignesh R | None | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-30 21:56 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 23 | Late | 25 | 25 | 2 | days |  | Clear
7.4981e+17 | TSD of CEEW Vendor master(reference) | Aishwarya T | None | 2024-01-29 09:30 | 2024-01-30 19:00 | 2024-01-30 10:00 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 37 | Late | 39 | 39 | 2 | days |  | Clear | Sai Krishna
7.4981e+17 | client call | Supril Jain | None | 2024-01-29 09:30 | 2024-02-02 19:00 | 2024-01-30 09:05 | To Do | Yes | 0% | Osborne USA - Zoho Analytics | None | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 45 | Late | 50 | 50 | 5 | days |  | Clear
7.4981e+17 | Zoho Support Call | Monik Chettiyar | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-28 18:11 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Zoho - Issues with New Blueprint | Monik Chettiyar | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-28 17:46 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | EL from future months in advance | Monik Chettiyar | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-28 17:38 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | HealthPlix¦¦Knowlarity¦¦Zoho Sync | Monik Chettiyar | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-28 17:27 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Email COntent Changes in zoho people | Monik Chettiyar | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 10:52 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 47 | Late | 48 | 48 | 1 | days
7.4981e+17 | NEED TO ADD NEW ORGANISATION AND LINK EMPLOYEES | Kiran Shrivastav | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 10:53 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | UAT Training | Kiran Shrivastav | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 15:02 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Project Status 1/25 | Stuti S. Kulshrestha | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 14:22 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 53 | Late | 54 | 54 | 1 | days |  | Clear
7.4981e+17 | GRN,Bills Form Creation | Mary Nisha | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 15:13 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Invoice Void Automation | M S Satya | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 12:31 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 53 | Late | 54 | 54 | 1 | days |  | Clear
7.4981e+17 | #5885 Custom Filters and Layout rule for mandate fields | Tanu Gupta | High | 2024-01-30 09:30 | 2024-02-01 19:00 | 2024-01-30 20:34 | Done | No | 100% | AMC - VAlign | Synup Digital Pvt Ltd - Zoho CRM & Desk ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 3 | 3 | 3 | days
7.4981e+17 | Cancel Fulfillment and Return Feasibility check | Anusuyadevi V | None | 2024-01-27 09:30 | 2024-01-27 19:00 | 2024-01-27 20:36 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Create Package and Shipment in ZI for partial fulfilled Order | Anusuyadevi V | None | 2024-01-26 09:30 | 2024-01-26 19:00 | 2024-01-26 21:30 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Remove the branch validation from the scorecard calculation | Tanu Gupta | High | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-26 20:58 | Development Complete | Yes | 10% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 53 | Late | 54 | 54 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Zoho CRM Support | Rajesh Shindagi | None | 2024-01-29 09:30 | 2024-02-10 19:00 | 2024-01-30 17:20 | To Do | Yes | 0% | AMC - VAlign | RGBSI | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 37 | Late | 50 | 50 | 11 | days
7.4981e+17 | Error in Invoice and Invoice Annexure School Code-3219234 | Swetha K | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 09:22 | In Progress | Yes | 0% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 48 | Late | 49 | 49 | 1 | days
7.4981e+17 | Check TNIPL Books Integration Issue | Vignesh R | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-24 16:20 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | Zoho Order Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 54 | Late | 55 | 55 | 1 | days |  | Clear
7.4981e+17 | Add to grouping Item / Quantity / Rate in All Quotations,approved quatations, and pending quatations | Maninder Singh | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-24 11:33 | In Progress | Yes | 0% | AMC - VAlign | FARM INDIA IMPEX ¦ Books, Creator, People, Payroll & Analytics ¦ 8-12-23 to 7-12-24 | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 54 | Late | 55 | 55 | 1 | days
7.4981e+17 | Add bill to and ship to description in all purchase order report | Maninder Singh | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-24 10:29 | In Progress | Yes | 0% | AMC - VAlign | FARM INDIA IMPEX ¦ Books, Creator, People, Payroll & Analytics ¦ 8-12-23 to 7-12-24 | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 54 | Late | 55 | 55 | 1 | days
7.4981e+17 | Adding Inbuild Components | Avinash Sah | None | 2024-02-06 19:00 | 2024-02-06 19:00 | 2024-01-23 19:03 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 | 30 | Late | 31 | 31 | 0 | days |  | Clear
7.4981e+17 | JSW - Review the ICICI Bank Payment Gateway API within Zoho Creator | Mohammed Yusha,Anusuyadevi V,Tanu Gupta | High | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-24 20:34 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,786479121,790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Testing Subform line items | Anusuyadevi V | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-24 09:25 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Client Call for Scorecard application - Go live activities | Tanu Gupta | High | 2024-01-22 09:30 | 2024-01-31 19:00 | 2024-01-23 09:34 | Done | No | 100% | IIFL SAMASTA - Scorecard AM & Above | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 11 | 11 | 8 | days |  | Clear | Selva Bharathi
7.4981e+17 | Test Case Document | Anusuyadevi V,Tanu Gupta | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-23 09:14 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121,790157522 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | Weekly Meeting | Monik Chettiyar | None |  |  | 2024-01-24 10:50 | To Do | No | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 |  | On Time |  | 0 | 0 | days
7.4981e+17 | field level validation Page1 | Avinash Sah | None |  |  | 2024-01-22 19:06 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Vendor Management TSD and solution walkthrough | Aishwarya T | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-24 17:55 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 45 | Late | 46 | 46 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Develop bot for functionality testing for MBE Search | Prableen Kaur | None | 2024-02-05 09:30 | 2024-02-07 19:00 | 2024-01-24 13:05 | To Do | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 40 | Late | 43 | 43 | 3 | days
7.4981e+17 | Template devlopment ICAC,CCO,PMD ICAC,PMD CCO | Mary Nisha | High | 2024-01-23 09:30 | 2024-01-24 19:00 | 2024-01-23 14:11 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 54 | Late | 56 | 56 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Member Management UI | Dharanidharan C,Rahul S S | None |  |  | 2024-01-23 19:07 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 830176551 | 701371504,830176551 |  | On Time |  | 0 | 0 | days |  | Clear | Dharanidharan C
7.4981e+17 | Study on Encryption and Decryption for Bank Gateway API | Anusuyadevi V | None | 2024-01-24 09:30 | 2024-01-25 19:00 | 2024-01-25 09:43 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 5 | Late | 7 | 7 | 2 | days
7.4981e+17 | #5852 Custom Template | Tanu Gupta | High | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 12:16 | Done | No | 100% | AMC - VAlign | Synup Digital Pvt Ltd - Zoho CRM & Desk ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Requirement Call | unassigned | High | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-22 19:00 | To Do | Yes | 0% | AMC - VAlign | Byron Medicals Pty ltd - AMC Support | 7.4981e+17 | 7.4981e+17 |  | 795545761 | - | 56 | Late | 57 | 57 | 1 | days
7.4981e+17 | Develop script to map RMSDC Data with Zoho Creator | Pannaga H | None | 2024-02-07 09:30 | 2024-02-08 19:00 | 2024-01-24 11:17 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 795342015 | 35 | Late | 37 | 37 | 2 | days
7.4981e+17 | Prepare cleansing rules for certificates data | Prableen Kaur | None | 2023-10-11 09:30 | 2024-01-19 19:00 | 2024-01-23 16:16 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 4 | Late | 105 | 105 | 73 | days
7.4981e+17 | Working On member api | Maninder Singh | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 14:05 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 55 | Late | 56 | 56 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | AR Sheet Data upload for Invoice and Company Membership status Update | Dharanidharan C | None | 2024-01-22 09:30 | 2024-02-14 19:00 | 2024-01-22 17:32 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 33 | Late | 57 | 57 | 18 | days |  | Clear
7.4981e+17 | Application Form - Field level Corrections and UI improvization | Dharanidharan C,Mallesh M S | None | 2024-01-22 09:30 | 2024-01-29 19:00 | 2024-01-22 17:32 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504,778475418 | 15 | Late | 23 | 23 | 6 | days |  | Clear
7.4981e+17 | Support on Zoho Payroll | Kiran Shrivastav | None | 2024-01-22 09:30 | 2024-01-23 19:00 | 2024-01-22 21:45 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 55 | Late | 57 | 57 | 2 | days
7.4981e+17 | Application form UI | Mallesh M S | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-22 13:32 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 20 | Late | 21 | 21 | 1 | days |  | Clear
7.4981e+17 | Application form Integration | Mallesh M S | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-22 13:30 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 22 | Late | 23 | 23 | 1 | days |  | Clear
7.4981e+17 | [## 94079017 ##] Zoho People Email Id Changes | Monik Chettiyar | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-22 23:03 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Associate and pracharak api | Maninder Singh | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-22 14:47 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 56 | Late | 57 | 57 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Kick-Off Meeting & Internal Meeting | Mohammed Yusha,Sai Krishna,Tanu Gupta | High | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 18:46 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,753339779,790157522 | 31 | Late | 32 | 32 | 1 | days |  | Clear
7.4981e+17 | #5831 CSM's Open Tickets along with the Jira | Tanu Gupta | High | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-23 12:28 | Done | No | 100% | AMC - VAlign | Synup Digital Pvt Ltd - Zoho CRM & Desk ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Client Call & Report Testing | Mohammed Yusha | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-24 18:45 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Five-Advance Reports & Analytics | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 1 | Late | 2 | 2 | 1 | days |  | Clear
7.4981e+17 | Issue in redirect to report | Vignesh R | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 15:26 | In Progress | Yes | 10% | Trimble Group_Zoho Books & Zoho Creator | Zoho Purchase and Inventory | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 59 | Late | 60 | 60 | 1 | days |  | Clear
7.4981e+17 | Integrate WordPress 'Morden Veneer Doors Bengaluru' form with CRM and assign owner | Sachin Patil | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 18:42 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Query on Leave module | Kiran Shrivastav | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 14:56 | Done | No | 100% | AMC - VAlign | Longitude Exports Pvt Ltd - Zoho CRM, Zoho People & Zoho Payroll ¦ 09-08-2023 ¦ 08-02-2024 | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Support request on RE: Manager review | Kiran Shrivastav | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 23:15 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Develop Python code to transform new columns in regional data | Pannaga H | None | 2024-01-16 09:30 | 2024-01-18 19:00 | 2024-01-18 18:28 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 795342015 | 5 | Late | 8 | 8 | 3 | days
7.4981e+17 | Deploy ID Support Process for Wave 1 Participants | Albert Diaz | None | 2024-01-25 09:30 | 2024-02-14 19:00 | 2024-01-20 05:48 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 809116687 | 12 | Late | 33 | 33 | 15 | days
7.4981e+17 | Create Email Content for MBE's | Stefan Bradham | None | 2024-01-19 09:30 | 2024-02-14 19:00 | 2024-01-20 05:28 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 836353936 | 7 | Late | 34 | 34 | 19 | days
7.4981e+17 | Re-Update Payment Receipt and disable auto create manual journals | Tanu Gupta | High | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-19 20:04 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Client Meeting ¦ Manual Journals and Payments Vouchers | Rishikesh Gogha,Tanu Gupta | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 19:57 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 745115006,790157522 | 59 | Late | 60 | 60 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | ACL Template Clarification Call(19/01/24) | Anusha V | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 15:10 | In Progress | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 59 | Late | 60 | 60 | 1 | days
7.4981e+17 | Shopify Sync Issue & Internal Call | Mohammed Yusha | None | 2024-01-02 09:30 | 2024-01-18 19:00 | 2024-01-18 19:34 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 17 | 17 | 13 | days
7.4981e+17 | Order processing application document | Supril Jain | None | 2024-01-18 09:30 | 2024-01-23 19:00 | 2024-01-22 08:52 | Done | No | 100% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 29 | Late | 35 | 35 | 4 | days
7.4981e+17 | Enhance the State Bifurcation functionality | Tanu Gupta | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 20:21 | In Progress | Yes | 10% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 59 | Late | 60 | 60 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Validation in deals to separate the partially received and fully received PO before converting to SO | Rajesh Shindagi | Medium | 2024-01-29 09:30 | 2024-01-31 16:30 | 2024-01-19 17:43 | Development Complete | Yes | 10% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 47 | Late | 50 | 50 | 26 | hrs |  | Clear | Dharanidharan C
7.4981e+17 | #5831 Call with Zoho Support and Client | Tanu Gupta | High | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 23:12 | Done | No | 100% | AMC - VAlign | Synup Digital Pvt Ltd - Zoho CRM & Desk ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Management & Control Page2 UI | Avinash Sah | None |  |  | 2024-01-19 19:20 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Additional charges insert functions and testing | Mary Nisha | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 15:09 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 59 | Late | 60 | 60 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Atlas Client Visit on 17-Jan-2024 | Vignesh R | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 19:28 | In Progress | Yes | 10% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 60 | Late | 61 | 61 | 1 | days |  | Clear
7.4981e+17 | Invoice TGS/2324/02615 amount not able to return (Return cash to warehouse) | Sachin Patil | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 19:14 | Development Complete | Yes | 0% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 60 | Late | 61 | 61 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Template feedbacks | Aishwarya T | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 15:03 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | GO live | Sai Krishna | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-19 09:55 | Done | No | 100% | QUICK HEAL - Zoho CRM & Zoho Marketing Automation | Milestone Two-Implementation of Zoho CRM – API Integrations | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Business Description UI | Nawaz Sharief | None |  |  | 2024-01-18 18:46 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 841115370 | 841115370 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Add courses and fields in zoho crm lead field for agile ,master | Maninder Singh | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-22 09:28 | Done | No | 100% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Multi Currency Configuration | Tanu Gupta | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 18:57 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | EMS- Issue while selecting SBU for Badri | Swetha K | None | 2024-01-18 09:30 | 2024-01-19 19:00 | 2024-01-18 19:09 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 3 | Late | 5 | 5 | 2 | days
7.4981e+17 | Lead module: Field mismatch in view page & edit page, Emails communication trails are not getting logged in the Email section of the deal. | Anusuyadevi V | None | 2024-01-17 09:30 | 2024-01-18 11:30 | 2024-01-17 19:06 | Done | No | 100% | AMC - VAlign | Infifresh 01-01-2024 to 31-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 2 | 2 | 11.5 | hrs
7.4981e+17 | UI screen for QA | Supreeth R Kalluraya | None | 2024-01-12 09:30 | 2024-01-31 19:00 | 2024-01-18 12:57 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | Milestone Four : Development completion and Go Live of CS Certification Portal. | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 788577227 | 788577227 | 47 | Late | 67 | 67 | 14 | days |  | Clear | Christ Bellarmine
7.4981e+17 | UI screen for update requested | Supreeth R Kalluraya | None | 2024-01-12 09:30 | 2024-01-31 19:00 | 2024-01-17 16:58 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | Milestone Four : Development completion and Go Live of CS Certification Portal. | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 788577227 | 788577227 | 47 | Late | 67 | 67 | 14 | days |  | Clear
7.4981e+17 | Item Detail Page Version 2 Automation - Workflows and functions in SG App | Ayush Singh | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 18:40 | In Progress | Yes | 10% | VSINTERCONNECT CR for Estore | Milestone Two-Development, UAT & Go Live of Estore CR | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 62 | Late | 63 | 63 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Update Deal description from deal to estimate in Zoho Books | Rajesh Shindagi | Medium | 2024-01-17 09:30 | 2024-01-19 16:30 | 2024-01-16 19:14 | Development Complete | Yes | 10% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 59 | Late | 62 | 62 | 26 | hrs |  | Clear | Dharanidharan C
7.4981e+17 | If I seelct part part code should come automatically | Nikita Srivastava | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 15:35 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 50 | Late | 51 | 51 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Leave | unassigned | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 19:18 | In Progress | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 775643568 | - | 61 | Late | 62 | 62 | 1 | days
7.4981e+17 | Refund or Adjustment in EMS System. | Maninder Singh | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 09:30 | Development Complete | Yes | 10% | Educational_Zoho Creator_CR | Milestone Eight-Implementation of Zoho Creator - Go Live | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 61 | Late | 62 | 62 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Changes in Issue Information | Sachin Patil | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 18:24 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | UAT feedback / queries Updates to Client on mail | Tanu Gupta | High | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 23:40 | In Progress | Yes | 10% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 62 | Late | 63 | 63 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Generate Communication Letter to Corp Members About Rollout and Wave Allocation | stefan bradham | None | 2024-01-17 09:30 | 2024-01-22 19:00 | 2024-01-18 01:05 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 836353936 | 1 | Late | 7 | 7 | 4 | days
7.4981e+17 | Create Standard Operating Process (SOP's) for Members Success (Lead Generation) | Christina Santos | None | 2024-02-13 09:30 | 2024-06-06 19:00 | 2024-01-18 00:07 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 825341377 | -80 | On Time | 35 | 35 | 83 | days
7.4981e+17 | Field level changes in CRM | Tanu Gupta | High | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 23:47 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Internal meeting for understanding of manual journal entries | Waheeba Khan,Rishikesh Gogha,Tanu Gupta | High | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 23:34 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 790157522 | 671373250,745115006,790157522 | 61 | Late | 62 | 62 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Layout Rule setup For leads Module | Monik Chettiyar | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-17 20:25 | QA level 1 Completed | Yes | 10% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 68 | Late | 69 | 69 | 1 | days |  | Clear
7.4981e+17 | Ownership Structure UI | Nawaz Sharief | None |  |  | 2024-01-17 19:04 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 841115370 | 841115370 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Client Meetings | Supreeth R Kalluraya | None | 2024-01-16 09:30 | 2024-02-16 19:00 | 2024-01-17 09:36 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 788577227 | 788577227 | 21 | Late | 53 | 53 | 24 | days |  | Clear
7.4981e+17 | Accounts Data Migration - Data cleaning and updating the templates | M S Satya | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 15:51 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 62 | Late | 63 | 63 | 1 | days |  | Clear
7.4981e+17 | Deal - amount - sum of all projections | Aishwarya T | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-18 10:38 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 61 | Late | 62 | 62 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | Management & Controls first page | Avinash Sah | None |  |  | 2024-01-18 10:10 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Reminder notification for service call closure on 8th day if the call is not closed. | Nikita Srivastava | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 11:43 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 50 | Late | 51 | 51 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Application Form Workflows and field changes and functions | Mary Nisha | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 10:18 | Development Complete | Yes | 0% | VSINTERCONNECT CR for Estore | Milestone Two-Development, UAT & Go Live of Estore CR | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 60 | Late | 61 | 61 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Project Kickoff | Supril Jain,Nikita Srivastava | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-17 09:15 | Done | No | 100% | Accorian - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914,774653652 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | CCO&ICAC view changes | Mary Nisha | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 12:55 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 66 | Late | 67 | 67 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Item Detail Page Version 2 Automation - Workflows and functions in IN App | Ayush Singh | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 18:49 | QA level 1 Completed | Yes | 10% | VSINTERCONNECT CR for Estore | Milestone Two-Development, UAT & Go Live of Estore CR | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 66 | Late | 67 | 67 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Zoho CRM TSD Document | Supril Jain | None | 2024-01-11 09:30 | 2024-01-16 19:00 | 2024-01-12 09:28 | Development | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 62 | Late | 68 | 68 | 4 | days
7.4981e+17 | Solution for Payments Made | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Solution for Payin Integration | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Solution for Invoice | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | With Balance Ledger | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Customer Master Integration Testing | Waheeba Khan | None |  |  | 2024-01-16 10:36 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Two-Payment for January2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Customer Recognition Work Flow | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Payin approval process | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Auto Payout setoff | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Payout approval process | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Call with client and zoho support team | Tanu Gupta | High | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-15 18:19 | In Progress | Yes | 10% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 66 | Late | 67 | 67 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Auto Sales Return | Anusuyadevi V | High | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 22:48 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Juspay Analytics Support | Rajesh Shindagi | None |  |  | 2024-01-12 10:41 | In Progress | No | 0% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Webform Code shared to Client and Zoho Projects Support call | Anusha V | High | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 23:13 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 66 | Late | 67 | 67 | 1 | days
7.4981e+17 | Warranty Tracking | Mohammed Yusha,Shavi Thakur | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-16 09:23 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Five-Advance Reports & Analytics | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 701373265,773081417 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Create the fields in the Sandbox for SpotDraft | Nikita Srivastava | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 18:20 | Done | No | 100% | AMC - VAlign | Better Place Support Activity | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | UAT issues discussion meeting | Maninder Singh | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 12:03 | QA Completed | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 66 | Late | 67 | 67 | 1 | days |  | Clear
7.4981e+17 | New user creation in Zoho people and onboarding triggered | Kiran Shrivastav | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 23:22 | Done | No | 100% | AMC - VAlign | Longitude Exports Pvt Ltd - Zoho CRM, Zoho People & Zoho Payroll ¦ 09-08-2023 ¦ 08-02-2024 | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Backend - Auto populating data (if already submitted) | Nawaz Sharief | None | 2024-01-31 09:30 | 2024-02-15 19:00 | 2024-01-11 19:00 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 841115370 | 21 | Late | 37 | 37 | 12 | days |  | Not Clear
7.4981e+17 | Backend -Ownership Structure | Nawaz Sharief | None | 2024-01-31 09:30 | 2024-02-05 19:00 | 2024-01-11 18:52 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 841115370 | 31 | Late | 37 | 37 | 4 | days |  | Not Clear
7.4981e+17 | OwnerShip Structure Screens | Nawaz Sharief | None | 2024-01-11 09:30 | 2024-01-18 19:00 | 2024-01-11 18:40 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 841115370 | 49 | Late | 57 | 57 | 6 | days |  | Not Clear
7.4981e+17 | Add roundoff in Bill flow | Vignesh R | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 10:02 | In Progress | Yes | 10% | Trimble Group_Zoho Books & Zoho Creator | Zoho Purchase and Inventory | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 62 | Late | 63 | 63 | 1 | days |  | Clear
7.4981e+17 | Analytics report creation testing forZone wise reports | Aishwarya T | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 17:45 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | New Maintenace contract details is not required in installation tab and Call closing is not possible | Nikita Srivastava | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 09:44 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 55 | Late | 56 | 56 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Create new Item Master Report for Store Managers (Own warehouse item should visible) | Sachin Patil | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 19:00 | Terminated/Cancelled | No | 100% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 1 | Late | 2 | 2 | 1 | days |  | Clear
7.4981e+17 | Add New Options on Enquiry Source field, add field dependencies and Lead Conversion Mapping | Sachin Patil | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 18:42 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-12 10:29 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Progress Junction | Supreeth R Kalluraya,Stuti S. Kulshrestha | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 20:36 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 788577227,808004288 | 67 | Late | 68 | 68 | 1 | days |  | Clear
7.4981e+17 | Client Escalation Meeting & Internal Call | Mohammed Yusha | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 19:42 | Done | No | 100% | Amilite ERP | Milestone Two-Zoho Creator – Costing & Quotation Management Application | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | Margin Calculation Query | Achyuth T M | High | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-12 13:36 | To Do | Yes | 0% | Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 56 | Late | 57 | 57 | 1 | days
7.4981e+17 | Recurring Tracking Report and Dashboard | Achyuth T M | High | 2024-01-17 09:30 | 2024-01-18 19:00 | 2024-01-12 13:36 | In Progress | Yes | 0% | Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 60 | Late | 62 | 62 | 2 | days
7.4981e+17 | Internal Meeting for Solution development | Selva Bharathi,Tanu Gupta | High | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 19:21 | Done | No | 100% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701368573,790157522 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Bill Template | Shavi Thakur,Tanu Gupta | High | 2024-01-12 09:30 | 2024-01-12 12:00 | 2024-01-11 16:13 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 773081417,790157522 | 6 | Late | 7 | 7 | 2.5 | hrs
7.4981e+17 | Issue in QC push to zoho books | Vignesh R | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 11:31 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 68 | Late | 69 | 69 | 1 | days
7.4981e+17 | P/L Matching with GSTR 3B Report | Rishikesh Gogha | None | 2024-01-17 09:30 | 2024-01-19 19:00 | 2024-01-10 09:43 | To Do | Yes | 0% | Good Will Enterprises - Zoho Books | Milestone Two-Assisting and Providing the support for Zoho Books issues | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 59 | Late | 62 | 62 | 3 | days
7.4981e+17 | UI Validation Rules - General Info Screens | Avinash Sah | None | 2024-01-17 09:30 | 2024-01-23 19:00 | 2024-01-11 12:37 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176894 | 13 | Late | 20 | 20 | 5 | days |  | Clear
7.4981e+17 | General Info Screens | Avinash Sah | None | 2024-01-09 09:30 | 2024-02-05 19:00 | 2024-01-11 12:30 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176894 | 31 | Late | 59 | 59 | 20 | days |  | Clear
7.4981e+17 | Changes in Financial Dashboard | Basavaraj Patil | High | 2024-01-04 09:30 | 2024-01-10 19:00 | 2024-01-10 09:51 | In Progress | Yes | 0% | AMC - VAlign | Saahas | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 68 | Late | 75 | 75 | 5 | days
7.4981e+17 | Activity Log for both External and Internal users | Kalyanasundaram L | None | 2024-01-09 09:30 | 2024-01-11 19:00 | 2024-01-11 09:56 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 67 | Late | 70 | 70 | 3 | days |  | Clear
7.4981e+17 | #5763 URGENT - Roundrobin Method is Not Working | Maninder Singh | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 10:26 | Done | No | 100% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Item Name section is not required in Pre-Installation module.(Pre Installation) | Nikita Srivastava | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 10:10 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 56 | Late | 57 | 57 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | If I enter Unit Price and Quantity then total prise should come automatically (Pre Installation) | Nikita Srivastava | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 10:04 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 56 | Late | 57 | 57 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Reassign Process | Ranjana Poojari | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 12:35 | Done | No | 100% | IIFL Samasta: Zoho Creator Employee House Visit (EHV) Change Request | Milestone One- Advance Payment Zoho Creator Employee House Visit (EHV) Change Request | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 1 | Late | 2 | 2 | 1 | days |  | Clear
7.4981e+17 | Clarification call/meeting (Internal/External) | Swetha K | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 09:43 | To Do | Yes | 0% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 67 | Late | 68 | 68 | 1 | days
7.4981e+17 | Vendor Master solution Document | Waheeba Khan | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-11 08:00 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Two-Payment for January2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 63 | Late | 64 | 64 | 1 | days
7.4981e+17 | Employee Master | Anusuyadevi V | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-10 08:49 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | UAT - Feedback points(9/1/2024) | Swetha K | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 10:52 | Done | No | 100% | IIFL SAMASTA -Zoho Creator_Helpdesk CR | Milestone One-Customization and Development of Change Request for Zoho Help Desk | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 2 | Late | 3 | 3 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Testing of Flow | Mohammed Yusha,Anusuyadevi V,Tanu Gupta | Medium | 2024-01-10 09:30 | 2024-01-12 19:00 | 2024-01-10 19:45 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,786479121,790157522 | 4 | Late | 7 | 7 | 3 | days
7.4981e+17 | Agappe Client Visit | Siddharth Sharma | None | 2024-01-09 09:30 | 2024-01-19 19:00 | 2024-01-10 09:42 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 | 59 | Late | 70 | 70 | 9 | days |  | Clear
7.4981e+17 | Integrations Help Document Creation | Dharanidharan C | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 13:42 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 67 | Late | 68 | 68 | 1 | days |  | Clear
7.4981e+17 | Members Success CRM Work Session | Stuti S. Kulshrestha | None | 2024-01-11 09:30 | 2024-01-12 19:00 | 2024-01-10 23:09 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 66 | Late | 68 | 68 | 2 | days |  | Clear
7.4981e+17 | Self appraisal Tab is not showing | Kiran Shrivastav | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 15:41 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Client Meeting ¦ Quotation Progress Demo | Mohammed Yusha,Tanu Gupta | High | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 19:44 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | R&D and Internal Call - A& C Project | Stuti S. Kulshrestha | None | 2024-01-09 09:30 | 2024-01-10 19:00 | 2024-01-09 13:54 | In Progress | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 68 | Late | 70 | 70 | 2 | days
7.4981e+17 | Task Automation if no modification is happening | Monik Chettiyar | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-09 19:13 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 73 | Late | 74 | 74 | 1 | days |  | Clear
7.4981e+17 | Zoho Support Call with Team | Monik Chettiyar | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-09 18:45 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Daily Meeting For Zoho Recruit and People | Monik Chettiyar | None | 2024-01-02 09:30 | 2024-01-31 19:00 | 2024-01-09 18:26 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 47 | Late | 77 | 77 | 22 | days
7.4981e+17 | Lead Conversion issue | Nikita Srivastava | None | 2024-01-09 09:30 | 2024-01-10 19:00 | 2024-01-09 16:39 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 13 | Late | 15 | 15 | 2 | days
7.4981e+17 | Sync PAN, Period and Notes from Creator to Books And Mark Vendors and Active and In-Active | Shavi Thakur,Tanu Gupta | None | 2024-01-09 17:30 | 2024-01-09 19:00 | 2024-01-09 18:03 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417,790157522 | 1 | Late | 2 | 2 | 1.5 | hrs
7.4981e+17 | KT on EI - P&I and EI-OMS | Swetha K | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 19:04 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 69 | Late | 70 | 70 | 1 | days
7.4981e+17 | Bill Module - Add more fields and sych with Books | Shavi Thakur,Tanu Gupta | High | 2024-01-10 15:30 | 2024-01-10 18:30 | 2024-01-09 18:03 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 773081417,790157522 | 0 | Late | 1 | 1 | 3 | hrs
7.4981e+17 | Business vertical as Digital lending and category based on tht | Swetha K | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 15:36 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Zoho Creator - Invoice Module Changes (Tax at line item, shipping address, send invoice to customer etc) | Tanu Gupta | High | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-09 18:31 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 67 | Late | 68 | 68 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Zoho Mail Clarifications and Support | Irshad Pasha | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 15:40 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 701341459 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | HTML to PDF in Catalyst | Avinash Sah | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 10:31 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 | 69 | Late | 70 | 70 | 1 | days |  | Clear
7.4981e+17 | External User - User Management Changes | Kalyanasundaram L | None | 2024-01-08 09:30 | 2024-01-09 19:00 | 2024-01-09 09:56 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 69 | Late | 71 | 71 | 2 | days |  | Clear
7.4981e+17 | Testing the DL department | Swetha K | None | 2024-01-09 09:30 | 2024-01-09 09:30 | 2024-01-09 09:38 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 0 | Late | 1 | 1 | 0 | days
7.4981e+17 | Client Call for updates in storage tracker | Tanu Gupta | High | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 18:34 | Done | No | 100% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Inventory Valuation 31st DEC- Blore | Waheeba Khan,Rishikesh Gogha | None | 2024-01-05 09:30 | 2024-01-08 19:00 | 2024-01-08 09:49 | Done | No | 100% | Genesis IT - Applications Training and query clarification on Zoho Books and Inventory | Milestone Two-Applications training and query clarifications | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 671373250,745115006 | 4 | Late | 8 | 8 | 2 | days
7.4981e+17 | User Manual Document | Tanu Gupta | High | 2024-01-23 09:30 | 2024-01-25 19:00 | 2024-01-08 09:35 | QA level 1 Completed | Yes | 30% | IIFL SAMASTA - Scorecard AM & Above | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 53 | Late | 56 | 56 | 3 | days |  | Clear | Selva Bharathi
7.4981e+17 | Fallback to close status after reply to closed email | Swetha K | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 18:55 | Done | No | 100% | IIFL SAMASTA -Zoho Creator_Helpdesk CR | Milestone One-Customization and Development of Change Request for Zoho Help Desk | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 5 | Late | 6 | 6 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | BOM Creation For EDC | Vaikuntam Chowdary | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-08 19:07 | In Progress | Yes | 10% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 66 | Late | 67 | 67 | 1 | days |  | Clear
7.4981e+17 | RE: 2nd shift attendance error | Kiran Shrivastav | None | 2024-01-08 09:30 | 2024-01-09 19:00 | 2024-01-08 19:45 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 2 | Late | 4 | 4 | 2 | days
7.4981e+17 | Payment Advice Directly data to be fetched from zoho books those details to be shown in Creator | Mohan Kumar | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-08 10:45 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | If any quote is marked as closed won then the rest of the quotes related to the project name and product should be marked as closed lost. | Aishwarya T | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 11:12 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 16 | Late | 17 | 17 | 1 | days
7.4981e+17 | Soft Launch Support Activities | Kalyanasundaram L | None | 2024-01-03 15:30 | 2024-01-04 05:00 | 2024-01-06 19:01 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 74 | Late | 76 | 76 | 8.5 | hrs |  | Clear
7.4981e+17 | Prequalification and Lead Assignment Flow Test | Sai Krishna | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-05 09:57 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 74 | Late | 75 | 75 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Sandbox to Live - IGL New branch,& split branch | Swetha K | None | 2024-02-01 09:30 | 2024-02-05 19:00 | 2024-01-05 16:35 | To Do | Yes | 0% | IIFL SAMASTA -New Branch Survey Enhancement | Milestone Two-Development, Configuration UAT and Go-Live of New Branch Survey Enhancement | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 42 | Late | 47 | 47 | 3 | days |  | Clear | Selva Bharathi
7.4981e+17 | Configuration of Lead Module and Field configurations | Rajesh Shindagi | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-04 19:19 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 73 | Late | 74 | 74 | 1 | days |  | Not clear
7.4981e+17 | Configuration of Workflow Rules: Deal Module | Rajesh Shindagi,Monik Chettiyar | None | 2024-01-15 09:30 | 2024-01-16 15:00 | 2024-01-04 19:06 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363,792262192 | 62 | Late | 64 | 64 | 15 | hrs |  | Not clear
7.4981e+17 | Relocation workflow- Checks | Kiran Shrivastav | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 15:53 | Done | No | 100% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Call on Annual appraisal form | Kiran Shrivastav | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 12:41 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Support Activities | Mary Nisha | None | 2024-01-01 09:30 | 2024-02-29 19:00 | 2024-01-08 11:19 | In Progress | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 18 | Late | 78 | 78 | 44 | days
7.4981e+17 | PDF and CCO ICAC form automations and validations | Mary Nisha | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-08 10:42 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 69 | Late | 70 | 70 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | 3CDN Client Workshop | Sai Krishna | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 09:47 | Done | No | 100% | AMC - VAlign | CTW Systems Private Limited ¦ Zoho One ¦ 27-09-2023 ¦ 26-092024 | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 753339779 | 753339779 | 59 | Late | 60 | 60 | 1 | days
7.4981e+17 | Import Manufacturing Bundles | Tanu Gupta | High | 2024-01-16 09:30 | 2024-01-17 19:00 | 2024-01-04 22:07 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 61 | Late | 63 | 63 | 2 | days |  | Clear | Supril Jain
7.4981e+17 | Edit option for Quote Header details and Remove Quote Line Items once Category is removed from Item Category | Anusuyadevi V | None | 2024-01-18 09:30 | 2024-01-19 19:00 | 2024-01-08 09:28 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | -1 | On Time | 1 | 1 | 2 | days
7.4981e+17 | Quotation Approval Changes | Anusuyadevi V | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-08 09:21 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Zoho Project Blue Print Automation | Mohammed Yusha | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-05 16:15 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 47 | Late | 48 | 48 | 1 | days
7.4981e+17 | UAT Demo | Mohammed Yusha,Tanu Gupta | High | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-05 16:11 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | POI Preference | Rishikesh Gogha | None | 2024-01-17 09:30 | 2024-01-18 19:00 | 2024-01-05 09:52 | Done | No | 100% | AMC - VAlign | EI - Zoho One Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | -1 | On Time | 1 | 1 | 2 | days
7.4981e+17 | Create the new module called "Unique id" and save the id after guest login successfully. | Nikita Srivastava | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 13:07 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 73 | Late | 74 | 74 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Connect with Zoho Inventory support for the Automation in Shopify to Inventory Integration | Shavi Thakur | None | 2024-01-05 12:30 | 2024-01-05 13:30 | 2024-01-05 09:19 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 3 | Late | 4 | 4 | 1 | hrs
7.4981e+17 | Zoho Creator Re-Solutioning & Internal Testing | Mohammed Yusha | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 19:08 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Calculation Changes in Material Return | Mallesh M S | None | 2024-01-09 09:30 | 2024-01-10 19:00 | 2024-01-08 17:14 | To Do | Yes | 0% | Ecovinal Project 3 - Farmer Management | Milestone Two-Zoho Creator – Farmer Operations: Configuration and customisation, Software demo | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 778475418 | 68 | Late | 70 | 70 | 2 | days |  | Clear
7.4981e+17 | Checkmate Functionality Review - Pricing and Access limit | Christ Bellarmine | None | 2024-02-01 09:30 | 2024-03-15 19:00 | 2024-01-06 02:41 | In Progress | Yes | 10% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 | 3 | Late | 47 | 47 | 32 | days
7.4981e+17 | External Meeting with durian team and WordPress developer team for new form integration(05 Jan 24) | Sachin Patil | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 18:49 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | UI Input and Review Call for Certification process | Supreeth R Kalluraya | None | 2024-01-01 09:30 | 2024-01-31 19:00 | 2024-01-04 23:38 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | Milestone Four : Development completion and Go Live of CS Certification Portal. | 7.4981e+17 | 7.4981e+17 |  | 788577227 | 788577227 | 47 | Late | 78 | 78 | 23 | days |  | Clear
7.4981e+17 | Create Invoice based on Shopify Status | Shavi Thakur | None | 2024-01-08 13:30 | 2024-01-08 16:00 | 2024-01-08 08:59 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 2 | Late | 3 | 3 | 2.5 | hrs
7.4981e+17 | Client Call For Zoho Meeting Walkthrough | Supril Jain | None | 2024-01-04 09:30 | 2024-01-10 19:00 | 2024-01-05 09:36 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 68 | Late | 75 | 75 | 5 | days
7.4981e+17 | Hiren and Dharani Feeback points ( 5/1/23) | M S Satya | None | 2024-01-08 09:30 | 2024-01-09 19:00 | 2024-01-08 18:43 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 69 | Late | 71 | 71 | 2 | days |  | Clear
7.4981e+17 | CTW Systems_Zoho people Demo | Kiran Shrivastav | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 11:06 | Done | No | 100% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Samasta Scrum - Jan24 & Feb24&Mar24 | Anusha V | None |  |  | 2024-01-09 09:17 | In Progress | No | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Zoho Flow integration with shopify and zoho inventory | Tanu Gupta | High | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 18:45 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Master Data Migration _Item | Sachin Patil | None | 2024-01-15 09:30 | 2024-01-16 19:00 | 2024-01-04 18:30 | Hold | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 776725592 | 62 | Late | 64 | 64 | 2 | days
7.4981e+17 | Valves Integration | Siddharth Sharma,Aishwarya T | None | 2024-01-04 09:30 | 2024-01-05 19:00 | 2024-01-04 16:46 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 756762742,772989157 | 20 | Late | 22 | 22 | 2 | days
7.4981e+17 | User Acceptance testing | Kiran Shrivastav | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-04 14:33 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Employee pay structure | Kiran Shrivastav | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-04 14:17 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 22 | Late | 23 | 23 | 1 | days
7.4981e+17 | Approvals | Kiran Shrivastav | None | 2024-01-22 09:30 | 2024-01-24 19:00 | 2024-01-04 14:12 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 26 | Late | 29 | 29 | 3 | days
7.4981e+17 | Mail Merge Templates | Kiran Shrivastav | None | 2024-01-17 09:30 | 2024-01-19 19:00 | 2024-01-04 14:00 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 31 | Late | 34 | 34 | 3 | days
7.4981e+17 | Benefits | Kiran Shrivastav | None | 2024-01-15 09:30 | 2024-01-17 19:00 | 2024-01-04 14:00 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 33 | Late | 36 | 36 | 3 | days
7.4981e+17 | Employee Database | Kiran Shrivastav | None | 2024-01-15 09:30 | 2024-01-17 19:00 | 2024-01-04 13:58 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 33 | Late | 36 | 36 | 3 | days
7.4981e+17 | Updates after UAT | Kiran Shrivastav | None | 2024-01-18 09:30 | 2024-01-25 19:00 | 2024-01-04 13:39 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 53 | Late | 61 | 61 | 6 | days
7.4981e+17 | Blueprint Process | Kiran Shrivastav | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-04 13:33 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 66 | Late | 67 | 67 | 1 | days
7.4981e+17 | Email Templates | Kiran Shrivastav | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-04 13:30 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 66 | Late | 67 | 67 | 1 | days
7.4981e+17 | Fill admission confirmation button should be disable after filling the admisiion confirmation button in digital coordinator button | Maninder Singh | None | 2024-01-09 09:30 | 2024-01-10 19:00 | 2024-01-04 12:47 | QA level 1 Completed | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 68 | Late | 70 | 70 | 2 | days |  | Clear
7.4981e+17 | All the auto fill details (Which comes from Profile) should be disable(Non-editable).Retest | Maninder Singh | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-04 12:34 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 69 | Late | 70 | 70 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Develop bot to handle exceptional data thrown by zoho | Prableen Kaur | None | 2024-02-06 09:30 | 2024-02-08 19:00 | 2024-01-04 14:07 | To Do | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 39 | Late | 42 | 42 | 3 | days
7.4981e+17 | Data Analysis of Eastern, Florida, Georgia | Prableen Kaur | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-04 13:44 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 792886644 | 792886644 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Training on UI Path- Developer Foundation | Pannaga H | Medium | 2024-01-04 09:30 | 2024-01-31 19:00 | 2024-01-04 13:33 | To Do | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 795342015 | 47 | Late | 75 | 75 | 20 | days
7.4981e+17 | Update email issue | Nikita Srivastava | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 11:04 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 74 | Late | 75 | 75 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Configuration of Translations | unassigned | None |  |  | 2024-01-04 12:08 | Terminated/Cancelled | No | 100% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | - |  | On Time |  | 0 | 0 | days |  | Not clear
7.4981e+17 | Configuration of Email Templates | Rajesh Shindagi | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-04 12:08 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 68 | Late | 69 | 69 | 1 | days |  | Not clear
7.4981e+17 | Configuration of Segmentation | unassigned | None |  |  | 2024-01-04 12:07 | To Do | No | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | - |  | On Time |  | 0 | 0 | days |  | Not clear
7.4981e+17 | Configuration of Case Escalation Rules | unassigned | None |  |  | 2024-01-04 12:07 | To Do | No | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | - |  | On Time |  | 0 | 0 | days |  | Not clear
7.4981e+17 | Configuration of Workflow Rules: Lead Module | Rajesh Shindagi,Monik Chettiyar | None | 2024-01-08 09:30 | 2024-01-09 15:00 | 2024-01-04 12:07 | In Progress | Yes | 10% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363,792262192 | 69 | Late | 71 | 71 | 15 | hrs |  | Clear
7.4981e+17 | Login via Email -> "*" sign should be there for mandatory fields. Login via phone-> "*" sign should be there for mandatory fields. | Maninder Singh | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-04 12:17 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 70 | Late | 71 | 71 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Update Profile -> I can upload any file format (ex: xlsx,gif,txt) in “Any Government Photo ID" | Maninder Singh | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-04 11:08 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 73 | Late | 74 | 74 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | KRA list Addition | Kiran Shrivastav | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-04 10:36 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Fetching data and function for additional charges | Ayush Singh,Mary Nisha | None | 2024-01-04 09:30 | 2024-01-05 19:00 | 2024-01-04 09:41 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679,775643568 | 73 | Late | 75 | 75 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Block the edit option for the users after 24 hr | Vignesh R | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-03 22:01 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 66 | Late | 67 | 67 | 1 | days |  | Clear
7.4981e+17 | No need to add Damage and Shortage Qty in Batch Details | Vignesh R | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-03 21:52 | In Progress | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 68 | Late | 69 | 69 | 1 | days |  | Clear
7.4981e+17 | No Need to check the Payment Status - Based on the Invoice CN want to be created | Vignesh R | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-03 21:42 | In Progress | Yes | 10% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 70 | Late | 71 | 71 | 1 | days |  | Clear
7.4981e+17 | Enable Discount Button - Based on that show the Discount in SO | Vignesh R | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-03 21:33 | In Progress | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 69 | Late | 70 | 70 | 1 | days |  | Clear
7.4981e+17 | Give option to update the Payment Status as Paid and add the Paid Amount ( Advance payment based on PO ) | Vignesh R | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-03 21:24 | Development Complete | Yes | 10% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 74 | Late | 75 | 75 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Assingment and SLA testing for Admin & Vigilance department | Swetha K | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 09:33 | Done | No | 100% | IIFL SAMASTA -Zoho Creator_Helpdesk CR | Milestone One-Customization and Development of Change Request for Zoho Help Desk | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Bill Payment Books Integration | Aaftab Ahmad | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-04 10:24 | Development Complete | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 776475994 | 66 | Late | 67 | 67 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Tax Books Integration | Aaftab Ahmad | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 10:24 | Development Complete | Yes | 10% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 776475994 | 74 | Late | 75 | 75 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Vendor Master Books Integration | Aaftab Ahmad | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-04 10:24 | Development Complete | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 776475994 | 73 | Late | 74 | 74 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | "Alternate workaround for Sharing permission settings. This will be shared separately over an email with solution approach and efforts.Sharing Permission - No of Users Limitations" | Siddharth Sharma | None | 2024-01-22 09:30 | 2024-01-26 19:00 | 2024-01-04 09:57 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 | 52 | Late | 57 | 57 | 5 | days |  | Clear
7.4981e+17 | Zoho sheet - zoho crm integration for valves | Siddharth Sharma | None | 2024-01-03 09:30 | 2024-01-05 19:00 | 2024-01-04 09:31 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 | 34 | Late | 37 | 37 | 3 | days
7.4981e+17 | iDatalytics Scrum Meeting | Irshad Pasha | None | 2024-01-04 11:30 | 2024-01-04 12:30 | 2024-01-03 16:53 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 701341459 | 74 | Late | 75 | 75 | 1 | hrs |  | Clear
7.4981e+17 | Test Case 4- Membership Renewal | Christina Santos | None | 2024-01-19 09:30 | 2024-03-22 19:00 | 2024-01-03 18:43 | In Progress | No | 80% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 808004288 | 825341377 | -4 | On Time | 60 | 60 | 46 | days
7.4981e+17 | Workflow & Automations- Churn Process | Dharanidharan C | None | 2024-01-18 09:30 | 2024-01-19 19:00 | 2024-01-03 17:40 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 10 | Late | 12 | 12 | 2 | days
7.4981e+17 | Integration of Creator to Zoho CRM | Dharanidharan C | None | 2024-01-11 09:30 | 2024-01-17 19:00 | 2024-01-03 17:25 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 12 | Late | 19 | 19 | 5 | days
7.4981e+17 | Member Portal Homepage Dashboard - User Management, Member Details, MBE search and connections | Dharanidharan C | None | 2024-02-05 09:30 | 2024-02-27 19:00 | 2024-01-03 17:21 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 13 | Late | 36 | 36 | 17 | days
7.4981e+17 | Workflow & Automations- Webinar Flow, other emails | Dharanidharan C | None | 2024-01-03 09:30 | 2024-01-17 19:00 | 2024-01-03 17:16 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 12 | Late | 27 | 27 | 11 | days
7.4981e+17 | Integration of CRM To Zoho Desk | Dharanidharan C | None | 2024-01-03 09:30 | 2024-01-17 19:00 | 2024-01-03 17:11 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 12 | Late | 27 | 27 | 11 | days
7.4981e+17 | Workflow & Automations- Subscription flow | Dharanidharan C | None | 2023-12-26 09:30 | 2024-01-05 19:00 | 2024-01-03 17:08 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 5 | Late | 16 | 16 | 9 | days
7.4981e+17 | Creation of Email templates - Member Registration | christina santos | None |  |  | 2024-01-03 17:07 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 825341377 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Configuration Member Contacts Field(i.e. Contact Module) | Dharanidharan C | None | 2023-12-21 09:30 | 2024-03-15 19:00 | 2024-01-03 16:57 | In Progress | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 3 | Late | 89 | 89 | 62 | days
7.4981e+17 | Create UI of Bookings Acknowledgement Page | Dharanidharan C | None | 2024-01-03 09:30 | 2024-01-17 19:00 | 2024-01-03 16:10 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 12 | Late | 27 | 27 | 11 | days
7.4981e+17 | Create Workflow & Automations, Blueprint Creation | Dharanidharan C | None | 2023-12-18 09:30 | 2024-01-03 19:00 | 2024-01-03 16:07 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 7 | Late | 24 | 24 | 13 | days
7.4981e+17 | Weekly Meeting. | Monik Chettiyar | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-03 15:45 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Exit Checklist - Document Understanding | Monik Chettiyar | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-03 14:10 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 76 | Late | 77 | 77 | 1 | days
7.4981e+17 | Migration from Google Drive to Zoho Workdrive | Irshad Pasha | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-03 11:17 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 701341459 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Zoho Bookings Multiple user issue fix development | M S Satya | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-04 12:08 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 69 | Late | 70 | 70 | 1 | days |  | Clear
7.4981e+17 | Arya Samaj ¦ Admin Management and People Management issues discussion | Maninder Singh | None | 2024-01-03 12:00 | 2024-01-03 13:00 | 2024-01-03 11:57 | Done | No | 100% | Arya Samaj - Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 0 | Late | 1 | 1 | 1 | hrs |  | Clear
7.4981e+17 | "Student ID" field name is not same for Hindi language.I can apply for same date multiple time for same student. | Maninder Singh | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-03 11:01 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 74 | Late | 75 | 75 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | " need question mark for" How much monthly fee can you pay for your children's studies in Gurukul" field. | Maninder Singh | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 10:56 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 75 | Late | 76 | 76 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Item Transfer changes | Mallesh M S | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-04 10:06 | In Progress | Yes | 10% | Ecovinal Project 3 - Farmer Management | None | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 60 | Late | 61 | 61 | 1 | days |  | Clear
7.4981e+17 | Client Meeting | Supril Jain | None | 2024-01-04 09:30 | 2024-02-13 19:00 | 2024-01-03 23:50 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 27 | Late | 68 | 68 | 29 | days |  | Clear
7.4981e+17 | Follow Up Email Notification - Enquiry | Nikita Srivastava | None | 2024-01-11 09:30 | 2024-01-12 19:00 | 2024-01-03 23:28 | To Do | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 774653652 | 66 | Late | 68 | 68 | 2 | days
7.4981e+17 | Enquiry Management Blueprint | Nikita Srivastava | None | 2024-01-09 09:30 | 2024-01-12 19:00 | 2024-01-03 23:23 | To Do | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 774653652 | 66 | Late | 70 | 70 | 4 | days
7.4981e+17 | Go Live Support | Irshad Pasha,Achyuth T M | None | 2024-01-03 09:30 | 2024-01-05 19:00 | 2024-01-04 10:08 | Terminated/Cancelled | No | 100% | Thoucentric_Zoho Books | Milestone Three-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 701341459,708853094 | 0 | Late | 3 | 3 | 3 | days |  | Clear
7.4981e+17 | External meeting with Durain Team & WordPress developer for integration | Sachin Patil | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 18:26 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | IIFL Scrum Call with Client | Selva Bharathi | None | 2024-01-04 10:30 | 2024-01-04 11:30 | 2024-01-03 17:39 | To Do | Yes | 0% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 701368573 | 74 | Late | 75 | 75 | 1 | hrs |  | Clear
7.4981e+17 | Quote Integration with Zoho CRM | Anusuyadevi V,Tanu Gupta | High | 2024-01-08 09:30 | 2024-01-09 19:00 | 2024-01-03 17:00 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 786479121,790157522 | 1 | Late | 3 | 3 | 2 | days
7.4981e+17 | User manual Update | Kiran Shrivastav | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 10:40 | Done | No | 100% | Karam Safety_Zoho ONE | Milestone Six-Implementation of Zoho Recruit | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 1 | Late | 2 | 2 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | Organisation Documents in Zoho Creator | Mohan Kumar | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-04 12:44 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Branch Books Integration | Vignesh R,Aaftab Ahmad | None | 2024-01-03 09:30 | 2024-01-04 19:00 | 2024-01-04 09:35 | Development Complete | Yes | 10% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 776475994 | 704175602,776475994 | 74 | Late | 76 | 76 | 2 | days |  | Clear | Waheeba Khan
7.4981e+17 | Zoho Inventory Sales Order Issue | Vaikuntam Chowdary | None | 2024-01-02 09:30 | 2024-01-03 19:00 | 2024-01-03 18:13 | In Progress | Yes | 10% | Karam Safety_Zoho ONE | None | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 75 | Late | 77 | 77 | 2 | days |  | Clear
7.4981e+17 | Order Management Flow testing | Mohammed Yusha,Vaikuntam Chowdary | None | 2024-01-09 15:00 | 2024-01-09 18:30 | 2024-01-03 17:20 | Done | No | 100% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 701373265,778472746 | 8 | Late | 9 | 9 | 3.5 | hrs |  | Clear
7.4981e+17 | Date and Amount validations | Anusuyadevi V,Tanu Gupta | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 15:42 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121,790157522 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Presentation on Advance Block | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Supply Workflow | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Advane and Credit blocks - Use case Understanding | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Masters discussion Pubsub/ERP/Salesforce | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Phase 1 Solutioning | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Work Shop 1 - Ledger | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Issue in Bills Push to Books | Vignesh R | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 15:27 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | Zoho Purchase and Inventory | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 76 | Late | 77 | 77 | 1 | days |  | Clear
7.4981e+17 | CRM Feedback ChangesAccounts,Contacts and Deals Module field level ValidationResolution of Hiren queries as documented | Sai Krishna | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 09:32 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 75 | Late | 76 | 76 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | STEERWORLD AMC Support Jan 23 FF | Sai Krishna | None | 2024-01-04 09:30 | 2024-01-17 19:00 | 2024-01-03 09:24 | To Do | Yes | 0% | AMC - VAlign | STEER Engineering Private Limited - Zoho CRM And Analytics ¦ 05-07-2023 ¦ 04-07-2024 | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 61 | Late | 75 | 75 | 10 | days
7.4981e+17 | Zoho Inventory & Shopify Integration | Mohammed Yusha,Shavi Thakur,Tanu Gupta | High | 2024-01-03 09:30 | 2024-01-04 19:00 | 2024-01-02 23:30 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,773081417,790157522 | 4 | Late | 6 | 6 | 2 | days
7.4981e+17 | Contact Info for Pre Leads and Leads | Tanu Gupta | High | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 23:24 | Done | No | 100% | AMC - VAlign | Infifresh 01-01-2024 to 31-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Related List and Automation to create and access creator Quote | Anusuyadevi V | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-03 09:06 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Error in people - payroll sync | Kiran Shrivastav | None | 2024-01-09 09:30 | 2024-01-10 19:00 | 2024-01-02 18:33 | Done | No | 100% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 47 | Late | 49 | 49 | 2 | days
7.4981e+17 | Post Go-Live Support | Anusuyadevi V,Tanu Gupta | High | 2024-01-02 09:30 | 2024-01-05 19:00 | 2024-01-02 17:23 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 786479121,790157522 | 1 | Late | 5 | 5 | 4 | days
7.4981e+17 | Change to COO approval instead of CBO approval in IGL new, split and DCL flow | Swetha K | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 19:14 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Fwd: Expense Management Error while uploading December conveyance + RM Email Change | Aaftab Ahmad | High | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 17:57 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 776475994 | 776475994 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Project Status Meetings | Supril Jain | None | 2024-01-03 09:30 | 2024-01-31 19:00 | 2024-01-03 09:47 | To Do | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 47 | Late | 76 | 76 | 21 | days
7.4981e+17 | Open Queries | unassigned | None | 2023-12-07 09:30 | 2024-01-12 19:00 | 2024-01-02 19:11 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 671373250 | - | 66 | Late | 103 | 103 | 27 | days |  | Clear
7.4981e+17 | Re: Full and Final Settlement Process for Employee Hrushikesh | Rishikesh Gogha | None | 2023-12-20 09:30 | 2023-12-20 19:00 | 2024-01-02 14:53 | Done | No | 100% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 15 | Late | 16 | 16 | 1 | days
7.4981e+17 | RE: TDS & Other Statutory Clarification | Rishikesh Gogha | None | 2023-12-11 09:30 | 2023-12-11 19:00 | 2024-01-02 14:27 | Done | No | 100% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 24 | Late | 25 | 25 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Betterplace: Bank Statement | Rishikesh Gogha | None | 2023-12-05 09:30 | 2023-12-05 19:00 | 2024-01-02 14:11 | Done | No | 100% | AMC - VAlign | Better Place Support Activity | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 30 | Late | 31 | 31 | 1 | days
7.4981e+17 | Invoice - Field Mapping in Custom Function | Mallesh M S | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-02 10:27 | To Do | Yes | 0% | The Yarn Bazar - TYBZ - CR001 | Milestone Two-Completion of Solution Development, Testing and Zoho Creator CR Go - Live | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 59 | Late | 60 | 60 | 1 | days |  | Clear
7.4981e+17 | API - Testing | Vaikuntam Chowdary,Mallesh M S | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-02 10:27 | In Progress | Yes | 10% | The Yarn Bazar - TYBZ - CR001 | Milestone Two-Completion of Solution Development, Testing and Zoho Creator CR Go - Live | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778472746,778475418 | 75 | Late | 76 | 76 | 1 | days |  | Clear
7.4981e+17 | working on the issues related to gurukul admission form | Maninder Singh | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 09:37 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 76 | Late | 77 | 77 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Consolidated Quote Template | Anusuyadevi V,Tanu Gupta | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-02 10:36 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121,790157522 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Deal - Validation create record in creator only if pipeline is PMD. | Ayush Singh | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 10:30 | Done | No | 100% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 1 | Late | 2 | 2 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Write Workflow And Validation For Subscription | Aaftab Ahmad | None | 2023-12-29 09:30 | 2024-01-02 19:00 | 2024-01-02 09:30 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 776475994 | 776475994 | 7 | Late | 12 | 12 | 3 | days |  | Clear | Waheeba Khan
7.4981e+17 | Add FG Value in the Inventory | Shavi Thakur | None | 2024-03-18 09:30 | 2024-03-18 19:00 | 2024-03-15 18:33 | To Do | No | 0% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Three-Order Management System | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 0 | On Time | 1 | 1 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Machani Dedicated Resource. | Mohan Kumar | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 11:58 | In Progress | Yes | 0% | Machani Dedicated Resource extension | Milestone One-Dedicated Resource for March 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Creating Additional Document form | Pavan S | None | 2024-03-16 18:45 | 2024-03-16 19:15 | 2024-03-16 18:44 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 845599619 | 845599619 | 2 | Late | 3 | 3 | 0.5 | hrs |  | Not Clear
7.4981e+17 | Document for email notifications file | Mary Nisha | High | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 11:02 | In Progress | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Test RMSDC- Chicago Wave1 data | Prableen Kaur | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 14:19 | To Do | Yes | 0% | iDATALYTCS UI PATH | None | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | OLL BOM- ER2M | Ranjana Poojari | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 09:02 | In Progress | Yes | 0% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 3 | Late | 4 | 4 | 1 | days |  | Clear
7.4981e+17 | Lapse reminder schedulers and Email Notif | Mallesh M S | None | 2024-03-04 09:30 | 2024-03-18 19:00 | 2024-03-15 16:20 | Ready for QC | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 778475418 | 0 | On Time | 15 | 15 | 11 | days
7.4981e+17 | Issue on Zoho payroll in documents uploading | Rishikesh Gogha | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 10:30 | To Do | Yes | 0% | AMC - VAlign | HESPL AMC - 2023 - 24 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Data Validation/ QC (including workflows, automations, integrations reports & Dashboard) | Dharanidharan C | None | 2024-03-13 09:30 | 2024-03-21 19:00 | 2024-03-16 01:16 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 828527327 | 701371504 | -3 | On Time | 6 | 6 | 7 | days
7.4981e+17 | Client Meeting for Zoho desk | Monik Chettiyar | None | 2024-03-15 19:00 | 2024-03-15 19:00 | 2024-03-15 18:01 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 3 | Late | 4 | 4 | 0 | days
7.4981e+17 | Urgent: Zoho Desk Call Activity Not Reflecting in Tickets | Monik Chettiyar | None | 2024-03-15 19:00 | 2024-03-15 19:00 | 2024-03-15 13:18 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 3 | Late | 4 | 4 | 0 | days
7.4981e+17 | Stepper Progress bar dynamic Tick mark | Mallesh M S | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 11:33 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 778475418 | 778475418 | 3 | Late | 4 | 4 | 1 | days |  | Clear
7.4981e+17 | Send Ticket Closure Email and Feedback Email to Customer based on Selected Check Box(Check Box - Closure Email and Feedback Email) | Sachin Patil | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 10:01 | In Progress | Yes | 0% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Approval Configuration for PR for CABH and funding car | Aishwarya T | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 17:45 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 3 | Late | 4 | 4 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Checkout function implementation | Mohan Kumar,Kiran Shrivastav | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-15 15:44 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 778473538791842987 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Exit Process implementation | Kiran Shrivastav | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 09:58 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Payment receipt automation and Payment Object Creation and Cancellation | Vaikuntam Chowdary | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 17:42 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Client Meetings | Rajesh Shindagi | None |  |  | 2024-03-14 17:13 | In Progress | No | 0% | Dr Reddy’s - Zoho CRM, Desk, SalesIQ | Milestone Three-1. Completion of Configuration, Customization2. Solution Demo3. User acceptanc | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 |  | On Time |  | 0 | 0 | days
7.4981e+17 | NMSDC Data Template | Mary Nisha | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 12:02 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 4 | Late | 5 | 5 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Zoho CRM - Deal to Quotes Correction | Monik Chettiyar | None | 2024-03-14 19:00 | 2024-03-14 19:00 | 2024-03-14 14:28 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 4 | Late | 5 | 5 | 0 | days
7.4981e+17 | Data Migration - Invoices | Tanu Gupta | None | 2024-03-14 09:30 | 2024-03-15 19:00 | 2024-03-14 14:00 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 3 | Late | 5 | 5 | 2 | days |  | Clear | Supril Jain
7.4981e+17 | Creating Validation for the E-Sign | Kalyanasundaram L | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 12:49 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 819676542 | 4 | Late | 5 | 5 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Clientjoy Tickets migrating into Zoho desk | Tanu Gupta | Medium | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 16:57 | Done | No | 100% | AMC - VAlign | Synup Digital Pvt Ltd - Zoho CRM & Desk ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Visitor management call with sudeep and team | Aishwarya T | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 17:13 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | 5002504 - Vimukti Girls School, Jaipur- Final installment asset invoice request-R23 | Swetha K | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 15:48 | To Do | Yes | 0% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Approval Configure for PR for IT Assets | Aishwarya T | None | 2024-03-14 09:30 | 2024-03-21 19:00 | 2024-03-14 12:45 | In Progress | No | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | -3 | On Time | 5 | 5 | 6 | days |  | Clear | Sai Krishna
7.4981e+17 | Internal Meeting on Data Migration Process | Rishikesh Gogha | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 09:44 | To Do | Yes | 0% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 4 | Late | 5 | 5 | 1 | days |  | Clear
7.4981e+17 | VSI Client Call | Sai Krishna | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-14 09:26 | Done | No | 100% | AMC - VAlign | VSI-Estore | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Working on March Deliverables | Nirmalkrishnan H | None | 2024-03-14 09:30 | 2024-03-15 19:00 | 2024-03-14 09:18 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 840979277 | 840979277 | 3 | Late | 5 | 5 | 2 | days |  | Clear
7.4981e+17 | Project Status Report WE14.3 | Stuti S. Kulshrestha | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 09:01 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | COA integrations | Tanu Gupta | Medium | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 09:31 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Books -Data Migration Template Preparation | Stuti S. Kulshrestha | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 11:19 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Internal meeting for payment integration via zoho sites to creator | Sai Krishna,Tanu Gupta | High | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 10:28 | In Progress | Yes | 10% | Namma Sampradaya_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 753339779790157522 | 4 | Late | 5 | 5 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Connect for a Call with VSI | Ayush Singh | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 17:54 | In Progress | Yes | 10% | VSINTERCONNECT CR for Estore | Milestone Two-Development, UAT & Go Live of Estore CR | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 5 | Late | 6 | 6 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Invoice Automation for other instalements | Swetha K | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 16:52 | In Progress | Yes | 0% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Recruit Demo_Haqdarshak | Kiran Shrivastav | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 16:58 | To Do | Yes | 0% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | UAT feedback for application submission process - Changes | Mallesh M S | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 17:34 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 778475418 | 778475418 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | Hierarchy Dashboard | Anusha V | High | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 15:52 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Zoho desk | Monik Chettiyar | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 10:01 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Thoucentric: PAYROLL - RECRUIT Integration | Rishikesh Gogha | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 14:43 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Management and Control Section Ui Development | Kalyanasundaram L,Avinash Sah,Pavan S | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 12:26 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 8.19676542830177E26 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | internal meetings | Vikram Pai V | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 10:44 | In Progress | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 845596686 | 845596686 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Push FG value from Books Stock Adj to Creator Stock Adj module | Shavi Thakur | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-12 18:29 | To Do | Yes | 0% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Three-Order Management System | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 5 | Late | 6 | 6 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Bills migration | Rishikesh Gogha | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 14:30 | To Do | Yes | 0% | SPERA - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Internal Meeting | Anas Ahmed | None |  |  | 2024-03-12 12:16 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Business Type | Subash Samuthirapandiyan | None |  |  | 2024-03-12 21:38 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 770263143 | 770263143 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | testing, tech support, KT, internal Assistance , meetings | Selva Bharathi | None | 2024-03-02 09:30 | 2024-03-02 19:00 | 2024-03-12 17:52 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573 | 16 | Late | 17 | 17 | 1 | days
7.4981e+17 | Client Visit | Selva Bharathi | None |  |  | 2024-03-12 15:23 | To Do | No | 0% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Two-Zoho Creator – OrderManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Contacts Accounts Import in the CRM | Ayush Singh,Mary Nisha | None | 2024-03-12 09:30 | 2024-03-13 19:00 | 2024-03-12 12:26 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679,775643568 | 5 | Late | 7 | 7 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | CRM Update | P Renuka Choudhary,Naveen M | None |  |  | 2024-03-13 13:24 | In Progress | No | 0% | Sales Activities | None | 7.4981e+17 | 7.4981e+17 |  | 829366386 | 765907894,829366386 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Zoho Bookings appointment support | Supril Jain | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 11:16 | To Do | Yes | 0% | AMC - VAlign | Janisthaa Fertility And IVF Centre - Zoho CRM ¦ 07-06-2023 ¦ 06-06-2024 | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | R&D (Alain Charles )/S | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 10:29 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 808004288,844784545 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Develop Bot to generate log report | Prableen Kaur | None | 2024-03-27 09:30 | 2024-03-28 19:00 | 2024-03-12 19:16 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 792886644 | 792886644 | -10 | On Time | -8 | -8 | 2 | days
7.4981e+17 | Annual Sales revenue mapping | Vikram Pai V | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 15:44 | Done | No | 100% | iDATALYTCS UI PATH | None | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 845596686 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Daily Standup | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-11 09:30 | 2024-03-15 19:00 | 2024-03-12 12:44 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 808004288,844784545 | 3 | Late | 8 | 8 | 5 | days
7.4981e+17 | Internal Meeting (Full Stack Developer Training) | Anas Ahmed | None |  |  | 2024-03-13 12:32 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Internal call/review call | Swetha K | None |  |  | 2024-03-13 10:24 | To Do | No | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 |  | On Time |  | 0 | 0 | days |  | Clear | Waheeba Khan
7.4981e+17 | Payment Object Cancellation through custom API and Order Cancellation | Vaikuntam Chowdary | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 09:25 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Daily task calls | Sai Krishna,Aishwarya T | None | 2024-03-12 09:30 | 2024-03-22 19:00 | 2024-03-12 16:25 | To Do | No | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | -4 | On Time | 7 | 7 | 9 | days |  | Clear | Sai Krishna
7.4981e+17 | Requirement gathering for Daily Data Migration | Prableen Kaur | None | 2024-03-13 09:30 | 2024-03-14 19:00 | 2024-03-13 17:38 | To Do | Yes | 0% | iDATALYTCS UI PATH | None | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 4 | Late | 6 | 6 | 2 | days
7.4981e+17 | Meeting Preparation | Devaraju S J | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 14:32 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 5 | Late | 6 | 6 | 1 | days |  | Not Clear
7.4981e+17 | ZOho Booking : Modifications in timings | Rishikesh Gogha | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 11:44 | To Do | Yes | 0% | AMC - VAlign | Janisthaa Fertility And IVF Centre - Zoho CRM ¦ 07-06-2023 ¦ 06-06-2024 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Business Information - Function Creation for Insert record - Recertification Process | Mallesh M S,Amrutha H V | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 11:27 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 778475418 | 778475418,845600661 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | HESPL: Re: Zoho Expense issue: Rahul Shinde | Rishikesh Gogha | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 10:20 | To Do | Yes | 0% | AMC - VAlign | HESPL AMC - 2023 - 24 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Spot award Requirement Discussion | Kiran Shrivastav | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 17:53 | To Do | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | 6073 Client call regarding regarding changes in VMS | Tanu Gupta | Medium | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 14:46 | In Progress | Yes | 0% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Weekly Meeting | Vignesh R | None | 2024-03-13 09:30 | 2024-03-15 19:00 | 2024-03-13 12:12 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 3 | Late | 6 | 6 | 3 | days
7.4981e+17 | Automation of Create Vendor in Creator and Books - Custom API | Anusuyadevi V | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 09:25 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Impot the item and Bills | Devaraju S J | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 18:58 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Rejection form for HOD late submision | Swetha K | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 10:41 | Done | No | 100% | IIFL SAMASTA - IMS Enhancement 3.5 | Milestone Two-Zoho Creator: Customization, Configuration, Testing and Go-Live of IMS enhancement | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Requirement Discovery Session | Mohammed Yusha,M S Satya | None | 2024-03-12 09:30 | 2024-03-13 19:00 | 2024-03-12 11:07 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,789497933 | 2 | Late | 4 | 4 | 2 | days
7.4981e+17 | Client Meeting | Kalyanasundaram L | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 11:10 | In Progress | Yes | 10% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 6 | Late | 7 | 7 | 1 | days |  | Clear
7.4981e+17 | Technical discussion | Dharanidharan C | None | 2024-03-11 09:30 | 2024-03-15 19:00 | 2024-03-11 15:08 | To Do | Yes | 0% | Right Horizons Financial Services Pvt Ltd. - Zoho CRM, Creator, Analytics | None | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 3 | Late | 8 | 8 | 5 | days
7.4981e+17 | Data validation and endpoint checking | Anas Ahmed | None |  |  | 2024-03-12 09:46 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Digital Campaign convert to Lead Automation Review | Dharanidharan C | None | 2024-03-07 09:30 | 2024-03-08 19:00 | 2024-03-11 19:22 | To Do | Yes | 0% | Right Horizons Financial Services Pvt Ltd. - Zoho CRM, Creator, Analytics | None | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 10 | Late | 12 | 12 | 2 | days
7.4981e+17 | Zoho Desk Ticket, Update In-Progess Date after Change Ticket Status to in-progess | Sachin Patil | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 17:29 | In Progress | Yes | 0% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | EMAIL TRIGGER ISSUE | Rishikesh Gogha | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-12 10:05 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Integration with CRM | Anusha V | High | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-12 09:37 | To Do | Yes | 0% | QUICK HEAL - Zoho CRM & Zoho Marketing Automation | Milestone One-Advance Payment for Project Initiation | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Configuring workflow/function for Allocation of CS | Aman Kumar | None |  |  | 2024-03-11 17:15 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Client Visit on 12-Mar-2024 | Vignesh R | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 09:59 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Internal Discussion | Mohammed Yusha,Vignesh R,Tanu Gupta | None | 2024-03-11 09:30 | 2024-03-15 19:00 | 2024-03-11 17:45 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 701373265,704175602,790157522 | 3 | Late | 8 | 8 | 5 | days |  | Clear
7.4981e+17 | Data Migration for bills & expense - post september 2023 | Tanu Gupta | High | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 10:14 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 6 | Late | 7 | 7 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Feedback points - 12/3 | Swetha K | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 09:34 | Done | No | 100% | IIFL SAMASTA- Admin Module CR | None | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | PRD review - Zoho<>ERP ledger blocking | Waheeba Khan | None |  |  | 2024-03-11 17:08 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | User Setup Configuration | Dharanidharan C | None | 2024-03-13 09:30 | 2024-03-15 19:00 | 2024-03-11 14:26 | To Do | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 3 | Late | 6 | 6 | 3 | days
7.4981e+17 | Open Issues - Release 1 and 2 | Dharanidharan C | None | 2024-03-11 09:30 | 2024-03-15 19:00 | 2024-03-11 14:19 | In Progress | Yes | 80% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 3 | Late | 8 | 8 | 5 | days
7.4981e+17 | Member Renewal Deals and invoice Creation | Dharanidharan C | None | 2024-03-11 19:00 | 2024-03-15 19:00 | 2024-03-11 14:10 | To Do | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 3 | Late | 8 | 8 | 4 | days
7.4981e+17 | Api configuration setup | Nikita Srivastava | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 11:43 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Running Java project local and migrating data to mysql | Anas Ahmed | None |  |  | 2024-03-11 10:48 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Page layout correction and Invoice date and number issue for invoice automation | Swetha K | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 09:27 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | women's Day celebration | Amrutha H V | None |  |  | 2024-03-08 18:32 | To Do | No | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 845600661 | 845600661 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Document Exploration | Aman Kumar | None |  |  | 2024-03-11 13:11 | In Progress | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | PRD review - Zoho<>ERP ledger blocking | Waheeba Khan | None |  |  | 2024-03-11 12:37 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Order cancellation automations and zoho books to zoho creator DN,CN integration | Vaikuntam Chowdary | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 10:53 | To Do | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Form fields mandatory and functions | Mary Nisha | High | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 10:25 | Done | No | 100% | AMC - VAlign | First Meridian - Innov and V5 | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Call with Janani regarding creator accessibility | Tanu Gupta | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 18:36 | In Progress | Yes | 0% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Learning New Concept in Creator | Pavan S | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 10:52 | To Do | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 845599619 | 845599619 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Create Comms Method for Service Interruptions or Enhancements to Active Users | Christ Bellarmine | None | 2024-03-08 09:30 | 2024-03-29 19:00 | 2024-03-10 09:03 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 | -11 | On Time | 11 | 11 | 16 | days
7.4981e+17 | Search Enhancement 1. (Features------------------) | Christ Bellarmine | None |  |  | 2024-03-10 08:44 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Finalize Daily Migration Automation Process and Communication | Irshad Pasha | None | 2024-03-08 09:30 | 2024-03-12 19:00 | 2024-03-08 20:54 | In Progress | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 701341459 | 6 | Late | 11 | 11 | 3 | days
7.4981e+17 | User Allocation Issue Resolution and queries | M S Satya | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-11 13:21 | To Do | Yes | 0% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 10 | Late | 11 | 11 | 1 | days |  | Clear
7.4981e+17 | Internal Meetings and Discussions | Aman Kumar | None |  |  | 2024-03-11 12:49 | In Progress | No | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Add Material Cost to Credit Note and Sales Return PDF | Sachin Patil | None | 2024-03-11 09:30 | 2024-03-12 19:00 | 2024-03-11 10:47 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 6 | Late | 8 | 8 | 2 | days
7.4981e+17 | Women's Day Team Catchup | Nikita Srivastava | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 18:26 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Zoho connect POC Integration and Setup | Aman Kumar | None |  |  | 2024-03-08 15:43 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Store books id or Po , VB , vendor in creator Store books item id in creator and create vendor | Aishwarya T | None | 2024-03-08 09:30 | 2024-03-15 19:00 | 2024-03-08 14:18 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | -1 | On Time | 7 | 7 | 6 | days |  | Clear | Sai Krishna
7.4981e+17 | Creating PPT for presentation and give a presentation to Uday Sir | Amrutha H V | None | 2024-03-07 14:30 | 2024-03-07 18:30 | 2024-03-08 10:36 | Done | No | 100% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 845600661 | 845600661 | 1 | Late | 2 | 2 | 4 | hrs
7.4981e+17 | Project Management and Books Flow | Stuti S. Kulshrestha | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 09:47 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 10 | Late | 11 | 11 | 1 | days |  | Clear
7.4981e+17 | Perform Data Migration for GI | Supreeth R Kalluraya | None | 2024-03-22 09:30 | 2024-04-01 19:00 | 2024-03-07 22:01 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 788577227 | -14 | On Time | -3 | -3 | 7 | days
7.4981e+17 | Validate Sample Data Migrated | Hiren Vakharia | None | 2024-03-11 09:30 | 2024-03-12 19:00 | 2024-03-07 21:53 | In Progress | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 811424903 | 6 | Late | 8 | 8 | 2 | days
7.4981e+17 | Develop script for data mapping from Adaptone to Zoho | Christ Bellarmine,Prableen Kaur | None | 2024-03-04 09:30 | 2024-03-15 19:00 | 2024-03-07 21:43 | In Progress | Yes | 60% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486,792886644 | 3 | Late | 15 | 15 | 10 | days
7.4981e+17 | Business Description Section-Dynamic | Aman Kumar | None |  |  | 2024-03-07 20:37 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | General Information Section-Dynamic | Aman Kumar | None |  |  | 2024-03-07 19:58 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | scheduled attendance records at the end of every month to the finance team. | Kiran Shrivastav | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-03-08 09:30 | To Do | Yes | 0% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Call with Zoho Team regarding Territory view issue | Tanu Gupta | High | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 14:20 | Done | No | 100% | AMC - VAlign | HAPPY RELIABLE SURGERIES PRIVATE LIMITED - Zoho CRM and Zoho Form ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Budget Reject & Revision | Mohammed Yusha,Tanu Gupta | High | 2024-03-07 09:30 | 2024-03-08 19:00 | 2024-03-07 14:08 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 790157522 | 701373265,790157522 | 6 | Late | 8 | 8 | 2 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Create Report for all Forms in Required Documents | Pavan S | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 12:40 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 845599619 | 845599619 | 10 | Late | 11 | 11 | 1 | days |  | Not Clear
7.4981e+17 | Giving Presentation and Meeting with Uday Sir | Pavan S,Vikram Pai V,Amrutha H V | None | 2024-03-07 02:30 | 2024-03-07 18:30 | 2024-03-08 10:34 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 845599619 | 845599619,845596686,845600661 | 1 | Late | 2 | 2 | 16 | hrs
7.4981e+17 | Foreign Operating Company Sub - form population - backend Workflow written | Kalyanasundaram L,Pavan S | None | 2024-03-07 09:30 | 2024-03-08 19:00 | 2024-03-08 09:38 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542,845599619 | 10 | Late | 12 | 12 | 2 | days |  | Clear | Selva Bharathi
7.4981e+17 | Data Migration Template | Kalyanasundaram L,Amrutha H V | None |  |  | 2024-03-08 09:26 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 819676542,845600661 |  | On Time |  | 0 | 0 | days |  | Not Clear | Selva Bharathi
7.4981e+17 | Integration to push the PO from Creator to book | Aishwarya T | None | 2024-03-07 09:30 | 2024-03-15 19:00 | 2024-03-07 17:13 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | -1 | On Time | 8 | 8 | 7 | days |  | Clear | Sai Krishna
7.4981e+17 | Data Migration of MBE in Company and Poral Users (MBE) | Kalyanasundaram L | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 11:23 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 10 | Late | 11 | 11 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Business Size and Certifications | Subash Samuthirapandiyan | None |  |  | 2024-03-07 20:02 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 770263143 | 770263143 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Meeting on KRA's March 2024 | Kiran Shrivastav | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-07 18:31 | To Do | Yes | 0% | AMC - VAlign | Neelgund Project Zoho HRMS Implementation | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Compliance Review Flow | Mallesh M S | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-07 13:34 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 778475418 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Thoucentric Scrum call_Meeting details daily | Monik Chettiyar | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-07 12:19 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Addition of record in Certification form | Aman Kumar | None |  |  | 2024-03-08 12:34 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | MBE Search App Walk through | Omprakash Kumar | None |  |  | 2024-03-08 09:47 | In Progress | No | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 845321609 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Sidebar for desk Audit Dashboard | Avinash Sah | None | 2024-03-11 09:30 | 2024-03-12 19:00 | 2024-03-07 19:15 | Ready for QC | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 830176894 | 6 | Late | 8 | 8 | 2 | days
7.4981e+17 | SAP.OA.232415840 is canceled | Nikita Srivastava | None |  |  | 2024-03-07 16:05 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Integration while creating of items from books to creator | Aishwarya T | None | 2024-03-08 09:30 | 2024-03-15 19:00 | 2024-03-08 11:50 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | -1 | On Time | 7 | 7 | 6 | days |  | Clear | Sai Krishna
7.4981e+17 | Internal meeting | Devaraju S J | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 19:16 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | Proforma Invoice Amounts Calculation Based on Percentage | Sachin Patil | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 16:38 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Disable Convert to Credit Note Button After Create Credit Note and Update Status to Sales Return | Sachin Patil | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 15:14 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Correction in Masters/Documents API payload structure | Anusuyadevi V | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 12:17 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Project Status Report WE 07/03 | Stuti S. Kulshrestha | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 09:56 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Data Migration - Component Items & Composite Items Post sep 2023 | Tanu Gupta | High | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 20:50 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 12 | Late | 13 | 13 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Concern Creating JC, Zoho Desk | Tanu Gupta | Medium | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 20:34 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 12 | Late | 13 | 13 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Scrum Call we 07.03 | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 11:04 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288,844784545 | 7 | Late | 8 | 8 | 1 | days |  | Clear
7.4981e+17 | Zoho Books Solutioning - A& C | Supril Jain,Stuti S. Kulshrestha | None | 2024-03-06 11:00 | 2024-05-01 13:00 | 2024-03-06 19:43 | To Do | No | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 756836914,808004288 | -44 | On Time | 13 | 13 | 382 | hrs
7.4981e+17 | Understanding the initial steps to trigger the function | Anas Ahmed | None |  |  | 2024-03-06 13:55 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Zoho Expense training/S | Shiwani Kumari | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 13:21 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Selling price to be captured along with buying price, Profitability to be captured from the difference between the two: these fields are mandatory since the quotation stage till the closing stage. | M S Satya | None | 2024-03-04 09:30 | 2024-03-08 19:00 | 2024-03-06 10:00 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 10 | Late | 15 | 15 | 5 | days |  | Clear
7.4981e+17 | Important: Leave Type in Dropdown Menu | Kiran Shrivastav | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 09:32 | Done | No | 100% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Manual Update of Emp Master data is a tedious process | Siddharth Sharma | None |  |  | 2024-03-07 09:05 | To Do | No | 0% | Agappe - Zoho CRM Revamp Project | Milestone Two-Implementation of Zoho CRM - Sales & Service Management Application | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Refund scenerio not working in employee ledger statements | Maninder Singh | High | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 10:57 | In Progress | Yes | 0% | AMC - VAlign | EI - Zoho One Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Re: Global Plan Subscription Support - Zoho Books ¦ BetterplaceUser Acces | Rishikesh Gogha | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-06 10:06 | To Do | Yes | 0% | AMC - VAlign | Betterplace | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | UAT | Rishikesh Gogha | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-06 09:42 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Boldfit - Weekly Status Update Call - March 2024 | Tanu Gupta | Medium | 2024-03-06 09:30 | 2024-03-27 19:00 | 2024-03-06 17:47 | In Progress | No | 10% | (BoldFit) Sasvat_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | -9 | On Time | 13 | 13 | 16 | days |  | Clear | Supril Jain
7.4981e+17 | Subform feasibilty check for Billing date for next month date and Unit rate to auto populate in subform | Aishwarya T | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 15:16 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 12 | Late | 13 | 13 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-26 09:30 | 2024-03-15 19:00 | 2024-03-06 13:29 | Done | No | 100% | Machani Dedicated Resource extension | Milestone One-Dedicated Resource for March 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | -4 | On Time | 15 | 15 | 15 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-26 09:30 | 2024-03-15 19:00 | 2024-03-06 13:28 | Done | No | 100% | Machani Dedicated Resource extension | Milestone One-Dedicated Resource for March 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | -4 | On Time | 15 | 15 | 15 | days
7.4981e+17 | Client Meeting for access issues and quries | Shavi Thakur,Tanu Gupta | High | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-06 09:31 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 773081417,790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Backend_API_Testing | Omprakash Kumar | None | 2024-03-01 09:30 | 2024-03-11 19:00 | 2024-03-05 15:03 | In Progress | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 845321609 | 845321609 | 7 | Late | 18 | 18 | 7 | days
7.4981e+17 | Understanding codebase | unassigned | None |  |  | 2024-03-05 13:45 | In Progress | No | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 845321609 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | UAT by NMSDC team | unassigned | None | 2024-03-21 09:30 | 2024-03-29 19:00 | 2024-03-04 21:35 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | - | -11 | On Time | -2 | -2 | 7 | days |  |  | Selva Bharathi
7.4981e+17 | Application Layout | Pavan S | None | 2024-03-04 09:30 | 2024-04-03 19:00 | 2024-03-04 21:35 | In Progress | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 845599619 | -16 | On Time | 15 | 15 | 23 | days
7.4981e+17 | Recertification Process | Mallesh M S | None | 2024-03-06 09:30 | 2024-03-12 19:00 | 2024-03-04 21:35 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 778475418 | 6 | Late | 13 | 13 | 5 | days
7.4981e+17 | Creation of Notifications for E-Sign Process | Kalyanasundaram L | None | 2024-03-02 09:30 | 2024-03-02 19:00 | 2024-03-04 21:35 | Development Complete | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 819676542 | 16 | Late | 17 | 17 | 1 | days
7.4981e+17 | Summary form- Dynamic | Aman Kumar | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-04 21:35 | Development Complete | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 839251991 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | Validation Logs for HTML Page | Rahul S S | None | 2024-03-01 09:30 | 2024-03-04 19:00 | 2024-03-04 21:35 | Ready for QC | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 830176551 | 14 | Late | 18 | 18 | 2 | days
7.4981e+17 | Completion of Application Form with tool tips | Kalyanasundaram L,Pavan S | None | 2024-03-01 09:30 | 2024-03-05 19:00 | 2024-03-04 21:35 | Ready for QC | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 819676542,845599619 | 13 | Late | 18 | 18 | 3 | days
7.4981e+17 | Cleint call for sles return and credit note linking issue | Tanu Gupta | High | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-06 09:22 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Edit Packing List-D | Devaraju S J | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 18:39 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Update UOM, Inventory COA, Purchase COA and Sales COA to Creator Items from Zoho Books | Sachin Patil | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 19:46 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 14 | Late | 15 | 15 | 1 | days |  | Clear
7.4981e+17 | Check working of Invoice Main Form Cancel | Sachin Patil | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 19:38 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | call on PMS with apoorva | Kiran Shrivastav | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 20:27 | In Progress | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | ER2 OLL, ER2 MFC OLL | Kalyanasundaram L | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 11:22 | In Progress | Yes | 10% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 819676542 | 13 | Late | 14 | 14 | 1 | days |  | Clear
7.4981e+17 | VSI AMC Feb-24 | Sai Krishna | None | 2024-02-01 09:30 | 2024-02-29 19:00 | 2024-03-04 14:30 | Done | No | 100% | AMC - VAlign | VSI-Estore | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 4 | Late | 33 | 33 | 21 | days
7.4981e+17 | Multiple Mobile Number donor entry | Sai Krishna | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-03-04 14:07 | Done | No | 100% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 13 | Late | 14 | 14 | 1 | days |  | Clear
7.4981e+17 | Client Visit on 07-Mar-2024 | Vignesh R | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 10:23 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | File Level Validation | Kalyanasundaram L | None |  |  | 2024-03-06 21:24 | In Progress | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 770263143 | 819676542 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Spera Templates-D | Devaraju S J | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 18:49 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Issue in the Inventory stock, Check the flow related to inventory update | Vignesh R | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 15:12 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Zoho Expense Overview/S | Shiwani Kumari | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 19:02 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Payment Received Status Back update to Creator | Shavi Thakur | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 23:19 | Terminated/Cancelled | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Three-Order Management System | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Project report app(VA mile) | Omprakash Kumar | None | 2024-02-16 09:30 | 2024-02-26 19:00 | 2024-03-05 13:31 | In Progress | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 845321609 | 845321609 | 21 | Late | 32 | 32 | 7 | days
7.4981e+17 | Master API queries - Call | Waheeba Khan | None |  |  | 2024-03-05 11:59 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Project Management Solution Demo - Client | Mohammed Yusha,Vignesh R,Tanu Gupta | None | 2024-03-04 09:30 | 2024-03-05 19:00 | 2024-03-04 20:00 | In Progress | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,704175602,790157522 | 13 | Late | 15 | 15 | 2 | days |  | Clear
7.4981e+17 | Validation to fetch the inventory details When Work Order Convert to Material Issue and Finalize | Sachin Patil | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 19:27 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 13 | Late | 14 | 14 | 1 | days |  | Clear
7.4981e+17 | New fields in Accounts Module#5971 | Nikita Srivastava | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 18:26 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Upload attachments, Qeustion & Answers, sub-heads, validations | Tanu Gupta | High | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-05 12:28 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 3 | Late | 4 | 4 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Can we have date of uploading besides attachment in the form, to get an idea which is the latest uploaded document | Swetha K | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-05 10:03 | Done | No | 100% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 4 | Late | 5 | 5 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | 9. No. Of cases a suspect is involved in, should be auto fetched with the employee code | Swetha K | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-05 09:55 | Done | No | 100% | IIFL SAMASTA - IMS Enhancement 3.5 | Milestone Two-Zoho Creator: Customization, Configuration, Testing and Go-Live of IMS enhancement | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Purchase Order Version Testing and Corrections | Ranjana Poojari | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 09:20 | Done | No | 100% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Overview of CEEW/S | Shiwani Kumari | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 19:03 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Create IRP -D | Devaraju S J | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 18:58 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Roles and Permission setup | Twinkle Gupta | None | 2024-03-25 09:30 | 2024-03-29 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -11 | On Time | -6 | -6 | 5 | days
7.4981e+17 | Creation of Review application of update received | Twinkle Gupta | None | 2024-03-27 09:30 | 2024-03-27 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -9 | On Time | -8 | -8 | 1 | days
7.4981e+17 | Completion of reports required for Desk Audit | Twinkle Gupta | None | 2024-03-18 09:30 | 2024-03-29 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -11 | On Time | 1 | 1 | 10 | days
7.4981e+17 | Creation of validation for application form | Twinkle Gupta | None | 2024-03-20 09:30 | 2024-03-20 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -2 | On Time | -1 | -1 | 1 | days
7.4981e+17 | Completion of Reviewer Summary | Aman Kumar | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-04 21:27 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 839251991 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | RMSDC Views of Reports(Open Queu , Statuses ,etc.,) | Twinkle Gupta | None | 2024-03-15 09:30 | 2024-03-19 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -1 | On Time | 4 | 4 | 3 | days
7.4981e+17 | View , Update comment , old inputs for Each type of investor | Twinkle Gupta | None | 2024-03-06 09:30 | 2024-03-12 19:00 | 2024-03-04 21:27 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | 6 | Late | 13 | 13 | 5 | days
7.4981e+17 | Change layout and design of audit logs page and display audit log history for "General Information Documents" on the audit log page. | Maninder Singh | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-04 21:27 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 782721491 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Application Review(dynamic) with Subsection Redirection | Aman Kumar | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-04 21:27 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 839251991 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | BA Testing of Application Allocation forms | Supreeth R Kalluraya,Amrutha H V | None | 2024-03-13 09:30 | 2024-03-15 19:00 | 2024-03-04 21:27 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 788577227,845600661 | 3 | Late | 6 | 6 | 3 | days
7.4981e+17 | Aging of application Notification to all the CS | Aman Kumar | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-04 21:27 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 839251991 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Validation of allocation of RMSDC as per zipcode entered in the application | Twinkle Gupta | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-04 21:27 | QC Passed | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | TCS Journal Creation and Zoho Books to creator Integration | Vaikuntam Chowdary | None | 2024-03-05 09:30 | 2024-03-06 19:00 | 2024-03-06 09:30 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 12 | Late | 14 | 14 | 2 | days
7.4981e+17 | Allocate the task actual percentage based on the available percentage | Vignesh R | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 15:07 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 13 | Late | 14 | 14 | 1 | days |  | Clear
7.4981e+17 | Domestic Flow Changes Discussion and Testing - internal | Waheeba Khan | None | 2024-03-05 09:30 | 2024-03-06 19:00 | 2024-03-05 09:26 | To Do | Yes | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 12 | Late | 14 | 14 | 2 | days
7.4981e+17 | character search | Avinash Sah | None |  |  | 2024-03-04 16:13 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Page for Purchase Order with button customisation | Aishwarya T | None | 2024-03-01 09:30 | 2024-03-15 19:00 | 2024-03-04 12:26 | Development Complete | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 3 | Late | 18 | 18 | 11 | days |  | Clear | Sai Krishna
7.4981e+17 | New designation updates | Kiran Shrivastav | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 10:42 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Import Employee Master from Zoho People to Zoho Creator | Shavi Thakur | None | 2024-03-01 09:30 | 2024-03-01 11:00 | 2024-03-03 21:22 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 2 | Late | 3 | 3 | 1.5 | hrs
7.4981e+17 | Email Pop up UI | Avinash Sah | None |  |  | 2024-03-01 12:55 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Naics Redesign Ui Creation | Avinash Sah | None |  |  | 2024-02-29 18:15 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Automated Quotation Creation for AMC & Spares | Siddharth Sharma | None |  |  | 2024-03-04 08:53 | To Do | No | 0% | Agappe - Zoho CRM Revamp Project | Milestone Two-Implementation of Zoho CRM - Sales & Service Management Application | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Vendor Onboarding Home page with button customization | Aishwarya T | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-03-01 10:34 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 13 | Late | 15 | 15 | 2 | days |  | Clear | Sai Krishna
7.4981e+17 | GRN Quantity calculation and On click of close GRN the status of GRN record to be updated to closed | Sai Krishna,Aishwarya T | None | 2024-02-27 09:30 | 2024-02-29 19:00 | 2024-03-01 10:27 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 7 | Late | 10 | 10 | 3 | days |  | Clear | Sai Krishna
7.4981e+17 | Make place of supply lookup field disabled on purchase requisition form , and On vendor selection in purchase requisition form auto populate place of supply from vendor onboarding form and In purchase requisition form add a dropdown field for service type with options (Goods and Services) | Aishwarya T | None | 2024-02-27 09:30 | 2024-02-29 19:00 | 2024-03-01 10:21 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 18 | Late | 21 | 21 | 3 | days |  | Clear | Sai Krishna
7.4981e+17 | Project Management Demo | Stuti S. Kulshrestha | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 15:48 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 14 | Late | 15 | 15 | 1 | days |  | Clear
7.4981e+17 | Changes In GRN Workflow(Reverse the Flow). | Basavaraj Patil | None | 2024-02-12 09:30 | 2024-03-15 19:00 | 2024-03-01 17:03 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | None | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 3 | Late | 36 | 36 | 25 | days |  | Clear | Waheeba Khan
7.4981e+17 | Check Books Integration of Item , Vendor and Customer Master. | unassigned | None | 2024-03-26 09:30 | 2024-04-02 19:00 | 2024-03-01 16:52 | In Progress | No | 10% | Atlas - Zoho Creator - P & I, And OMS | None | 7.4981e+17 | 7.4981e+17 |  | 781564441 | - | -15 | On Time | -7 | -7 | 6 | days |  | Clear | Waheeba Khan
7.4981e+17 | UAT release 3 and updates | Dharanidharan C | None | 2024-02-01 09:30 | 2024-02-29 19:00 | 2024-03-01 12:40 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 18 | Late | 47 | 47 | 21 | days |  | Clear
7.4981e+17 | Internal testing | Rishikesh Gogha | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-03-04 10:24 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Email Notification: Invoice overdue¦ Sales PErson | Rishikesh Gogha | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-03-04 09:57 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | V-Align All Hands Meeting | Tanu Gupta | High | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-02 15:48 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | In the Sales Order, If Items are not associate with sales order then not allow to convert SO to Profoma Invoice | Sachin Patil | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-01 19:35 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | Field-mapping for RMSDC data | Prableen Kaur | None | 2024-02-27 09:30 | 2024-02-29 19:00 | 2024-03-01 16:02 | To Do | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 18 | Late | 21 | 21 | 3 | days
7.4981e+17 | Data Migration to Inventory for Samsung Electronic City Warehouse | Sachin Patil | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 19:42 | To Do | Yes | 0% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 18 | Late | 19 | 19 | 1 | days |  | Clear
7.4981e+17 | Update Budget allocation details month wise | Vignesh R | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-29 18:40 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 19 | Late | 20 | 20 | 1 | days |  | Clear
7.4981e+17 | Discovery Meeting- Books | Stuti S. Kulshrestha | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-01 15:36 | Done | No | 100% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Report Creation | unassigned | None | 2024-02-29 09:30 | 2024-03-29 19:00 | 2024-03-01 09:34 | To Do | No | 0% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 789497933 | - | -11 | On Time | 19 | 19 | 22 | days |  | Clear
7.4981e+17 | Stand up meeting-D | Devaraju S J | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 17:56 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 18 | Late | 19 | 19 | 1 | days
7.4981e+17 | Farm India ¦ Project Overview | Maninder Singh | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 12:42 | QA Completed | Yes | 10% | Farm India: Zoho Creator Change Request | None | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 18 | Late | 19 | 19 | 1 | days |  | Clear
7.4981e+17 | Zoho Books Go Live Meeting | Shavi Thakur | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 22:35 | To Do | Yes | 0% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Four-Financial Accounting Management System | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 18 | Late | 19 | 19 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Analyzing the search functionality on Catalyst for omptimization | Anas Ahmed | None |  |  | 2024-02-29 19:38 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Data population bug fix in drop down | Anas Ahmed | None |  |  | 2024-02-29 19:32 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Correcting the export functionality on search | Anas Ahmed | None |  |  | 2024-02-29 19:28 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Tree Structure - MBE Cert (HTML & CSS only) | Anas Ahmed | None | 2024-02-19 09:30 | 2024-02-20 19:00 | 2024-02-29 19:02 | In Progress | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | None | 7.4981e+17 | 7.4981e+17 |  | 842755527 | 842755527 | 27 | Late | 29 | 29 | 2 | days
7.4981e+17 | File handling with Redux in Tree Structure | Anas Ahmed | None |  |  | 2024-02-29 18:47 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | UI for Level 1 - Tree Structure | Anas Ahmed | None |  |  | 2024-02-29 18:42 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Create React Sub Component | Anas Ahmed | None |  |  | 2024-02-29 18:33 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Paternity leave issue (repeatedly not ok) | Kiran Shrivastav | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-02-29 14:21 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 19 | 19 | 2 | days
7.4981e+17 | Chaity Pathak – INNOO225 is not able update educational and other details | Kiran Shrivastav | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-02-29 14:21 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 19 | 19 | 2 | days
7.4981e+17 | Showing others instead of onduty | Kiran Shrivastav | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-02-29 14:18 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 19 | 19 | 2 | days
7.4981e+17 | CRM Sandbox Integration Issue | Siddharth Sharma | None |  |  | 2024-02-29 09:23 | To Do | No | 0% | AMC - VAlign | Agappe Tickets | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Redesign View Allocation Page | Tanu Gupta | High | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 23:48 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 8 | Late | 9 | 9 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Training of Zoho expense to Airowire/S | Shiwani Kumari | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 18:24 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Zoho Books - Requirement Gathering - Starstuff | Tanu Gupta,Manish | High | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 15:59 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522,833052784 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Client Meeting - 27/2/24 | M S Satya | None |  |  | 2024-02-28 09:52 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Checkmate Development | Dharanidharan C | None | 2024-03-14 19:00 | 2024-03-22 19:00 | 2024-02-27 21:55 | In Progress | No | 70% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 701371504 | -4 | On Time | 5 | 5 | 6 | days
7.4981e+17 | Vendor Integration Books to Creator | Shavi Thakur | None | 2024-02-26 09:30 | 2024-02-26 12:00 | 2024-02-26 18:28 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 21 | Late | 22 | 22 | 2.5 | hrs
7.4981e+17 | Client Meetings 26/2/24 | M S Satya | None |  |  | 2024-02-26 21:26 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | #5992 New Enhancements | Tanu Gupta | High | 2024-02-26 09:30 | 2024-03-04 19:00 | 2024-02-26 19:26 | In Progress | Yes | 0% | AMC - VAlign | HAPPY RELIABLE SURGERIES PRIVATE LIMITED - Zoho CRM and Zoho Form ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 14 | Late | 22 | 22 | 6 | days
7.4981e+17 | Users & Permission Setup | Shavi Thakur,Tanu Gupta | High | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-02-26 19:06 | To Do | Yes | 0% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 773081417,790157522 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | Ticket Module Customizations | Shavi Thakur,Tanu Gupta | High | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 19:01 | Done | No | 100% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 773081417,790157522 | 15 | Late | 16 | 16 | 1 | days
7.4981e+17 | Earned Leave balance Correction | Monik Chettiyar | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 16:42 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Project Catchup Plan and Review | Rishikesh Gogha | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 09:43 | To Do | Yes | 0% | SPERA - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 18 | Late | 19 | 19 | 1 | days
7.4981e+17 | ABMPL-Zoho Creator other Redemption Category flow discussion | Vaikuntam Chowdary | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-28 19:06 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 31 | Late | 32 | 32 | 1 | days |  | Clear
7.4981e+17 | Internal Call- Waheeba | Stuti S. Kulshrestha | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 10:29 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Payment Object Modeling and Automations and Ledger Summary Zoho Books Integration | Vaikuntam Chowdary | None | 2024-02-27 09:30 | 2024-02-28 19:00 | 2024-02-28 09:26 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 19 | Late | 21 | 21 | 2 | days
7.4981e+17 | Configure the new api for new leads -OBD | Nikita Srivastava | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-27 17:40 | In Progress | Yes | 0% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Change UOM to MTs in billing invoice page | Maninder Singh | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 09:33 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 11 | Late | 12 | 12 | 1 | days |  | Clear
7.4981e+17 | AIROWIRE ZOHO BOOKS QUERIES | unassigned | None |  |  | 2024-02-28 09:43 | To Do | No | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | COA Opening balance Issue | Rishikesh Gogha | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-28 09:33 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | None | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 20 | Late | 21 | 21 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Meeting to discuss a new requirement (task) related to Zoho Desk | Sachin Patil | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-27 19:29 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Support Meeting | unassigned | None | 2024-02-26 09:30 | 2024-02-27 19:00 | 2024-02-27 19:16 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | - | 20 | Late | 22 | 22 | 2 | days
7.4981e+17 | Sync Customers to Zoho Creator from Zoho Books | Sachin Patil | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-27 18:47 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 20 | Late | 21 | 21 | 1 | days |  | Clear
7.4981e+17 | UAT improvisations | Kiran Shrivastav | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 19:41 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Weekly Project Status Report WE 29.02.2024 | Stuti S. Kulshrestha | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 11:10 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Email alert required if there's any revision in the SO to the Dhyan Admin.(Super Admin) | M S Satya | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-29 09:01 | To Do | Yes | 0% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 19 | Late | 20 | 20 | 1 | days |  | Clear
7.4981e+17 | Invoices Import in ZOHO Books and Data Validation | Ayush Singh,Mary Nisha | None | 2024-02-27 09:30 | 2024-02-28 19:00 | 2024-02-28 18:36 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679,775643568 | 19 | Late | 21 | 21 | 2 | days |  | Clear
7.4981e+17 | ICAC and CCO template corrections and form updations | Mary Nisha | High | 2024-03-05 09:30 | 2024-03-06 19:00 | 2024-02-28 10:54 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 12 | Late | 14 | 14 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | ER2M 7Way and ER2M MFC BOM | Ranjana Poojari,Kalyanasundaram L | None | 2024-02-27 09:30 | 2024-02-28 19:00 | 2024-02-27 10:49 | In Progress | Yes | 0% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 778475421,819676542 | 19 | Late | 21 | 21 | 2 | days |  | Clear
7.4981e+17 | Requirement Discovery Session | Mohammed Yusha,Tanu Gupta | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 18:51 | Done | No | 100% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | #5862 - Inquiry Regarding Integration of Last Call Attempt Data into Zoho Analytics | Monik Chettiyar | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-29 00:11 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Email trigger for recommend and not recommend and other button action | Swetha K | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 19:35 | Done | No | 100% | IIFL SAMASTA- Admin Module CR | Milestone One-Advance payment for Admin Module Change Request | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 15 | Late | 16 | 16 | 1 | days
7.4981e+17 | Weekly - Scrum Call | Mohammed Yusha,Tanu Gupta | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 18:46 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Testing of flow | Tanu Gupta | High | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-28 09:43 | Done | No | 100% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Email Data template - Attach an attachment in the Email | Ayush Singh | None | 2024-02-19 09:30 | 2024-02-20 19:00 | 2024-02-27 17:11 | Done | No | 100% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 16 | Late | 18 | 18 | 2 | days
7.4981e+17 | Setting Up Policies | Rishikesh Gogha | None | 2024-02-26 09:30 | 2024-02-27 19:00 | 2024-02-27 15:57 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 20 | Late | 22 | 22 | 2 | days
7.4981e+17 | Discussion on Probation confirmation workflow error | Kiran Shrivastav | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 15:10 | To Do | Yes | 0% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Zoho CRM Quotes Module Product is not getting push and Deals issue | Monik Chettiyar | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-23 21:29 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 38 | Late | 39 | 39 | 1 | days
7.4981e+17 | Zoho People Exit Checklist Data Correction | Monik Chettiyar | None | 2024-02-08 09:30 | 2024-02-09 19:00 | 2024-02-23 21:16 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 38 | Late | 40 | 40 | 2 | days
7.4981e+17 | UAT Support | Shavi Thakur | None | 2024-02-22 15:30 | 2024-02-22 19:00 | 2024-02-22 21:07 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Four-Financial Accounting Management System | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 10 | Late | 11 | 11 | 3.5 | hrs |  | Clear | Mohammed Yusha
7.4981e+17 | Data Discrepancy - EHV | Ranjana Poojari | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-26 09:28 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 18 | Late | 19 | 19 | 1 | days
7.4981e+17 | Ozone Chart of accounts-D | Devaraju S J | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 18:11 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | Send Communication to Wave 1 MBE's | Stefan Bradham | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-02-22 21:59 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 836353936 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Write a Custom function for Vendor Status back update to Creator and Create Bill Export Excel | Shavi Thakur | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-26 02:12 | To Do | Yes | 0% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | Customization of Invoice and PI templates | Rishikesh Gogha | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-23 09:39 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Import -Invoice-D | Devaraju S J | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 18:26 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Meeting with Healthplix team to under the issue in zoho crm not able call | Monik Chettiyar | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-26 11:23 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Postman API Testing | Monik Chettiyar | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 10:29 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Image Prieview Implementation | Anusha V | High | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 21:34 | Done | No | 100% | IIFL Samasta: Shop Keeper Onboarding CR | Milestone One-Configuration, Development, Testing and Go-Live of Shopkeeper Onboarding CR | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | Import Credit Notes/S | Shiwani Kumari | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 18:06 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | Item Master Automation - Purchase Order and PO Automation | Ranjana Poojari | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-23 08:52 | Done | No | 100% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Import Bills/S | Shiwani Kumari | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 18:25 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Filtering Categories | Rishikesh Gogha | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-26 09:37 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | #5988 Zoho changes Requirement | Maninder Singh | High | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 17:24 | Done | No | 100% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Oracle Report Discussion | Vignesh R,Achyuth T M,Rishikesh Gogha | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-23 09:53 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602,708853094,745115006 | 25 | Late | 26 | 26 | 1 | days |  | Clear
7.4981e+17 | Add logic for Rundown Branches | Tanu Gupta | High | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-22 23:25 | In Progress | Yes | 10% | IIFL Samasta Zoho Creator Score Card Enhancement | Milestone One-Implementation of Score Card Enhancement | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 24 | Late | 25 | 25 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Ledger Summary modeling and Integration | Vaikuntam Chowdary | None | 2024-02-22 09:30 | 2024-02-23 19:00 | 2024-02-23 18:42 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 24 | Late | 26 | 26 | 2 | days
7.4981e+17 | Internal Meeting 1 | Sai Krishna,Aishwarya T | None | 2024-01-30 09:30 | 2024-02-02 19:00 | 2024-02-23 18:26 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 45 | Late | 49 | 49 | 4 | days |  | Clear | Sai Krishna
7.4981e+17 | Requirement Gathering Session 2 | Sai Krishna,Aishwarya T | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-02-23 16:17 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 34 | Late | 35 | 35 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Byron Support - febuary | unassigned | None | 2024-02-01 09:30 | 2024-02-29 19:00 | 2024-02-23 18:16 | In Progress | Yes | 0% | AMC - VAlign | Byron Medical Pty Ltd ¦ Zoho One ¦ 01-10-2023 ¦ 30-09-2024 | 7.4981e+17 | 7.4981e+17 |  | 789497933 | - | 18 | Late | 47 | 47 | 21 | days
7.4981e+17 | After Finalized Material Consumption, Add Bundle to Zoho Books Composite Item | Sachin Patil | None | 2024-02-22 09:30 | 2024-02-23 19:00 | 2024-02-22 19:12 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 24 | Late | 26 | 26 | 2 | days |  | Clear
7.4981e+17 | API documentation on Invoice, CN, DN and testing on POSTMAN | Anusuyadevi V | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-22 09:48 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Workflows & Automations ,Custom Functions | Anusha V | High | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-22 09:33 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Imported Invoices and payments in CRM | Ayush Singh | None | 2024-02-20 09:30 | 2024-02-21 19:00 | 2024-02-21 09:49 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 26 | Late | 28 | 28 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Add Composite Item to Zoho Creator BOM from Zoho book Composite Item | Sachin Patil | None | 2024-02-21 09:30 | 2024-02-22 19:00 | 2024-02-21 19:49 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 25 | Late | 27 | 27 | 2 | days |  | Clear
7.4981e+17 | Ozone Inc Invoice template/S | Shiwani Kumari | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 09:37 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Vendor Master Creation and Automations | Shavi Thakur | None | 2024-02-20 09:30 | 2024-02-20 12:00 | 2024-02-21 05:34 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 6 | Late | 7 | 7 | 2.5 | hrs
7.4981e+17 | Unit Testing for P&L | Tanu Gupta | High | 2024-02-20 09:30 | 2024-02-27 19:00 | 2024-02-21 09:39 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 9 | 9 | 6 | days
7.4981e+17 | Go Live (Full Launch) MBE's W.3 | unassigned | None | 2024-03-12 09:30 | 2024-03-15 19:00 | 2024-02-20 22:43 | To Do | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | - | 3 | Late | 7 | 7 | 4 | days
7.4981e+17 | Schedule Wave 1 Training Webinars | Kris Oswold | High | 2024-01-01 09:30 | 2024-02-16 19:00 | 2024-02-20 21:58 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 824545238 | 824545238 | 4 | Late | 51 | 51 | 35 | days
7.4981e+17 | Import Item Master-D | Devaraju S J | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 18:06 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Import-Invoice-D | Devaraju S J | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-22 09:34 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | Debit Note integration and Invoice, Credit Note Corrections | Vaikuntam Chowdary | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-21 09:36 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | P&I user dashboard page view | Swetha K | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 18:54 | Done | No | 100% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 16 | Late | 17 | 17 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Product Name change for BOM | Kalyanasundaram L | None | 2024-02-20 09:30 | 2024-02-21 19:00 | 2024-02-21 11:03 | Development Complete | Yes | 0% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 26 | Late | 28 | 28 | 2 | days |  | Clear
7.4981e+17 | New fields in Accounts Module | Nikita Srivastava | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-21 09:51 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | R &d to create the custom forecast module to manage the target vs achievement in crm | Nikita Srivastava | None |  |  | 2024-02-20 18:35 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Issue in invoice creation alert | Vignesh R | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-21 10:27 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | Client Visit on 20-Feb-2024 | Vignesh R | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 18:43 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Import of COA/S | Shiwani Kumari | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 18:32 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Zoho CRM to Zoho Books Data is not getting push | Monik Chettiyar | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-21 13:12 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | Data Migration for AERB module. | Supril Jain | None | 2023-10-03 09:30 | 2023-12-20 19:00 | 2024-02-21 10:55 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 78 | Late | 157 | 157 | 57 | days
7.4981e+17 | Generate QR Code to auto fetch invoice amount. | Basavaraj Patil | None | 2024-02-19 09:30 | 2024-02-22 19:00 | 2024-02-20 14:44 | In Progress | Yes | 10% | Atlas - Zoho Creator - P & I, And OMS | None | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 25 | Late | 29 | 29 | 4 | days |  | Clear | Waheeba Khan
7.4981e+17 | OBD Call | Nikita Srivastava | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 18:14 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | Zoho Access to be changed | Aishwarya T | None | 2024-02-19 09:30 | 2024-02-20 19:00 | 2024-02-19 19:06 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 27 | Late | 29 | 29 | 2 | days |  | Clear | Irshad Pasha
7.4981e+17 | Automated notification to vendor to raise bill based on payment date | Aishwarya T | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-19 12:05 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 25 | Late | 26 | 26 | 1 | days |  | Clear
7.4981e+17 | Validation Setup for purchase order | Sai Krishna,Aishwarya T | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 11:59 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 28 | Late | 29 | 29 | 1 | days |  | Clear
7.4981e+17 | Field level automation for purchase requisition | Sai Krishna,Aishwarya T | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-19 11:55 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 32 | Late | 33 | 33 | 1 | days |  | Clear
7.4981e+17 | UAT | Sai Krishna,Aishwarya T | None | 2024-03-18 09:30 | 2024-03-20 19:00 | 2024-02-19 11:39 | To Do | No | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | -2 | On Time | 1 | 1 | 3 | days |  | Clear
7.4981e+17 | Vendor onboarding form automations | Sai Krishna,Aishwarya T | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-19 10:49 | In Progress | Yes | 30% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 34 | Late | 35 | 35 | 1 | days |  | Clear
7.4981e+17 | Zoho People Exit Checklist Error | Monik Chettiyar | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 19:10 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Invoice data migrations | Mary Nisha | None | 2024-02-16 09:30 | 2024-02-19 19:00 | 2024-02-16 17:17 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 28 | Late | 32 | 32 | 2 | days |  | Clear
7.4981e+17 | Assign Deal Owner based on City for Deal Comes Chandirarh Facebook Campaign form and WordPrss form | Sachin Patil | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 18:49 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Client Site Visit 16/02/24 | M S Satya | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 18:28 | In Progress | Yes | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | PO Version Changes and Budget Version Changes | Ranjana Poojari | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 18:13 | Done | No | 100% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Zoho books Demo Internal | Waheeba Khan,Rishikesh Gogha,Tanu Gupta,Devaraju S J,Shiwani Kumari | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-19 09:36 | In Progress | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 671373250,745115006,790157522,844783967,844784545 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | Re: Punch Access ¦ Navi Mumbai location | Kiran Shrivastav | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 10:53 | Done | No | 100% | AMC - VAlign | Neelgund Developers LLP ¦ Zoho People, Recruit & Payroll ¦ 19-10-2023 ¦ 18-10-2024 | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | RE: PMS Process : Re:[## 5733 ##] Re: Annual Appraisal Process Automation | Kiran Shrivastav | None | 2024-02-19 09:30 | 2024-02-23 19:00 | 2024-02-19 22:07 | In Progress | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 24 | Late | 29 | 29 | 5 | days
7.4981e+17 | Sync Items to Zoho Creator from Zoho Books | Sachin Patil | None | 2024-02-19 09:30 | 2024-02-20 19:00 | 2024-02-19 19:02 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 27 | Late | 29 | 29 | 2 | days |  | Clear
7.4981e+17 | Automation/S | Shiwani Kumari | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 18:41 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Reassign the efforts based on the un-utilized cost | Vignesh R | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-16 20:06 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 25 | Late | 26 | 26 | 1 | days |  | Clear
7.4981e+17 | Applicant dashboard development | unassigned | None |  |  | 2024-02-16 19:47 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176551 | - |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Completed remaining day tasks | Shiwani Kumari | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 18:24 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | SO Creation for unbounded flow & Testing | Anusha V | None | 2024-02-14 09:30 | 2024-02-15 19:00 | 2024-02-19 09:59 | To Do | Yes | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 32 | Late | 34 | 34 | 2 | days
7.4981e+17 | Zoho CRM New Changes 01 | Rajesh Shindagi | None | 2024-02-16 09:30 | 2024-02-29 19:00 | 2024-02-18 14:11 | In Progress | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 18 | Late | 32 | 32 | 10 | days
7.4981e+17 | UI & UX Development | Tanu Gupta,Omprakash Kumar | High | 2024-03-04 09:30 | 2024-03-07 19:00 | 2024-02-16 19:04 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522,845321609 | 11 | Late | 15 | 15 | 4 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Multi-level Approver for Budget | Tanu Gupta | High | 2024-02-21 09:30 | 2024-02-22 19:00 | 2024-02-16 18:53 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 21 | Late | 23 | 23 | 2 | days |  | Clear
7.4981e+17 | Project Discovery : Multiple Team and Hashtags | Mohammed Yusha,Tanu Gupta | High | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 18:44 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 12 | Late | 13 | 13 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Vendor Masters and Invoice Master Integration to Zoho Books | Vaikuntam Chowdary | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-16 15:57 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | P&L Requirement Gathering | Tanu Gupta | High | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-20 09:33 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Banking Transactions Categorizing | Rishikesh Gogha | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 18:30 | To Do | Yes | 0% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 28 | Late | 29 | 29 | 1 | days |  | Clear
7.4981e+17 | Removing unwanted fields and making required changes based on demo feedback | Anusuyadevi V | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-20 09:32 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | Reports-D | Devaraju S J | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 18:32 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Sprint 1 demo and Internal Discussion | Anusuyadevi V | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-19 11:07 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Testing and Test UseCase document | Waheeba Khan | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-16 09:44 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Sales Order Item Enabled/Disabled FIelds and Redirect to Main form Report After adding Item | Sachin Patil | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 19:15 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | Recurring Journal/S | Shiwani Kumari | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 18:12 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | North 4 region Access | Nikita Srivastava | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 19:10 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Mandatory Fields | Nikita Srivastava | None | 2024-02-15 09:30 | 2024-02-16 19:00 | 2024-02-15 17:39 | In Progress | Yes | 0% | Accorian - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 31 | Late | 33 | 33 | 2 | days
7.4981e+17 | Email Follow-up | Kiran Shrivastav | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 10:00 | To Do | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | Zoho Books Custom Duty Integration | Shavi Thakur | None | 2024-02-15 09:30 | 2024-02-15 11:00 | 2024-02-16 07:54 | QA level 1 Completed | Yes | 10% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Three-Order Management System | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 32 | Late | 33 | 33 | 1.5 | hrs |  | Clear | Mohammed Yusha
7.4981e+17 | COA Sync(Books to Creator) | Shavi Thakur | None | 2024-02-14 09:30 | 2024-02-14 13:00 | 2024-02-14 21:05 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 0 | Late | 1 | 1 | 3.5 | hrs
7.4981e+17 | Item Master form | Aishwarya T | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 18:58 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 15 | Late | 16 | 16 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | RPA Meeting/S | Shiwani Kumari | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:29 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Quote Sync(Creator to Books) | Shavi Thakur | None | 2024-02-13 15:30 | 2024-02-13 19:00 | 2024-02-13 17:01 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 1 | Late | 2 | 2 | 3.5 | hrs
7.4981e+17 | Accounts, Contacts Master File Upload and Verification | Dharanidharan C | None | 2024-01-22 09:30 | 2024-02-15 19:00 | 2024-02-13 16:16 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 32 | Late | 57 | 57 | 19 | days |  | Clear
7.4981e+17 | Go members Data Upload and Verification | Dharanidharan C | None | 2024-01-22 09:30 | 2024-02-14 19:00 | 2024-02-13 16:16 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 33 | Late | 57 | 57 | 18 | days |  | Clear
7.4981e+17 | Excel creations for accounts | Mary Nisha | High | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 11:06 | QA level 1 Completed | Yes | 30% | VSINTERCONNECT CR for Estore | Milestone Two-Development, UAT & Go Live of Estore CR | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 34 | Late | 35 | 35 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Map members data based on new template | Pannaga H | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-13 18:24 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 795342015 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | Full launch External Users Data Migration | Kalyanasundaram L | None | 2024-02-12 09:30 | 2024-02-16 19:00 | 2024-02-13 10:08 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 31 | Late | 36 | 36 | 5 | days |  | Clear
7.4981e+17 | Bulk adjustment-D | Devaraju S J | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 18:18 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Manual journals-D | Devaraju S J | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 18:13 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | UAT Doubts Call with Deepak | Tanu Gupta | High | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 20:42 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | UI changes for View Resource Allocation | Tanu Gupta | High | 2024-02-13 09:30 | 2024-02-15 19:00 | 2024-02-13 19:38 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 21 | Late | 24 | 24 | 3 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Sync Failures documentation | Anusuyadevi V | None | 2024-02-12 09:30 | 2024-02-13 19:00 | 2024-02-13 09:30 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Five-Payment for April 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 3 | 3 | 2 | days
7.4981e+17 | Automated Accounting Transactions in Zoho Books and Inventory/S | Shiwani Kumari | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 18:05 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Client Visit on 13-Feb-2024 | Vignesh R | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 17:41 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Zoho CRM - Post Go Live Changes | Mohammed Yusha,Tanu Gupta | None | 2024-02-14 09:30 | 2024-02-20 19:00 | 2024-02-14 17:47 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 1 | Late | 8 | 8 | 5 | days
7.4981e+17 | Stand up-D | Devaraju S J | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:29 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Client call for walkthrough of Agent Performance Report | Tanu Gupta | High | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-13 08:37 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Four-Implementation of Zoho CRM Application | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 35 | Late | 36 | 36 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Client Meeting | Vaikuntam Chowdary | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-15 09:32 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 33 | Late | 34 | 34 | 1 | days |  | Clear
7.4981e+17 | Realized gain or Loss-D | Devaraju S J | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 18:00 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Integration Dependencies within different API's | Vaikuntam Chowdary | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-14 09:32 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Two-Payment for January2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Set up the Daily Automation for MBE Search Upload from AdaptOne | Prableen Kaur | None | 2024-03-25 09:30 | 2024-04-05 19:00 | 2024-02-12 20:58 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 792886644 | -18 | On Time | -6 | -6 | 10 | days
7.4981e+17 | Project Management Meeting & Scrum Meeting | Mohammed Yusha,Vignesh R,Tanu Gupta | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 18:40 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,704175602,790157522 | 8 | Late | 9 | 9 | 1 | days |  | Clear
7.4981e+17 | Internal Meeting with Waheeba | Mohammed Yusha | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 19:52 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Four-Financial Accounting Management System | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | Account Receivable Management-d | Devaraju S J | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:31 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Internal Meeting | Vaikuntam Chowdary | None | 2024-02-12 09:30 | 2024-02-16 19:00 | 2024-02-12 18:29 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 31 | Late | 36 | 36 | 5 | days
7.4981e+17 | Configuration of Customer Module and Fields | unassigned | None |  |  | 2024-02-12 16:26 | To Do | No | 0% | Dr Reddy’s - Zoho CRM, Desk, SalesIQ | Milestone One-Advance payment for Zoho project initiation [Zoho Desk & Zoho SalesIQ, Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Configuration of Orders Module and Fields | Rajesh Shindagi | None | 2024-02-12 09:30 | 2024-02-14 19:00 | 2024-02-12 16:26 | Done | No | 100% | Dr Reddy’s - Zoho CRM, Desk, SalesIQ | Milestone One-Advance payment for Zoho project initiation [Zoho Desk & Zoho SalesIQ, Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 26 | Late | 29 | 29 | 3 | days
7.4981e+17 | Account receivable management - A | Akshay Parameshwara Hegde | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:37 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784261 | 844784261 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Account receivable management/S | Shiwani Kumari | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:27 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 35 | Late | 36 | 36 | 1 | days
7.4981e+17 | Zoho RPA Induction | Prableen Kaur | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-15 10:51 | Done | No | 100% | RPA Master Plan | None | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 2 | Late | 3 | 3 | 1 | days |  | Clear
7.4981e+17 | Hide, Show, Enabled and Disabled Delivery Challan Fields | Sachin Patil | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:05 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Employee Adding error in people | Kiran Shrivastav | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-02-12 17:28 | Done | No | 100% | AMC - VAlign | Longitude Exports Pvt Ltd - Zoho CRM, Zoho People & Zoho Payroll ¦ 09-08-2023 ¦ 08-02-2024 | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | Acceptable range for sales invoice should be PO +5% in create purchase invoice | Maninder Singh | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 15:19 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 28 | Late | 29 | 29 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Support request on Exit checklist | Kiran Shrivastav | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 09:26 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | RMSDC Data Migration | Supreeth R Kalluraya | None | 2024-02-12 09:30 | 2024-02-15 19:00 | 2024-02-12 21:35 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 788577227 | 788577227 | 22 | Late | 26 | 26 | 4 | days |  | Clear
7.4981e+17 | Finalization of Update Requested POV BE | Supreeth R Kalluraya | None | 2024-02-09 09:30 | 2024-02-13 19:00 | 2024-02-12 13:47 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | Milestone Four : Development completion and Go Live of CS Certification Portal. | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 788577227 | 788577227 | 34 | Late | 39 | 39 | 3 | days |  | Clear
7.4981e+17 | Sales Order Enabled/Disabled FIelds and Redirect to Report | Sachin Patil | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 19:24 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | In Accepted Qty do not allow to add Decimal value, If Number of Boxes is Not Empty | Sachin Patil | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 19:14 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | #5941 Add 'Inbound Call' to Round Robin Method | Maninder Singh | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 17:26 | Done | No | 100% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-01 09:30 | 2024-02-15 19:00 | 2024-02-14 10:56 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 19 | 19 | 11 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-01 09:30 | 2024-02-15 19:00 | 2024-02-14 10:56 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 19 | 19 | 11 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-01 09:30 | 2024-02-15 19:00 | 2024-02-14 10:56 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 19 | 19 | 11 | days
7.4981e+17 | Change format of Billing invoice and add additional fields | Maninder Singh | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 09:28 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 26 | Late | 27 | 27 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Validate function searching | Mary Nisha | High | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 12:44 | QA level 1 Completed | Yes | 30% | VSINTERCONNECT CR for Estore | Milestone Two-Development, UAT & Go Live of Estore CR | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 34 | Late | 35 | 35 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | ABMPL-Zoho Creator and Zoho Desk Flow | Vaikuntam Chowdary | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-12 12:24 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 45 | Late | 46 | 46 | 1 | days |  | Clear
7.4981e+17 | Project and reporting tag-D | Devaraju S J | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 18:46 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Solutioning on API failures | Anusuyadevi V | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-08 18:51 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Five-Payment for April 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | 3294066 Saandeepani Academy For Excellence-ASSET final /3rd Installment request | Swetha K | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 09:32 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Application Flowchart | Vignesh R | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 18:44 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 14 | Late | 15 | 15 | 1 | days |  | Clear
7.4981e+17 | Item Subgroup Creation | Mohan Kumar | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 12:15 | To Do | Yes | 0% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 38 | Late | 39 | 39 | 1 | days
7.4981e+17 | Request for creating HR Admin role in Zoho People | Kiran Shrivastav | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-09 16:31 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | Probation Confirmation workflow not getting triggered | Kiran Shrivastav | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 09:30 | Done | No | 100% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | Zoho CRM Weekly Meetiing | Monik Chettiyar | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-12 01:23 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Create employee ledger statements feature in zoho creator | Maninder Singh | High | 2024-02-09 09:30 | 2024-02-12 19:00 | 2024-02-09 15:52 | Done | No | 100% | AMC - VAlign | EI - Zoho One Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 14 | Late | 18 | 18 | 2 | days
7.4981e+17 | Link SO to PO in create PO through lookup field | Maninder Singh | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-09 09:26 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 28 | Late | 29 | 29 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Item And Inventory/S | Shiwani Kumari | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 18:34 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Follow Up Email Template | Nikita Srivastava | None | 2024-02-12 09:30 | 2024-02-15 19:00 | 2024-02-12 10:18 | In Progress | Yes | 0% | Accorian - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 774653652 | 32 | Late | 36 | 36 | 4 | days
7.4981e+17 | Enquiry Management Blueprint | Nikita Srivastava | None | 2024-02-12 09:30 | 2024-02-16 19:00 | 2024-02-12 10:05 | In Progress | Yes | 0% | Accorian - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 774653652 | 31 | Late | 36 | 36 | 5 | days
7.4981e+17 | Assign Owner to Deal for 'RMA_Veneer Door 06-02-2024' Facebook Campaign Form | Sachin Patil | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 19:10 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Escalation work with monik | Kiran Shrivastav,Monik Chettiyar | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 12:45 | In Progress | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987,792262192 | 39 | Late | 40 | 40 | 1 | days
7.4981e+17 | Validation On Purchase Order - Expected Delivery Date for Service PO | Sachin Patil | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 18:51 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Farm India ¦ Change Requests Discussion | Maninder Singh | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 15:48 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | Integration Check & Client Meeting | Mohammed Yusha | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 19:35 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Five-Advance Reports & Analytics | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | Project Management Review | Mohammed Yusha | None | 2024-02-08 09:30 | 2024-02-09 19:00 | 2024-02-08 19:28 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | -1 | On Time | 1 | 1 | 2 | days |  | Clear
7.4981e+17 | Advance payment trough Bank and custom approvals | Rishikesh Gogha | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-12 10:02 | To Do | Yes | 0% | Airowire - Zoho Expense | None | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 38 | Late | 39 | 39 | 1 | days
7.4981e+17 | Migration of Wave 1 Council Data to Zoho | Prableen Kaur,Kalyanasundaram L | None | 2024-03-18 09:30 | 2024-03-19 19:00 | 2024-02-09 22:16 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 792886644,819676542 | -1 | On Time | 1 | 1 | 2 | days
7.4981e+17 | SMS triggers after data Upload Schedular Functionality | Anusha V | High | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-09 19:38 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | #5913 Lead Status | Tanu Gupta | High | 2024-02-08 09:30 | 2024-02-09 19:00 | 2024-02-08 23:36 | Done | No | 100% | AMC - VAlign | HAPPY RELIABLE SURGERIES PRIVATE LIMITED - Zoho CRM and Zoho Form ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Meeting-D | Devaraju S J | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 18:38 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Support request : Employee master data upload | Kiran Shrivastav | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-08 10:53 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 18 | Late | 19 | 19 | 1 | days
7.4981e+17 | Identify User Roles | Leahanne Thomas | None | 2024-02-07 09:30 | 2024-02-09 19:00 | 2024-02-07 21:54 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 811824969 | 30 | Late | 33 | 33 | 3 | days
7.4981e+17 | Button Creation in WH_PO Report & Testing | Anusha V | High | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-07 19:44 | Done | No | 100% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Meeting with Zoho team for Linking between Custom Module and Calls Module | Tanu Gupta | High | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:42 | Done | No | 100% | (BoldFit) Sasvat_Zoho One | Milestone Four-Implementation of Zoho CRM Application | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | CheckMate Implementation | Christ Bellarmine,Dharanidharan C | None | 2024-02-06 09:30 | 2024-02-29 19:00 | 2024-02-07 11:09 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 81581486,701371504 | 11 | Late | 35 | 35 | 18 | days
7.4981e+17 | TSD | Tanu Gupta | High | 2024-02-06 09:30 | 2024-02-09 19:00 | 2024-02-06 19:07 | Development Complete | Yes | 30% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 38 | Late | 42 | 42 | 4 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Approval: Apple Global School-2472480 | Swetha K | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 13:08 | To Do | Yes | 0% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 40 | Late | 41 | 41 | 1 | days
7.4981e+17 | Chart of Accounts, Tax Master creation and update creator ID in Document | Anusuyadevi V | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-07 10:44 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Zoho CRM module and field requirement | Dharanidharan C,Rajesh Shindagi | None | 2024-02-02 09:30 | 2024-02-09 19:00 | 2024-02-06 15:42 | In Progress | Yes | 0% | Dr Reddy’s - Zoho CRM, Desk, SalesIQ | None | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 701371504,758002363 | 38 | Late | 46 | 46 | 6 | days
7.4981e+17 | Charts of Accounts | Shiwani Kumari | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 18:51 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Client meetings | Prableen Kaur | None | 2024-02-05 09:30 | 2024-02-08 19:00 | 2024-02-06 17:52 | In Progress | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 39 | Late | 43 | 43 | 4 | days
7.4981e+17 | Company Name - Priority support needed | Kiran Shrivastav | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 12:06 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | Vist Out station planner | Nikita Srivastava | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 19:31 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Channel Partner report | Nikita Srivastava | None |  |  | 2024-02-06 18:17 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Daily Data Migration for Catalyst Version | Kalyanasundaram L | None | 2024-02-05 09:30 | 2024-02-15 19:00 | 2024-02-06 08:24 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 32 | Late | 43 | 43 | 9 | days |  | Clear
7.4981e+17 | Automation to assign respective Roles and Profiles to Users | Dharanidharan C | None | 2024-02-06 09:30 | 2024-02-20 19:00 | 2024-02-05 17:07 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 2 | Late | 17 | 17 | 11 | days
7.4981e+17 | Basic Navigation | Devaraju S J | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:22 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | COA-D | Devaraju S J | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 18:44 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Requirement gathering for MBE Users list as per RMSDC | Prableen Kaur | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 18:22 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Email Notification Changes | Vignesh R | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 22:22 | In Progress | Yes | 10% | Vestian Global_Zoho Creator | Milestone Two-Zoho Creator – Procurement &Billing Management System.3. Completion of Config | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 41 | Late | 42 | 42 | 1 | days |  | Clear
7.4981e+17 | Mark Lead as Unqualified | unassigned | None |  |  | 2024-02-06 19:55 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 701371504 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Creating a new Task for a Lead | unassigned | None |  |  | 2024-02-06 19:54 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 701371504 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Mobile number and Zip code Validation during Lead Creation | unassigned | None |  |  | 2024-02-06 19:54 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 701371504 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | TCS Name is not updated for some invoices. TCS Name should be updated from SO | Sachin Patil | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 18:42 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Contacts and Customers - A | Akshay Parameshwara Hegde | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 18:36 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784261 | 844784261 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Zoho creator syn error- Rahul Prasad | Kiran Shrivastav | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 11:34 | Done | No | 100% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | ABMPL Testing | Shavi Thakur | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:24 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 41 | Late | 42 | 42 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | TSD and flowchart for Vendor Registration and Vendor Portal | Sai Krishna,Aishwarya T | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 10:33 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 30 | Late | 31 | 31 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Testing feedback Correction /UAT | Selva Bharathi | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-05 18:20 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573 | 32 | Late | 33 | 33 | 1 | days |  | Clear
7.4981e+17 | Data Migration | Selva Bharathi | None | 2024-02-08 19:00 | 2024-02-08 19:00 | 2024-02-05 18:17 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573 | 39 | Late | 40 | 40 | 0 | days |  | Clear
7.4981e+17 | Create OMS Flow Chart | Vignesh R | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 16:15 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 40 | Late | 41 | 41 | 1 | days
7.4981e+17 | Checking issue in invoice TCS push to zoho books | Vignesh R | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 10:23 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 40 | Late | 41 | 41 | 1 | days
7.4981e+17 | Basic Navigation | Shiwani Kumari | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:27 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | ZOho People Exit Checklist Meeting | Monik Chettiyar | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-06 01:53 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Airowire Meeting for zoho books and CRM Corrections | Monik Chettiyar | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-06 01:31 | Done | No | 100% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | Changes in SLA Email Notification Templates | Sachin Patil | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 19:19 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Client Engagement : M.O.M and R&D on Zoho Creator Integration application | Sai Krishna,Aishwarya T | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 18:24 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 28 | Late | 29 | 29 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Vendor Bill without PO - PO amount more than 50000 is also got submitted | Swetha K | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 16:30 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 42 | Late | 43 | 43 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Report Customization for RHR | Anusha V | High | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-06 09:32 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | Client call for review of crm, desk, and creator | Tanu Gupta | High | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 20:49 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 42 | Late | 43 | 43 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Zoho One User Addition | Irshad Pasha | None | 2024-02-01 09:30 | 2024-02-05 19:00 | 2024-02-05 12:09 | Done | No | 100% | Ozone Entertainment - Zoho ONE | None | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 701341459 | 0 | Late | 5 | 5 | 3 | days
7.4981e+17 | Create Reports for Portal Users | Dharanidharan C | None | 2024-02-06 09:30 | 2024-02-20 19:00 | 2024-02-02 17:19 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 2 | Late | 17 | 17 | 11 | days
7.4981e+17 | Need to check the issue of the user not getting access to edit the SOW, On SOW module need to apply validation that if the related deal status is not converted then on load give an error for not creating the SOW | Aishwarya T | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 15:43 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 45 | Late | 46 | 46 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | The Due Date will be extended by 2 business days when the ticket is in progress | Sachin Patil | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 18:56 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Create GRN sales summary report in analytics and embed into zoho creator | Maninder Singh | None | 2024-02-02 09:30 | 2024-02-12 19:00 | 2024-02-02 13:43 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 28 | Late | 39 | 39 | 7 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-25 09:30 | 2024-02-02 19:00 | 2024-02-02 10:48 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 17 | Late | 26 | 26 | 7 | days
7.4981e+17 | Inventory / Non-Inventory tracking item mismatch in creator and books | Sachin Patil | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 10:40 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 45 | Late | 46 | 46 | 1 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-02-02 10:36 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | until the previously leads marked as Dead, Junk, not qualified the leads status should be re-enquiry. When leads status is Dead, Junk, not qualified and user filled a form then it should come as a New Lead. | Maninder Singh | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 09:25 | Done | No | 100% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | External Meeting with Stellar Team for Desk Point Discussion (2 Feb 2024) | Sachin Patil | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 19:36 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Meeting with Servetel and Boldfit for Custom Module Linking | Tanu Gupta | High | 2024-02-02 09:30 | 2024-02-09 19:00 | 2024-02-04 22:05 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Four-Implementation of Zoho CRM Application | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 38 | Late | 46 | 46 | 6 | days |  | Clear | Supril Jain
7.4981e+17 | KARAM-Zoho Inventory discussion | Vaikuntam Chowdary | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-02 18:35 | In Progress | Yes | 10% | Karam Safety_Zoho ONE | None | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 46 | Late | 47 | 47 | 1 | days |  | Clear
7.4981e+17 | Call with client for live testing and minor issue fix in scorecard app | Tanu Gupta | High | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 19:06 | Done | No | 100% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Team Inspire : Standup Call Feb 2024 | Supril Jain,Nikita Srivastava,Maninder Singh,Tanu Gupta,Kiran Shrivastav,Monik Chettiyar | Medium | 2024-02-01 09:30 | 2024-02-29 19:00 | 2024-02-04 22:16 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 756836914,774653652,782721491,790157522,791842987,792262192 | 14 | Late | 43 | 43 | 21 | days
7.4981e+17 | Demo Calls | unassigned | High | 2024-01-29 09:30 | 2024-01-31 19:00 | 2024-02-01 21:15 | In Progress | Yes | 0% | Prodevans - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 795545761 | - | 47 | Late | 50 | 50 | 3 | days
7.4981e+17 | SBU wise Bill Report - ZB | Achyuth T M | High | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 18:43 | In Progress | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 46 | Late | 47 | 47 | 1 | days
7.4981e+17 | POs not created from SO | M S Satya | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 12:33 | Done | No | 100% | AMC - VAlign | Byron Medical Pty Ltd ¦ Zoho One ¦ 01-10-2023 ¦ 30-09-2024 | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | EI Permision User manuall | Mary Nisha | None | 2024-02-02 09:30 | 2024-02-06 19:00 | 2024-02-02 16:08 | QA level 1 Completed | Yes | 30% | Educational Initiatives - P&I CR | None | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 41 | Late | 46 | 46 | 3 | days |  | Clear | Dharanidharan C
7.4981e+17 | Issue in Invoice creation | Vignesh R | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 20:28 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 46 | Late | 47 | 47 | 1 | days
7.4981e+17 | ChatGPT keyword generation with NLP and ChatGPT | Prableen Kaur,Pannaga H | None | 2024-02-01 09:30 | 2024-02-05 19:00 | 2024-02-02 18:30 | In Progress | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644,795342015 | 42 | Late | 47 | 47 | 3 | days
7.4981e+17 | Analyse data and prepare exception report for the council data | Pannaga H | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-05 12:26 | To Do | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 795342015 | 41 | Late | 42 | 42 | 1 | days
7.4981e+17 | Import Customer Master Data - Client Visit | Basavaraj Patil | None | 2024-01-29 09:30 | 2024-02-06 19:00 | 2024-02-02 16:53 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 41 | Late | 50 | 50 | 7 | days |  | Clear | Waheeba Khan
7.4981e+17 | Import live Inventory Data and also generate QR code and QR code Number. | Basavaraj Patil | None | 2024-01-22 09:30 | 2024-02-02 19:00 | 2024-02-02 16:43 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 45 | Late | 57 | 57 | 10 | days |  | Clear | Waheeba Khan
7.4981e+17 | Invoice Module Creation | Anusuyadevi V | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 21:22 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Zoho Integration with Zoho Books & Custom Functionality & Testing | Anusha V | High | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 20:26 | Done | No | 100% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | All Vendor Bill Payment Details | Swetha K | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 16:37 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 46 | Late | 47 | 47 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Standard Edition Features Check and CRM Setup | unassigned | High | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-02-01 11:22 | Done | No | 100% | Prodevans - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 795545761 | - | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | ABMPL-Zoho Creator other redemption categories flow discussion | Vaikuntam Chowdary | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-02-01 09:19 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 47 | Late | 48 | 48 | 1 | days |  | Clear
7.4981e+17 | Vendor Finance approval - PAN Card validation | Swetha K | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 09:42 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 46 | Late | 47 | 47 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | hierarchy Mapping Issue and approval process | Nikita Srivastava | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 18:49 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Vendor Requistion report | Swetha K | None | 2024-01-31 09:30 | 2024-02-01 19:00 | 2024-01-31 18:44 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 46 | Late | 48 | 48 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Create GRN Purchase summary report in analytics and embed into zoho creator | Maninder Singh | Medium | 2024-02-01 09:30 | 2024-02-12 19:00 | 2024-02-01 14:28 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 28 | Late | 40 | 40 | 8 | days |  | Clear
7.4981e+17 | PMD CCO - Dynamic table will show in the same table if its same service Type and setting of the rate | Ayush Singh | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-02-01 10:59 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 47 | Late | 48 | 48 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | ICAC&PMD ICAC Template Updations | Mary Nisha | High | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 17:40 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 47 | Late | 48 | 48 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | January payrun matching | Kiran Shrivastav | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 11:28 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 22 | Late | 23 | 23 | 1 | days
7.4981e+17 | Chain Container | Ranjana Poojari | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 10:39 | Done | No | 100% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 2 | Late | 3 | 3 | 1 | days |  | Clear
7.4981e+17 | Zoho People Custom Function For Field update | Monik Chettiyar | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 11:53 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 48 | Late | 49 | 49 | 1 | days
7.4981e+17 | All Templates Updation and Creation | M S Satya | None | 2024-01-29 09:30 | 2024-01-30 19:00 | 2024-01-29 18:42 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 48 | Late | 50 | 50 | 2 | days |  | Clear
7.4981e+17 | Accounts And Contacts Linkage update based on feedback Mail | Dharanidharan C | None | 2024-01-29 09:30 | 2024-01-30 19:00 | 2024-01-29 17:37 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 14 | Late | 16 | 16 | 2 | days |  | Clear
7.4981e+17 | Code Merging and Resolving Conflicts | Nawaz Sharief | None | 2024-01-25 09:30 | 2024-01-31 19:00 | 2024-01-25 19:32 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 841115370 | 36 | Late | 43 | 43 | 5 | days |  | Clear
7.4981e+17 | Under Vendor bill "Verification Report" on validate error | Swetha K | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 09:35 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 47 | Late | 48 | 48 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Client meeting with zoho team for payment and manual journals | Waheeba Khan,Tanu Gupta | High | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 20:16 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 671373250,790157522 | 48 | Late | 49 | 49 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Internal Meeting & Email Response | Mohammed Yusha,Vignesh R | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 18:59 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,704175602 | 8 | Late | 9 | 9 | 1 | days |  | Not Clear
7.4981e+17 | Integration Issue & Support Meeting | Mohammed Yusha | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 19:46 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Uploading file to Creator API Development(Python) | Pannaga H | None |  |  | 2024-01-30 09:29 | In Progress | No | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 795342015 | 795342015 |  | On Time |  | 0 | 0 | days
7.4981e+17 | In quotes update project terrritory | Aishwarya T | None | 2024-01-29 09:30 | 2024-01-30 19:00 | 2024-01-29 12:17 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 9 | Late | 11 | 11 | 2 | days
7.4981e+17 | Data pertaining to the change log - OMS | Swetha K | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 19:08 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Ganttchart | Waheeba Khan | None | 2024-01-25 09:30 | 2024-01-29 19:00 | 2024-01-30 12:05 | Done | No | 100% | SPERA - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 1 | Late | 6 | 6 | 3 | days
7.4981e+17 | Custom workflow to notify contact without Survey link | Tanu Gupta | High | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 21:37 | Done | No | 100% | AMC - VAlign | Synup Digital Pvt Ltd - Zoho CRM & Desk ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Bulk Send Donation Receipt to Confirmed Donors | Sai Krishna,Tanu Gupta | High | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 21:27 | In Progress | Yes | 10% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 790157522 | 753339779,790157522 | 49 | Late | 50 | 50 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Oauth Generation | Anusuyadevi V | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 19:12 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Zoho Projects Post Go-Live changes | Rajesh Shindagi | None | 2024-01-24 09:30 | 2024-01-30 19:00 | 2024-01-25 15:49 | In Progress | Yes | 10% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 48 | Late | 55 | 55 | 5 | days |  | Clear
7.4981e+17 | Client Meeting | Supril Jain | None | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-31 09:24 | In Progress | Yes | 0% | AMC - VAlign | Global Learning service LLP - Zoho CRM ¦ 05-05-2023 ¦ 04-05-2024 | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 47 | Late | 49 | 49 | 2 | days
7.4981e+17 | ICAC&CCO Reject reason automations | Mary Nisha | None | 2024-01-25 09:30 | 2024-01-26 19:00 | 2024-01-25 15:47 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 52 | Late | 54 | 54 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Employee ID issue | Kiran Shrivastav | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 18:07 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 29 | Late | 30 | 30 | 1 | days
7.4981e+17 | Stock Value mismatch with the actual inventory value | Vignesh R | None | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-30 22:00 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 47 | Late | 49 | 49 | 2 | days
7.4981e+17 | Create P& I Flow Chart | Vignesh R | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 13:41 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 48 | Late | 49 | 49 | 1 | days
7.4981e+17 | Zoho CRM - FIeld level details document | Supril Jain | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-30 09:08 | Done | No | 100% | Accorian - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | ChatGPT Keyword extraction prompt change | Basavaraj Patil,Prableen Kaur | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 18:26 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 781564441,792886644 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Support Call people and payroll | Monik Chettiyar | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-28 17:48 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Tickets are not getting created for Inbound Missed Calls On Desk | Monik Chettiyar | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-28 17:40 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | Support Meeting For Zoho People & Payroll. | Monik Chettiyar | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-28 17:28 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Data Upload | Ranjana Poojari | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 18:36 | Done | No | 100% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 6 | Late | 7 | 7 | 1 | days |  | Clear
7.4981e+17 | Updates discussed in UAT training call | Kiran Shrivastav | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 12:14 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 48 | Late | 49 | 49 | 1 | days
7.4981e+17 | January Payroll TDS issue | Kiran Shrivastav | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 17:00 | To Do | Yes | 0% | AMC - VAlign | Neelgund Project Zoho HRMS Implementation | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 49 | Late | 50 | 50 | 1 | days
7.4981e+17 | Client Visit on 25-Jan-2023 | Vignesh R | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 18:04 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 53 | Late | 54 | 54 | 1 | days
7.4981e+17 | Add approval process for discounted invoices (Store manager can edit or approve the invoice) | Sachin Patil | None | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-30 19:22 | Development Complete | Yes | 10% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 47 | Late | 49 | 49 | 2 | days |  | Clear | Waheeba Khan
7.4981e+17 | BOD Module Creation and data upload | Dharanidharan C | None |  |  | 2024-01-25 23:41 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Email Notification Rules & Templates | unassigned | High | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-31 09:21 | Done | No | 100% | Prodevans - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 795545761 | - | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Re: Padma Seshadri/Lakshmi School/Lakshmi MAtriculation/AM Jain - 2nd invoice School Code-3700372 | Swetha K | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 12:55 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Update SO status as Fulfilled when a order is fulfilled | Anusuyadevi V | None | 2024-01-26 09:30 | 2024-01-26 19:00 | 2024-01-26 21:30 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Zoho Team call - # 9552660 Error during Shopify and Zoho Inventory Item Sync | Anusuyadevi V,Tanu Gupta | High | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-26 21:13 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 786479121,790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | P&I - hide SBU email in subform onload which is hidden | Swetha K | None | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-30 17:24 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 47 | Late | 49 | 49 | 2 | days
7.4981e+17 | Reversal of Invoice | unassigned | None | 2024-01-31 09:30 | 2024-02-05 19:00 | 2024-01-30 12:42 | To Do | Yes | 0% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | - | 42 | Late | 48 | 48 | 4 | days
7.4981e+17 | Reversal of Invoice -school code - 3799725 ASSET (INV/3125) & Cares (INV/3272) | Swetha K | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 09:34 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | PO / SO numbers should be contineous regardless of comodities.in all PO/SO | Maninder Singh | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-24 11:35 | In Progress | Yes | 0% | AMC - VAlign | FARM INDIA IMPEX ¦ Books, Creator, People, Payroll & Analytics ¦ 8-12-23 to 7-12-24 | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 53 | Late | 54 | 54 | 1 | days
7.4981e+17 | Checking on Blank Page showing when we push to books | Vignesh R | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-24 10:39 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | Zoho Order Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 54 | Late | 55 | 55 | 1 | days |  | Clear
7.4981e+17 | Create Purchase Order for Service Inventory Items (For Samsung Warehouse) | Sachin Patil | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 19:16 | Development Complete | Yes | 0% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 55 | Late | 56 | 56 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Add 'Reject' button on Return Item to Warehouse Report for Rejecting the Return Item from Store Manager | Sachin Patil | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 09:51 | Development Complete | Yes | 0% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 55 | Late | 56 | 56 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | External Lead App Historical data Discussion | Anusha V | None | 2024-01-23 09:30 | 2024-02-02 19:00 | 2024-01-24 09:46 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 34 | Late | 45 | 45 | 9 | days
7.4981e+17 | Client Call for Demo of solutions in zoho creator | Tanu Gupta | High | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-23 09:37 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 56 | Late | 57 | 57 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Flow Testing | Anusuyadevi V | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-23 09:17 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | ZOho CRM Custom Validation | Monik Chettiyar | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-24 10:52 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 62 | Late | 63 | 63 | 1 | days
7.4981e+17 | Creating custom kanban dashboard | Nikita Srivastava | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 17:56 | Done | No | 100% | AMC - VAlign | Better Place Support Activity | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Bug Resolve | Nawaz Sharief | None | 2024-01-24 09:30 | 2024-01-31 19:00 | 2024-01-24 18:45 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 841115370 | 36 | Late | 44 | 44 | 6 | days |  | Clear
7.4981e+17 | Develop POC for functionality testing of MBE Search | Prableen Kaur | None | 2024-01-16 09:30 | 2024-01-18 19:00 | 2024-01-24 13:05 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 6 | Late | 9 | 9 | 3 | days
7.4981e+17 | On the clone page, we need to give the validation for quote selected for project value addup application engineer need to see all the user to assign quote owner update the view of my records for all the modules as fav so that the user will see their records only | Aishwarya T | None | 2024-01-24 09:30 | 2024-01-25 19:00 | 2024-01-24 10:45 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Notification issue | Nikita Srivastava | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-24 19:27 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | NewBranch & Admin module Issues | Anusha V | None | 2024-01-24 09:30 | 2024-01-25 19:00 | 2024-01-25 09:47 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 42 | Late | 44 | 44 | 2 | days
7.4981e+17 | Mail Trigger to Lead Automation and Testing | Anusha V | High | 2024-01-12 09:30 | 2024-01-23 19:00 | 2024-01-24 11:17 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 55 | Late | 67 | 67 | 8 | days
7.4981e+17 | Prodevans CRM Requirement Call | Anusha V | High | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-22 19:09 | In Progress | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 56 | Late | 57 | 57 | 1 | days
7.4981e+17 | Develop script to upload documents from local storage to Zoho using APIs | Prableen Kaur,Pannaga H | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-01-24 11:21 | In Progress | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644,795342015 | 38 | Late | 39 | 39 | 1 | days
7.4981e+17 | Stand-up/Internal discussions | Prableen Kaur,Pannaga H | None | 2024-01-02 09:30 | 2024-01-30 19:00 | 2024-01-24 10:31 | In Progress | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644,795342015 | 48 | Late | 77 | 77 | 21 | days
7.4981e+17 | Pop up Form | Nawaz Sharief | None |  |  | 2024-01-22 19:04 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 841115370 | 841115370 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Email to Zoho Support for Payment Gateway issues with other payment modes | Dharanidharan C | None |  |  | 2024-01-22 17:35 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 701371504 | 701371504 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Renewal Deals - Invoice Creation and automations | Dharanidharan C,M S Satya | None | 2024-01-22 09:30 | 2024-01-29 19:00 | 2024-01-22 17:32 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504,789497933 | 15 | Late | 23 | 23 | 6 | days |  | Clear
7.4981e+17 | RE: January payroll issue | Kiran Shrivastav | None | 2024-01-22 09:30 | 2024-01-23 19:00 | 2024-01-22 21:48 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 10 | Late | 12 | 12 | 2 | days
7.4981e+17 | Notification Automation | Mallesh M S | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-22 13:32 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 19 | Late | 20 | 20 | 1 | days |  | Clear
7.4981e+17 | Application form Integration - Deal | Mallesh M S | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-22 13:32 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 21 | Late | 22 | 22 | 1 | days |  | Clear
7.4981e+17 | Leads to Contacts to Deals Code | Monik Chettiyar | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-22 23:06 | Development Complete | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 66 | Late | 67 | 67 | 1 | days |  | Clear
7.4981e+17 | Subform creation and update Select days values in CRM and Creator | Mary Nisha | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-22 15:00 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 56 | Late | 57 | 57 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Client Call For Zoho Invoicing & Internal Call | Mohammed Yusha,Tanu Gupta | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 18:49 | Done | No | 100% | AMC - VAlign | Infifresh 01-01-2024 to 31-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Not Able to Raise Invoice for ASSET - Error | Swetha K | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 16:07 | Hold | Yes | 0% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 55 | Late | 56 | 56 | 1 | days
7.4981e+17 | Sales Order Edit Widget | Vishnu D A | None | 2024-01-19 09:30 | 2024-01-22 15:00 | 2024-01-23 00:57 | In Progress | Yes | 10% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 838472289 | 838472289 | 56 | Late | 60 | 60 | 15 | hrs |  | Clear | Siddharth Sharma
7.4981e+17 | Support request on RE: Instant Sync error | Kiran Shrivastav | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 19:28 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Changes in Dashboard | Vignesh R | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 10:18 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 59 | Late | 60 | 60 | 1 | days
7.4981e+17 | Import Service Items and Item Price List to Zoho Creator and push to books | Sachin Patil | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 10:01 | Terminated/Cancelled | No | 100% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 11 | Late | 12 | 12 | 1 | days |  | Clear
7.4981e+17 | Holidays | Kiran Shrivastav | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 10:44 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | Map existing code with regional data | Pannaga H | None | 2024-01-15 09:30 | 2024-01-18 19:00 | 2024-01-18 18:30 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 795342015 | 5 | Late | 9 | 9 | 4 | days
7.4981e+17 | Run Daily Activation Report | Albert Diaz | None | 2024-02-20 09:30 | 2024-02-21 19:00 | 2024-01-20 05:50 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 809116687 | 16 | Late | 18 | 18 | 2 | days
7.4981e+17 | Create Email Content for Corp Members | stefan bradham | None | 2024-01-19 09:30 | 2024-01-22 19:00 | 2024-01-20 05:31 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 836353936 | 1 | Late | 5 | 5 | 2 | days
7.4981e+17 | Send RMSDC Personnel List | Christ Bellarmine | None | 2024-01-19 09:30 | 2024-01-20 19:00 | 2024-01-20 05:22 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 | 2 | Late | 4 | 4 | 2 | days
7.4981e+17 | Roles and Permissions Configurations | Tanu Gupta | High | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-19 20:00 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 56 | Late | 57 | 57 | 1 | days
7.4981e+17 | ACL Templates Replacemnt in Functions & Addition of 2 new Functions for ACL | Anusha V | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 15:10 | In Progress | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 59 | Late | 60 | 60 | 1 | days
7.4981e+17 | Reversal of Invoice - For school code - 617089 I believe this invoice was raised (Inv No. INV/2900) | Swetha K | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 09:43 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Discrepancy in Student Count | Swetha K | None | 2024-01-23 09:30 | 2024-01-24 19:00 | 2024-01-22 09:39 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 6 | Late | 8 | 8 | 2 | days
7.4981e+17 | Rectify the issue on mismatch of target value between upload file and uploaded data in system | Tanu Gupta | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 20:23 | In Progress | Yes | 10% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 59 | Late | 60 | 60 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Client meetings | Rishikesh Gogha,Rajesh Shindagi | None |  |  | 2024-01-19 18:35 | In Progress | No | 10% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 745115006,758002363 |  | On Time |  | 0 | 0 | days |  | Clear | Dharanidharan C
7.4981e+17 | Claim Detailed Report Zoho Analytics | Achyuth T M | High | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-19 14:34 | Done | No | 100% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Check Books integration for all the modules | Vignesh R | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-22 10:03 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 56 | Late | 57 | 57 | 1 | days
7.4981e+17 | Major Holiday and Minor Holiday adding | Mary Nisha | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 17:37 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 59 | Late | 60 | 60 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Zoho CRM - Process Flow Diagram | Supril Jain | None | 2024-01-18 09:30 | 2024-01-23 19:00 | 2024-01-19 07:13 | In Progress | Yes | 0% | Accorian - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 55 | Late | 61 | 61 | 4 | days
7.4981e+17 | Activation of Zoho CRM ID | Nikita Srivastava | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 19:20 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | #5851 Changes Required in Zoho | Maninder Singh | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-18 17:14 | Done | No | 100% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Business Description page - 2, 3 UI Development | Nawaz Sharief | None |  |  | 2024-01-19 19:22 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 841115370 | 841115370 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Website API Integration | Sai Krishna | None | 2024-01-22 09:30 | 2024-01-23 19:00 | 2024-01-19 09:53 | Done | No | 100% | QUICK HEAL - Zoho CRM & Zoho Marketing Automation | Milestone Two-Implementation of Zoho CRM – API Integrations | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 16 | Late | 18 | 18 | 2 | days
7.4981e+17 | Application push to creator | Mary Nisha | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-22 10:28 | Development Complete | Yes | 0% | VSINTERCONNECT CR for Estore | Milestone Two-Development, UAT & Go Live of Estore CR | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 56 | Late | 57 | 57 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | UAT Demo | Mohammed Yusha,Tanu Gupta | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 18:58 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Test Document Creation | Anusuyadevi V,Tanu Gupta | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 20:40 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121,790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | RHI - Steel Production API | Anusuyadevi V | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 19:26 | Done | No | 100% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | UI screen for Final Review | Supreeth R Kalluraya | None | 2024-01-12 09:30 | 2024-01-31 19:00 | 2024-01-18 12:57 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | Milestone Four : Development completion and Go Live of CS Certification Portal. | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 788577227 | 788577227 | 47 | Late | 67 | 67 | 14 | days |  | Clear | Christ Bellarmine
7.4981e+17 | UI Screen for Escalation | Supreeth R Kalluraya | None | 2024-01-11 09:30 | 2024-01-31 19:00 | 2024-01-17 16:59 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | Milestone Four : Development completion and Go Live of CS Certification Portal. | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 788577227 | 788577227 | 47 | Late | 68 | 68 | 15 | days |  | Clear | Christ Bellarmine
7.4981e+17 | OBD Call Issue | Nikita Srivastava | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 18:45 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 16 | Late | 17 | 17 | 1 | days
7.4981e+17 | ZOHO EXPENSE INTERGRATION SYNCING ISSUE | Rishikesh Gogha | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 10:19 | Done | No | 100% | AMC - VAlign | HESPL AMC - 2023 - 24 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Client Meeting - Requirement Gathering | Supril Jain | None | 2024-01-17 09:30 | 2024-01-22 19:00 | 2024-01-18 09:28 | In Progress | Yes | 0% | Accorian - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 56 | Late | 62 | 62 | 4 | days
7.4981e+17 | Start Date and End Date Automation Fix and membership start date | M S Satya | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 13:41 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 62 | Late | 63 | 63 | 1 | days |  | Clear
7.4981e+17 | Application Form Automation and Page Creation | Mallesh M S | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-17 09:38 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 28 | Late | 29 | 29 | 1 | days |  | Clear
7.4981e+17 | Assign Owner to New Facebook Campaign Form Deal(Vishakapatnam) | Sachin Patil | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 19:00 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Create User Manual | Mohammed Yusha,Anusuyadevi V,Tanu Gupta | High | 2024-01-22 19:00 | 2024-01-24 14:00 | 2024-01-17 10:23 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,786479121,790157522 | 6 | Late | 9 | 9 | 2 | days
7.4981e+17 | Review CRM with (Internal Team) | Leahanne Thomas | None | 2024-01-17 09:30 | 2024-02-05 19:00 | 2024-01-18 01:10 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 811824969 | 8 | Late | 28 | 28 | 14 | days
7.4981e+17 | Create Standard Operating Process (SOP's) for Finance- | Leahanne Thomas | None | 2024-02-13 09:30 | 2024-06-06 19:00 | 2024-01-18 00:07 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 811824969 | -80 | On Time | 35 | 35 | 83 | days
7.4981e+17 | CreateTraining (QRC, Playbook, Videos How to’s, FAQ’s- Finance Team) | Christ Bellarmine | None |  |  | 2024-01-17 23:51 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 |  | On Time |  | 0 | 0 | days
7.4981e+17 | IIFL Scrum Call | Tanu Gupta | High | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 23:37 | In Progress | Yes | 10% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 61 | Late | 62 | 62 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Email Id Issue changes for One of the user | Monik Chettiyar | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-17 20:27 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Zoho People Support Meeting | Monik Chettiyar | None | 2024-01-10 09:30 | 2024-01-12 19:00 | 2024-01-17 20:17 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 5 | Late | 8 | 8 | 3 | days
7.4981e+17 | User story 2 - reports rework in analytics | M S Satya | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 09:42 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 61 | Late | 62 | 62 | 1 | days |  | Clear
7.4981e+17 | Contact Data Migration - Data Cleaning and Updating the template | M S Satya | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 15:53 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 62 | Late | 63 | 63 | 1 | days |  | Clear
7.4981e+17 | Converetd deal - create a check box in sow module, one deal shd have only one SOW, and filter only if its deal converted | Aishwarya T | None | 2024-01-17 09:30 | 2024-01-18 19:00 | 2024-01-18 10:39 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 60 | Late | 62 | 62 | 2 | days |  | Clear | Irshad Pasha
7.4981e+17 | All Modules Customization | Aishwarya T | None | 2024-01-16 09:30 | 2024-01-17 19:00 | 2024-01-18 10:31 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 61 | Late | 63 | 63 | 2 | days |  | Clear | Irshad Pasha
7.4981e+17 | #5836 CRM Changes for V-Align Team | Maninder Singh | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-18 09:37 | Done | No | 100% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Meeting :Expense Management Revamp ¦ Leader statements issue discussion | Maninder Singh | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 12:33 | Done | No | 100% | Educational_Zoho Creator_CR | Milestone Eight-Implementation of Zoho Creator - Go Live | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | Dashboard - Show Pi and Po different table | Sachin Patil | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 15:27 | Done | No | 100% | Stanzen_Zoho_Creator Change Request 4 | Milestone One-Implementation of Zoho Creator Change Request 4 | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Account Module - Billing Address Automation | M S Satya | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 13:04 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 66 | Late | 67 | 67 | 1 | days |  | Clear
7.4981e+17 | Zoho Survey MBE Form Creation | Sai Krishna | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-16 09:42 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 66 | Late | 67 | 67 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Email Template Notification update - v5, FM and Digisales | Mary Nisha | High | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 10:28 | Done | No | 100% | AMC - VAlign | First Meridian - Start Date - 01-05-2023 and End Date - 30-04-2024 | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 775643568 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | Solution for Credit Notes | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Solution for Payout Integration | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Solution for Bill | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | By Credit note | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Auto Payment knock off Form and Solution | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Manual updation of Customer for incoming payments | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Payin Integration with Bank | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Payout on Cash Back | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Payout Integration with Bank | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Quote Configuration Page | Anusuyadevi V,Tanu Gupta | High | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-15 18:23 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 786479121,790157522 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Sales Order Fulfillment Test Cases | Anusuyadevi V | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 22:51 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | ZB Vs EMS Report | Waheeba Khan | None | 2024-01-12 09:30 | 2024-01-18 19:00 | 2024-01-12 18:20 | To Do | Yes | 0% | Educational Initiatives : Improvisation of the Books and Budgeting Master and Payment Integration in | Milestone Two-Project and SBU mapping in Zoho Creator and Books | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 60 | Late | 67 | 67 | 5 | days |  | Clear
7.4981e+17 | Video Manuals | Rishikesh Gogha | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-12 09:47 | Done | No | 100% | Airowire - Zoho Expense | Milestone One-Advance Payment for Project Initiation - Zoho Expense | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | UAT Changes | Mohammed Yusha,Shavi Thakur | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-16 09:24 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Five-Advance Reports & Analytics | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 701373265,773081417 | 5 | Late | 6 | 6 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | RY and ED BOM | Kalyanasundaram L | None | 2024-01-11 09:30 | 2024-01-12 19:00 | 2024-01-15 22:55 | To Do | Yes | 0% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 66 | Late | 68 | 68 | 2 | days |  | Clear
7.4981e+17 | Guest Portal associate,member,employee etc. not visible afterapproval | Maninder Singh | None | 2024-01-12 09:30 | 2024-01-16 19:00 | 2024-01-12 14:46 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 62 | Late | 67 | 67 | 3 | days |  | Clear | Supril Jain
7.4981e+17 | December payrun | Kiran Shrivastav | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 23:23 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | Save As draft(backend) | Nawaz Sharief | None | 2024-01-31 09:30 | 2024-02-15 19:00 | 2024-01-11 19:01 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 841115370 | 21 | Late | 37 | 37 | 12 | days |  | Not Clear
7.4981e+17 | Backend - -Management & Controls | Nawaz Sharief | None | 2024-01-31 09:30 | 2024-02-05 19:00 | 2024-01-11 18:54 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 841115370 | 31 | Late | 37 | 37 | 4 | days |  | Not Clear
7.4981e+17 | Management & Controls Screens | Avinash Sah | None | 2024-01-19 09:30 | 2024-01-23 19:00 | 2024-01-11 18:43 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 830176894 | 44 | Late | 49 | 49 | 3 | days |  | Clear
7.4981e+17 | Add roundoff in Invoice flow | Vignesh R | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 10:04 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | Zoho Order Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 62 | Late | 63 | 63 | 1 | days |  | Clear
7.4981e+17 | Connected For Meeting With Client | Swetha K,Aaftab Ahmad | Medium | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 18:29 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 776475994 | 774026088,776475994 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | If I seelct part part code should come automatically | Nikita Srivastava | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 09:47 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 55 | Late | 56 | 56 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Once the status is changed to “In Progress” - sending follow-up emails to customer | Sachin Patil | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 19:01 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | External Meeting with Durian Team and Convert Lead to Deal for New WordPress Form(Premium Furniture Showroom Visakhapatnam) | Sachin Patil | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 18:44 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 10:29 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 38 | Late | 39 | 39 | 1 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-12 10:29 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Quote Automation Testing and Correction | Anusuyadevi V | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-11 23:02 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Margin Calculation Report | Achyuth T M | High | 2024-01-23 09:30 | 2024-01-24 19:00 | 2024-01-12 13:36 | To Do | Yes | 0% | Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 54 | Late | 56 | 56 | 2 | days
7.4981e+17 | Cash Flow Logic Discussion | Achyuth T M | High | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-12 13:36 | To Do | Yes | 0% | Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 61 | Late | 62 | 62 | 1 | days
7.4981e+17 | Client Meeting for Post Go Live doubts | Mohammed Yusha,Tanu Gupta | High | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 19:25 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Test | Irshad Pasha | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 18:57 | In Progress | Yes | 10% | Captain Fresh - Zoho CRM | None | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 701341459 | 67 | Late | 68 | 68 | 1 | days |  | Clear
7.4981e+17 | Additional Zone Wise reports | Aishwarya T | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 14:46 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 15 | Late | 16 | 16 | 1 | days
7.4981e+17 | Feasibility check of using zoho survey for certification forms | Sai Krishna | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-10 09:38 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 69 | Late | 70 | 70 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | UI Validation Rules -Business Info Screen | Avinash Sah | None | 2024-01-17 09:30 | 2024-01-23 19:00 | 2024-01-11 12:38 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176894 | 13 | Late | 20 | 20 | 5 | days |  | Clear
7.4981e+17 | Buiness Description Screens | Nawaz Sharief | None | 2024-01-17 09:30 | 2024-01-19 19:00 | 2024-01-11 12:33 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 841115370 | 48 | Late | 51 | 51 | 3 | days |  | Clear
7.4981e+17 | Portal User Acceess Function | M S Satya | None | 2024-01-10 09:30 | 2024-01-11 19:00 | 2024-01-10 16:36 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 67 | Late | 69 | 69 | 2 | days |  | Clear
7.4981e+17 | Custom Function creation for updating the MBE in the Customer Master and the status is decertified/expired/terminated, revoking the status of the portal Users | Kalyanasundaram L | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-11 09:59 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 69 | Late | 70 | 70 | 1 | days |  | Clear
7.4981e+17 | Add buttons on Quality Check reports, Enabled new workflows for QC without submit, Validation on QC and Testing | Sachin Patil | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 19:57 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Item description is not required | Nikita Srivastava | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 10:11 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 56 | Late | 57 | 57 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Address should in same manner for billing and shipping (Pre Installation) | Nikita Srivastava | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 10:06 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 56 | Late | 57 | 57 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | R&D - Alain & Charles | Stuti S. Kulshrestha | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 13:51 | In Progress | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 68 | Late | 69 | 69 | 1 | days
7.4981e+17 | Lead module issue | Nikita Srivastava | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 11:13 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Pre-Lead Status Locking and update city, zipcode | Anusuyadevi V | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-11 09:24 | Done | No | 100% | AMC - VAlign | Infifresh 01-01-2024 to 31-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | HTML Template | Mohammed Yusha,Anusuyadevi V | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-10 08:51 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 701373265,786479121 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Zoho Creator - Client Call for Report and Multi Quote | Tanu Gupta | High | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 19:24 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 68 | Late | 69 | 69 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Juspay ¦ Client meeting for post-go live doubts/issues | Tanu Gupta | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 19:56 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Auto Create Credit Notes | Anusuyadevi V,Tanu Gupta | High | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-10 19:36 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 786479121,790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Client Call with nishica for crm walkthrough | Supril Jain | None | 2024-01-09 09:30 | 2024-01-09 10:30 | 2024-01-10 07:53 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 69 | Late | 70 | 70 | 1 | hrs
7.4981e+17 | BA DO Standup | Supreeth R Kalluraya,Stuti S. Kulshrestha | None | 2024-01-11 09:30 | 2024-01-19 19:00 | 2024-01-10 23:13 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 788577227,808004288 | 59 | Late | 68 | 68 | 7 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Issue in Keyword generation ChatGPT | Basavaraj Patil,Prableen Kaur | None | 2024-01-10 09:30 | 2024-01-11 19:00 | 2024-01-10 18:48 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 781564441,792886644 | 12 | Late | 14 | 14 | 2 | days
7.4981e+17 | Progress Junction 1/9 & 1/10 | Supreeth R Kalluraya,Stuti S. Kulshrestha | None | 2024-01-09 09:30 | 2024-01-10 19:00 | 2024-01-09 20:34 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 788577227,808004288 | 0 | Late | 2 | 2 | 2 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Notes Prompt Development for Deals Module | M S Satya | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 15:04 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 69 | Late | 70 | 70 | 1 | days |  | Clear
7.4981e+17 | New FAQ Update in Zoho People | Monik Chettiyar | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 19:18 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Request to assist with zoho login | Monik Chettiyar | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-09 18:47 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | New offer Letter Content Changes | Monik Chettiyar | None | 2024-01-03 09:30 | 2024-01-09 19:00 | 2024-01-09 18:32 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 69 | Late | 76 | 76 | 5 | days
7.4981e+17 | Revamping Export Region | Nikita Srivastava | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 17:51 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Add Layout Rule for Sales Type and Status | Sachin Patil | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 19:03 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | #268 Deactivate user from Zoho CRM | Maninder Singh | None |  |  | 2024-01-09 13:59 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Issue in Vendor sync for PAN No | Shavi Thakur,Tanu Gupta | High | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 18:04 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 773081417,790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Profit and Loss Query Table 1 | Achyuth T M | High | 2024-01-09 09:30 | 2024-01-11 19:00 | 2024-01-09 17:08 | Done | No | 100% | Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 1 | Late | 4 | 4 | 3 | days
7.4981e+17 | Zoho Desk and Creator - Send attachments from crm to desk while createTicket | Tanu Gupta | High | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-09 18:35 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 62 | Late | 63 | 63 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Zoho Creator - Storage Tracker Changes | Tanu Gupta | High | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 18:26 | Development Complete | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 69 | Late | 70 | 70 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Item Tracking Report | Achyuth T M | High | 2024-01-08 09:30 | 2024-01-10 19:00 | 2024-01-09 10:05 | In Progress | Yes | 0% | Ecovinal Project 3 - Farmer Management | Milestone Two-Zoho Creator – Farmer Operations: Configuration and customisation, Software demo | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 68 | Late | 71 | 71 | 3 | days |  | Clear
7.4981e+17 | Scrum Call - 01--01-2024 | Ranjana Poojari | None |  |  | 2024-01-08 18:14 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Partner and Partner lead Modules | Aishwarya T | None | 2024-01-08 09:30 | 2024-01-09 19:00 | 2024-01-08 13:29 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 69 | Late | 71 | 71 | 2 | days
7.4981e+17 | SLA configuration for Digital lending department | Swetha K | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 18:43 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Zoho - ERP Roadmap | Waheeba Khan | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 12:12 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Two-Payment for January2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 57 | Late | 58 | 58 | 1 | days
7.4981e+17 | UAT and UAT Changes | Anusuyadevi V | None | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-08 09:38 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | -1 | On Time | 1 | 1 | 2 | days
7.4981e+17 | customer Happiness enabled for all department and happiness rating in all department(9) email content | Swetha K | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 18:57 | Done | No | 100% | IIFL SAMASTA -Zoho Creator_Helpdesk CR | Milestone One-Customization and Development of Change Request for Zoho Help Desk | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 5 | Late | 6 | 6 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | ABMPL Application Demo Internally | Vaikuntam Chowdary | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-08 19:09 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 69 | Late | 70 | 70 | 1 | days |  | Clear
7.4981e+17 | Member Management CRM Work Session | Stuti S. Kulshrestha | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 23:35 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 2 | Late | 3 | 3 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Connecting With Support Team | Kalyanasundaram L | None | 2024-01-08 09:30 | 2024-01-15 19:00 | 2024-01-08 11:02 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 63 | Late | 71 | 71 | 6 | days |  | Clear
7.4981e+17 | Automations (CCO form coverage schedule) | Ayush Singh,Mary Nisha | None | 2024-01-04 09:30 | 2024-01-05 19:00 | 2024-01-05 15:40 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 772908679,775643568 | 73 | Late | 75 | 75 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Certificates Module Data Check for each Column | Kalyanasundaram L | High | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-06 19:19 | Development Complete | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 75 | Late | 76 | 76 | 1 | days |  | Clear
7.4981e+17 | KT Given Over Projects | unassigned | None | 2024-01-05 09:30 | 2024-01-10 19:00 | 2024-01-05 18:35 | To Do | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 776475994 | - | 68 | Late | 74 | 74 | 4 | days
7.4981e+17 | Sandbox to Live - IL New branch | Swetha K | None | 2024-02-02 09:30 | 2024-02-05 19:00 | 2024-01-05 16:36 | To Do | Yes | 0% | IIFL SAMASTA -New Branch Survey Enhancement | Milestone Two-Development, Configuration UAT and Go-Live of New Branch Survey Enhancement | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 42 | Late | 46 | 46 | 2 | days |  | Clear | Selva Bharathi
7.4981e+17 | Demo on Supply chain management | Waheeba Khan | None | 2024-01-05 09:30 | 2024-01-15 19:00 | 2024-01-05 09:52 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Two-Payment for January2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 50 | Late | 61 | 61 | 7 | days
7.4981e+17 | Configuration of Workflow Rules: Task Module | Rajesh Shindagi,Monik Chettiyar | None | 2024-01-17 09:30 | 2024-01-19 15:00 | 2024-01-04 19:06 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363,792262192 | 59 | Late | 62 | 62 | 24.5 | hrs |  | Not clear
7.4981e+17 | Create Project And Assign In Tour TE: 202400018 + Rename Sub-form's Field | Aaftab Ahmad | Medium | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 19:04 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 776475994 | 776475994 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | RE: Lack of POI submission in ZOHO | Kiran Shrivastav | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 12:55 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Miscellaneous Tasks | Mary Nisha | None | 2024-01-10 09:30 | 2024-02-29 19:00 | 2024-01-08 11:24 | In Progress | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 18 | Late | 69 | 69 | 37 | days
7.4981e+17 | Hide and Show fields in Creator and automations | Mary Nisha | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 10:42 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 70 | Late | 71 | 71 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Region Change Request | Nikita Srivastava | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 12:20 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Proposal Attachment Functionality | Sai Krishna | None | 2024-01-04 09:30 | 2024-01-05 19:00 | 2024-01-05 09:38 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 73 | Late | 75 | 75 | 2 | days |  | Clear
7.4981e+17 | Scorecard Call with Client for various queries and issues | Tanu Gupta | High | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 20:32 | Done | No | 100% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 2 | Late | 3 | 3 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Validate quote availability before moving to quotation submitted stage | Anusuyadevi V | None | 2024-01-16 09:30 | 2024-01-17 19:00 | 2024-01-08 09:24 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Client Call On Books Open Points & Changes | Mohammed Yusha | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 19:45 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Four-Financial Accounting Management System | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | TSD Creation & Solutioning | Mohammed Yusha | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-05 16:12 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 54 | Late | 55 | 55 | 1 | days
7.4981e+17 | Client Demo - Zoho Creator, Desk & Books | Mohammed Yusha | None | 2024-01-08 09:30 | 2024-01-09 19:00 | 2024-01-05 16:04 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 69 | Late | 71 | 71 | 2 | days |  | Clear
7.4981e+17 | Data Import on Item Master for Samsung Electronic City Warehouse | Sachin Patil | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 13:06 | Terminated/Cancelled | No | 100% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 2 | Late | 3 | 3 | 1 | days |  | Clear
7.4981e+17 | Website Updates - Sign up links update | unassigned | None |  |  | 2024-01-05 09:51 | To Do | No | 0% | V-Align Marketing Activites | None | 7.4981e+17 | 7.4981e+17 |  | 800651184 | - |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Create Content for FAQ of MBE applicant dashboard | Kris Oswold,Constance Jones | None | 2024-01-04 09:30 | 2024-03-20 19:00 | 2024-01-04 20:40 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 788577227 | 824545238,811824790 | -2 | On Time | 75 | 75 | 55 | days
7.4981e+17 | CPS Transaction Changes | Mallesh M S | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-08 17:15 | In Progress | Yes | 10% | Ecovinal Project 3 - Farmer Management | Milestone Two-Zoho Creator – Farmer Operations: Configuration and customisation, Software demo | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 778475418 | 68 | Late | 69 | 69 | 1 | days |  | Clear
7.4981e+17 | Client Visit on 08-Jan-2023 | Vignesh R,Mallesh M S | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 11:19 | In Progress | Yes | 10% | Ecovinal Project 3 - Farmer Management | Milestone Two-Zoho Creator – Farmer Operations: Configuration and customisation, Software demo | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602,778475418 | 70 | Late | 71 | 71 | 1 | days |  | Clear
7.4981e+17 | Convert WordPress (New Forms) Lead to Deal and Assign owner to deal | Sachin Patil | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 18:51 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Stock Adjustment - For raw material or V to V need to fetch the rate from last Bill Price | Sachin Patil | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-05 11:19 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Model Name required in Channel Partner Report | Nikita Srivastava | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 10:37 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Client Call For Zoho Survey Walkthrough | Supril Jain | None | 2024-01-05 09:30 | 2024-01-10 19:00 | 2024-01-05 09:37 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 68 | Late | 74 | 74 | 4 | days
7.4981e+17 | Whatsapp Intreation (Gupshups) | Ayush Singh | None | 2024-03-14 09:30 | 2024-03-15 19:00 | 2024-01-09 09:18 | In Progress | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 3 | Late | 5 | 5 | 2 | days
7.4981e+17 | Employee data bulk upload | Kiran Shrivastav | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 11:40 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | SharedServices Flow(08/01/24) | Anusha V | None |  |  | 2024-01-09 09:19 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Setup Sales order cycle for zoho inventory | Tanu Gupta | High | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 18:47 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | HO Team Partial Save flow & Chechbox placement | Anusha V | High | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-08 09:51 | Done | No | 100% | IFL SAMASTA - Zoho Creator -Shopkeeper Onboarding | Milestone Two-Configuration and Customization of Zoho Creator- Shopkeeper Onboarding Change request | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | BOM Approval Process Creation | Vaikuntam Chowdary | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 15:25 | QA level 1 Completed | Yes | 10% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 74 | Late | 75 | 75 | 1 | days |  | Clear
7.4981e+17 | Zoho Payroll Training | Kiran Shrivastav | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-04 14:34 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Prior Payrun | Kiran Shrivastav | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-04 14:17 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Employee details | Kiran Shrivastav | None | 2024-01-25 09:30 | 2024-01-26 19:00 | 2024-01-04 14:17 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 25 | Late | 27 | 27 | 2 | days
7.4981e+17 | Roles and Permissions | Kiran Shrivastav | None | 2024-01-17 09:30 | 2024-01-19 19:00 | 2024-01-04 14:00 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 31 | Late | 34 | 34 | 3 | days
7.4981e+17 | Probation Flow | Kiran Shrivastav | None | 2024-01-15 09:30 | 2024-01-19 19:00 | 2024-01-04 14:00 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 31 | Late | 36 | 36 | 5 | days
7.4981e+17 | Leave Management | Kiran Shrivastav | None | 2024-01-15 09:30 | 2024-01-17 19:00 | 2024-01-04 13:58 | Development | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 61 | Late | 64 | 64 | 3 | days
7.4981e+17 | Training | Kiran Shrivastav | None | 2024-01-24 09:30 | 2024-01-26 19:00 | 2024-01-04 13:39 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 52 | Late | 55 | 55 | 3 | days
7.4981e+17 | Offer Letter Templates | Kiran Shrivastav | None | 2024-01-11 09:30 | 2024-01-12 19:00 | 2024-01-04 13:33 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 66 | Late | 68 | 68 | 2 | days
7.4981e+17 | HR Inbox | Kiran Shrivastav | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-04 13:30 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 66 | Late | 67 | 67 | 1 | days
7.4981e+17 | Hiring Pipeline | Kiran Shrivastav | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-04 13:30 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 67 | Late | 68 | 68 | 1 | days
7.4981e+17 | I can select year 2020 in "Select the approximate year in which you became a member of the Council?" even though I have selected 2020 in "Select the approximate year since which you are the member?”, User can only become Council member after two years of Becoming member, thus "Rest options should be disable in dropdown. | Maninder Singh | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-04 12:35 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 69 | Late | 70 | 70 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | If i select (Other) in "Payment For" field, new open file should have description like "please add Payment for description"Retest | Maninder Singh | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-04 12:29 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 70 | Late | 71 | 71 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Data Analysis Greater New England, Houston,Michigan | Prableen Kaur,Pannaga H | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-04 13:55 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 792886644 | 792886644,795342015 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | Data Analysis of each document of 23 Regions | Prableen Kaur | None | 2024-01-04 09:30 | 2024-01-12 19:00 | 2024-01-04 13:38 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 11 | Late | 20 | 20 | 7 | days
7.4981e+17 | Council Member Validation | Maninder Singh | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-04 11:06 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 782721491 | 67 | Late | 68 | 68 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Import Credit Notes | Tanu Gupta | High | 2024-01-05 09:30 | 2024-01-10 19:00 | 2024-01-04 12:08 | Development Complete | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 68 | Late | 74 | 74 | 4 | days |  | Clear | Supril Jain
7.4981e+17 | Configuration of Copy Customization | unassigned | None |  |  | 2024-01-04 12:08 | Terminated/Cancelled | No | 100% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | - |  | On Time |  | 0 | 0 | days |  | Not clear
7.4981e+17 | Configuration of Deal Module and Field layout rules and field automations | Rajesh Shindagi | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-04 12:08 | In Progress | Yes | 10% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 69 | Late | 70 | 70 | 1 | days |  | Clear
7.4981e+17 | Configuration of Scoring Rules | unassigned | None |  |  | 2024-01-04 12:07 | To Do | No | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | - |  | On Time |  | 0 | 0 | days |  | Not clear
7.4981e+17 | Configuration of Actions | Rajesh Shindagi,Monik Chettiyar | None | 2024-01-15 09:30 | 2024-01-19 17:00 | 2024-01-04 12:07 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363,792262192 | 59 | Late | 64 | 64 | 45.5 | hrs |  | Not clear
7.4981e+17 | Import Data Into Zoho Catalyst. | Basavaraj Patil | None | 2023-12-26 09:30 | 2024-01-05 19:00 | 2024-01-04 09:57 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 73 | Late | 84 | 84 | 9 | days |  | Clear | Christ Bellarmine
7.4981e+17 | Update profile -> need to fix CHAR length of "Postal Address", "City/Village" & "District" fields. | Maninder Singh | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-04 12:12 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 70 | Late | 71 | 71 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Operation Dashboard S2 and S3 | Sachin Patil | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 10:38 | Done | No | 100% | Stanzen_Zoho_Creator Change Request 4 | Milestone One-Implementation of Zoho Creator Change Request 4 | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Videos for Hiring Manager and recruiter steps | Kiran Shrivastav | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 10:27 | Done | No | 100% | Karam Safety_Zoho ONE | Milestone Six-Implementation of Zoho Recruit | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | Import Invoice and Reco | Tanu Gupta | High | 2024-01-03 09:30 | 2024-01-04 19:00 | 2024-01-03 23:15 | Development Complete | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 790157522 | 790157522 | 74 | Late | 76 | 76 | 2 | days |  | Clear | Supril Jain
7.4981e+17 | Need to check and change the view of the GRN Subform | Vignesh R | None | 2024-01-10 09:30 | 2024-01-11 19:00 | 2024-01-03 21:53 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 67 | Late | 69 | 69 | 2 | days |  | Clear
7.4981e+17 | Client Visit on 05-Jan-2023 | Vignesh R | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-03 21:44 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 73 | Late | 74 | 74 | 1 | days
7.4981e+17 | Check Black screen while pushing to the books or updating the masters | Vignesh R | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-03 21:34 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | Zoho Purchase and Inventory | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 69 | Late | 70 | 70 | 1 | days |  | Clear
7.4981e+17 | Bills Date Difference in Creator and Books | Vignesh R | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-03 21:26 | Development Complete | Yes | 10% | Trimble Group_Zoho Books & Zoho Creator | Zoho Purchase and Inventory | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 74 | Late | 75 | 75 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | UAT Support | Swetha K | None | 2024-01-05 09:30 | 2024-01-10 19:00 | 2024-01-04 11:24 | Done | No | 100% | IIFL SAMASTA -Zoho Creator_Helpdesk CR | Milestone One-Customization and Development of Change Request for Zoho Help Desk | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 2 | Late | 8 | 8 | 4 | days |  | Clear | Selva Bharathi
7.4981e+17 | Invoice Books Integration | Aaftab Ahmad | None | 2024-01-09 09:30 | 2024-01-10 19:00 | 2024-01-04 10:24 | Development Complete | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 776475994 | 68 | Late | 70 | 70 | 2 | days |  | Clear | Waheeba Khan
7.4981e+17 | COA Books Integration | Aaftab Ahmad | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 10:24 | Development Complete | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 776475994 | 74 | Late | 75 | 75 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Warehouse/Branch Books Integration | Aaftab Ahmad | None |  |  | 2024-01-04 10:24 | Terminated/Cancelled | No | 100% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 776475994 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Zoho CRM and Knowlarity Integration | Siddharth Sharma | None | 2024-01-25 09:30 | 2024-01-31 19:00 | 2024-01-04 09:59 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 | 47 | Late | 54 | 54 | 5 | days |  | Clear
7.4981e+17 | Area-wise customer list | Siddharth Sharma | None | 2024-01-04 09:30 | 2024-01-08 19:00 | 2024-01-04 09:53 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 | 70 | Late | 75 | 75 | 3 | days |  | Clear
7.4981e+17 | iDatalytics Scrum Meeting | Christ Bellarmine | None | 2024-01-04 11:30 | 2024-01-04 12:30 | 2024-01-03 16:53 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 81581486 | 74 | Late | 75 | 75 | 1 | hrs |  | Clear
7.4981e+17 | Internal Discussion on Supply chain management | Waheeba Khan | None | 2024-01-02 09:30 | 2024-01-12 19:00 | 2024-01-03 10:40 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Two-Payment for January2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 53 | Late | 64 | 64 | 9 | days
7.4981e+17 | QA - Release 4 | Dharanidharan C,Stuti S. Kulshrestha | None | 2024-01-18 09:30 | 2024-01-19 19:00 | 2024-01-03 17:45 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504,808004288 | 10 | Late | 12 | 12 | 2 | days
7.4981e+17 | QA - Release 2 | Dharanidharan C,Stuti S. Kulshrestha | None | 2024-01-09 09:30 | 2024-01-17 19:00 | 2024-01-03 17:29 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504,808004288 | 12 | Late | 21 | 21 | 7 | days
7.4981e+17 | Creation of Email templates -Portal | christina santos | None | 2024-01-11 09:30 | 2024-01-15 19:00 | 2024-01-03 17:23 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 825341377 | 2 | Late | 7 | 7 | 3 | days
7.4981e+17 | Custom Reports & Dashboards-EA Allocation | Dharanidharan C | None | 2024-01-09 09:30 | 2024-01-17 19:00 | 2024-01-03 17:17 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 12 | Late | 21 | 21 | 7 | days
7.4981e+17 | Custom Reports & Dashboards- Member Reg | Dharanidharan C | None | 2024-01-03 09:30 | 2024-01-17 19:00 | 2024-01-03 17:12 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 12 | Late | 27 | 27 | 11 | days
7.4981e+17 | Setting up of Invoice template | Dharanidharan C | None | 2023-12-26 09:30 | 2024-01-05 19:00 | 2024-01-03 17:08 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 5 | Late | 16 | 16 | 9 | days
7.4981e+17 | Workflow & Automations- Proposal & Dues Stage | Dharanidharan C | None | 2023-12-26 09:30 | 2024-01-05 19:00 | 2024-01-03 17:08 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 5 | Late | 16 | 16 | 9 | days
7.4981e+17 | Configuration Member Contacts Field(i.e. Accounts Module) | Dharanidharan C | None | 2023-12-21 09:30 | 2024-03-15 19:00 | 2024-01-03 17:00 | In Progress | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 3 | Late | 89 | 89 | 62 | days
7.4981e+17 | Share Integration to CRM with MS Outlook | Dharanidharan C | None | 2024-01-04 09:30 | 2024-01-17 19:00 | 2024-01-03 16:11 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 12 | Late | 26 | 26 | 10 | days
7.4981e+17 | Create Custom Reports & Dashboards | Dharanidharan C | None | 2023-12-18 09:30 | 2024-01-17 19:00 | 2024-01-03 16:07 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 12 | Late | 43 | 43 | 23 | days
7.4981e+17 | Blueprint Correction in leads and Deals Module | Monik Chettiyar | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-03 15:56 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 76 | Late | 77 | 77 | 1 | days
7.4981e+17 | Final Data Set preparation including Go members and Master sheet | Dharanidharan C,Stuti S. Kulshrestha | None | 2024-01-12 19:00 | 2024-02-09 19:00 | 2024-01-03 15:39 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504,808004288 | 13 | Late | 42 | 42 | 20 | days
7.4981e+17 | Migration from Google Mail to Zoho Mail | Irshad Pasha | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-03 11:17 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 701341459 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Testing - Zoho Bookings Multiple user issue fix development | M S Satya | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 12:09 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 74 | Late | 75 | 75 | 1 | days |  | Clear
7.4981e+17 | Issue and Purchase Report | Achyuth T M | High | 2024-01-03 09:30 | 2024-01-05 19:00 | 2024-01-03 19:41 | Done | No | 100% | Ecovinal Project 3 - Farmer Management | Milestone Two-Zoho Creator – Farmer Operations: Configuration and customisation, Software demo | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 0 | Late | 3 | 3 | 3 | days |  | Clear
7.4981e+17 | need date validation for " Departure date" & " Arrival date". (now I can enter past date in arrival date. ). | Maninder Singh | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-03 11:02 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 74 | Late | 75 | 75 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | I can submit scholarship form multiple time for same student. (don't allow multiple times). | Maninder Singh | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 10:57 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 75 | Late | 76 | 76 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | CCO PDF Level Fields creation and data fetching from the CRM. | Ayush Singh | None | 2024-01-04 09:30 | 2024-01-05 19:00 | 2024-01-04 17:02 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 73 | Late | 75 | 75 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Update the new cost to farmer summary | Mallesh M S | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-04 10:04 | QA level 1 Completed | Yes | 10% | Ecovinal Project 3 - Farmer Management | None | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 67 | Late | 68 | 68 | 1 | days |  | Clear
7.4981e+17 | Opportunity Module Product subform and fields | Nikita Srivastava | None | 2024-01-09 09:30 | 2024-01-10 19:00 | 2024-01-03 23:29 | To Do | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 774653652 | 68 | Late | 70 | 70 | 2 | days
7.4981e+17 | Opportunity Management Blueprint | Nikita Srivastava | None | 2024-01-12 09:30 | 2024-01-16 19:00 | 2024-01-03 23:24 | To Do | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 774653652 | 62 | Late | 67 | 67 | 3 | days
7.4981e+17 | Templates Customization | Ayush Singh,Mary Nisha | None | 2024-01-03 09:30 | 2024-01-05 19:00 | 2024-01-03 10:22 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679,775643568 | 73 | Late | 76 | 76 | 3 | days |  | Clear | Dharanidharan C
7.4981e+17 | Convert new WordPress lead to Deal and assign deal to Owner | Sachin Patil | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 18:29 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Agappe Scrum Call | Selva Bharathi | None | 2024-01-04 14:00 | 2024-01-04 15:00 | 2024-01-03 17:41 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | Milestone Three-Implementation of Zoho CRM - Sales & Service Management Application | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 701368573 | 74 | Late | 75 | 75 | 1 | hrs |  | Not Clear
7.4981e+17 | Weekly Project Update Meeting | Waheeba Khan,Supril Jain,Tanu Gupta | High | 2024-01-03 09:30 | 2024-01-31 19:00 | 2024-01-03 17:04 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 671373250,756836914,790157522 | 47 | Late | 76 | 76 | 21 | days |  | Clear | Supril Jain
7.4981e+17 | Add Ticket Type Field on Ticket and Create Lead based on Ticket Type | Sachin Patil | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 10:55 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Email Notification Approval mechanism for Journal Voucher | Mohan Kumar | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 12:45 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Testing of Quote Module Functionality | Anusuyadevi V | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 10:32 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Fulfillment Changes | Vaikuntam Chowdary | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 18:20 | Development Complete | Yes | 10% | The Yarn Bazaar - Sales & Purchase Management System | Milestone Three-Implementation of Zoho Creator – Order Management System | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 778472746 | 778472746 | 75 | Late | 76 | 76 | 1 | days |  | Clear
7.4981e+17 | Desk Integration testing | Mohammed Yusha,Vaikuntam Chowdary | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-03 17:20 | Done | No | 100% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 701373265,778472746 | 8 | Late | 9 | 9 | 1 | days |  | Clear
7.4981e+17 | Testing of Quote Module | Anusuyadevi V,Tanu Gupta | High | 2024-01-03 09:30 | 2024-01-09 19:00 | 2024-01-03 16:24 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 786479121,790157522 | 1 | Late | 8 | 8 | 5 | days
7.4981e+17 | Ledger and API's | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | API requirment discussion | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Governance Review | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Payout options and automation | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Knock of Report - Requirment ans Solution discussion | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Requirment Analysis - Incoming payments, Payouts, Integration | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Alert in Stock Adjustment | Vignesh R | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 17:33 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 76 | Late | 77 | 77 | 1 | days
7.4981e+17 | PAN/Mobile Entry Change | Sai Krishna | None | 2024-01-10 09:30 | 2024-01-11 19:00 | 2024-01-03 09:34 | QA level 1 Completed | Yes | 10% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 67 | Late | 69 | 69 | 2 | days |  | Clear
7.4981e+17 | CPC AMC Support Jan 24 FF | Sai Krishna | None | 2024-01-02 09:30 | 2024-01-15 19:00 | 2024-01-03 09:26 | Done | No | 100% | AMC - VAlign | Columbia Pacific Communities | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 49 | Late | 63 | 63 | 10 | days
7.4981e+17 | Team Inspire : Standup Call Jan 2024 | Supril Jain,Nikita Srivastava,Maninder Singh,Tanu Gupta,Kiran Shrivastav,Monik Chettiyar | High | 2024-01-02 09:30 | 2024-01-31 19:00 | 2024-01-02 23:57 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 756836914,774653652,782721491,790157522,791842987,792262192 | 4 | Late | 34 | 34 | 22 | days |  | Clear | Supril Jain
7.4981e+17 | Infifresh - Pre Lead Nurturing Process | Tanu Gupta | High | 2024-01-02 09:30 | 2024-01-04 19:00 | 2024-01-02 23:25 | Hold | Yes | 0% | AMC - VAlign | Infifresh 01-01-2024 to 31-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 74 | Late | 77 | 77 | 3 | days
7.4981e+17 | Show Line item details in Consolidated Template | Anusuyadevi V | None | 2024-01-10 09:30 | 2024-01-11 19:00 | 2024-01-03 09:07 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Requirement Gathering Document_People & payroll_Ozone Entertainments | Kiran Shrivastav | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 18:40 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 3 | Late | 4 | 4 | 1 | days |  | Clear
7.4981e+17 | Sick Leaves issue | Kiran Shrivastav | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 18:27 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | EHV Issue-02-01-2023 | Ranjana Poojari | None |  |  | 2024-01-02 20:23 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Email Changes And Configuration | Aaftab Ahmad | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-02 18:02 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 776475994 | 776475994 | 6 | Late | 7 | 7 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | "Student ID" field name is not same for Hindi language. | Maninder Singh | None | 2024-01-03 09:30 | 2024-01-04 19:00 | 2024-01-03 09:52 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 74 | Late | 76 | 76 | 2 | days |  | Clear | Supril Jain
7.4981e+17 | Solution Demo on Ledger and Advance blocking | Waheeba Khan | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 19:32 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Two-Payment for January2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 63 | Late | 64 | 64 | 1 | days
7.4981e+17 | Customer Payment Import For 425 Account | Rishikesh Gogha | None | 2023-12-21 09:30 | 2023-12-21 19:00 | 2024-01-02 14:56 | Done | No | 100% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 14 | Late | 15 | 15 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Betterplace : Currency Adjustments | Rishikesh Gogha | None | 2023-12-12 09:30 | 2023-12-12 19:00 | 2024-01-02 14:35 | Done | No | 100% | AMC - VAlign | Betterplace | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 23 | Late | 24 | 24 | 1 | days
7.4981e+17 | Fwd: Zoho expanse issue | Rishikesh Gogha | None | 2023-12-05 09:30 | 2023-12-05 19:00 | 2024-01-02 14:13 | Done | No | 100% | AMC - VAlign | HESPL AMC - 2023 - 24 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 30 | Late | 31 | 31 | 1 | days
7.4981e+17 | Bill - Field Mapping in Custom Function | Mallesh M S | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-02 10:27 | To Do | Yes | 0% | The Yarn Bazar - TYBZ - CR001 | Milestone Two-Completion of Solution Development, Testing and Zoho Creator CR Go - Live | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 56 | Late | 57 | 57 | 1 | days |  | Clear
7.4981e+17 | Sale Order - Mapping | Mallesh M S | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-02 10:27 | QA level 1 Completed | Yes | 10% | The Yarn Bazar - TYBZ - CR001 | Milestone Two-Completion of Solution Development, Testing and Zoho Creator CR Go - Live | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 74 | Late | 75 | 75 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Daily Status Call | Waheeba Khan | None | 2024-01-02 09:30 | 2024-01-15 19:00 | 2024-01-02 10:35 | Development | Yes | 0% | Furnishka - Zoho Books | Milestone Two-Zoho Books Improvisation Services | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 63 | Late | 77 | 77 | 10 | days
7.4981e+17 | Quotation Subform changes | Anusuyadevi V,Tanu Gupta | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-02 10:36 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121,790157522 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Client Script - Show alert while creating rate scheduler for non PMD deal | Ayush Singh | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 10:34 | Done | No | 100% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 1 | Late | 2 | 2 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Write Workflow And Validation For Training | Aaftab Ahmad | None | 2023-12-29 09:30 | 2024-01-02 19:00 | 2024-01-02 09:30 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 776475994 | 776475994 | 7 | Late | 12 | 12 | 3 | days |  | Clear | Waheeba Khan
7.4981e+17 | 1. The Lead type field should auto populate based on the lead layout selected | M S Satya | None | 2023-12-29 09:30 | 2023-12-29 19:00 | 2024-01-01 23:07 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 5 | Late | 6 | 6 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Addition of Fields in Zoho Books Invoice Template | Stuti S. Kulshrestha | None | 2024-03-15 09:30 | 2024-03-18 19:00 | 2024-03-15 18:41 | To Do | No | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | On Time | 4 | 4 | 2 | days
7.4981e+17 | MMT and Bulk Travel Vendor Flow Research | Stuti S. Kulshrestha | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 13:56 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Five-Implementation of Zoho Expense - Employee Expense & Claims / Reimbursements | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 3 | Late | 4 | 4 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Auto Populate data for all sub form of Type of Investor | Pavan S | None | 2024-03-16 19:47 | 2024-03-16 20:15 | 2024-03-16 19:46 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 845599619 | 845599619 | 2 | Late | 3 | 3 | 0.47 | hrs |  | Not Clear
7.4981e+17 | Internal Standup & Client Meeting For Trip | Mohammed Yusha | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 11:55 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 3 | Late | 4 | 4 | 1 | days |  | Clear
7.4981e+17 | KIH Project Reports | Ranjana Poojari | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 16:03 | In Progress | Yes | 0% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Vidya Vanam Signed Doc - SSF approval issue | Swetha K | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 11:09 | To Do | Yes | 0% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Expiration reminder schedulers and Email Notif | Mallesh M S | None | 2024-03-04 09:30 | 2024-03-18 19:00 | 2024-03-15 16:22 | Ready for QC | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 778475418 | 0 | On Time | 15 | 15 | 11 | days
7.4981e+17 | AWS architecture for Spring Boot porject | Anas Ahmed | None |  |  | 2024-03-15 10:32 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Develop Electronic Certification Payment System | Christ Bellarmine | High | 2024-03-14 09:30 | 2024-03-22 19:00 | 2024-03-16 02:17 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 | -4 | On Time | 5 | 5 | 7 | days
7.4981e+17 | Develop Output Report of CRM Data from Zoho | Dharanidharan C | High | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 21:04 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 701371504 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | 7 Day inactivity automation solution and Development | M S Satya | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 16:42 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 3 | Late | 4 | 4 | 1 | days |  | Clear
7.4981e+17 | Product Code Dynamic Population | Kalyanasundaram L | None | 2024-03-15 09:30 | 2024-03-27 19:00 | 2024-03-15 11:38 | To Do | No | 0% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Two-Zoho Creator – OrderManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | -9 | On Time | 4 | 4 | 9 | days |  | Clear
7.4981e+17 | Deals Module Changes need to work on Custom Function | Monik Chettiyar | None | 2024-03-15 19:00 | 2024-03-15 19:00 | 2024-03-15 10:14 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 3 | Late | 4 | 4 | 0 | days
7.4981e+17 | Validation for Approval configurator | Aishwarya T | None | 2024-03-15 09:30 | 2024-03-29 19:00 | 2024-03-15 18:27 | To Do | No | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | -11 | On Time | 4 | 4 | 11 | days |  | Clear | Sai Krishna
7.4981e+17 | Approval Configurator for PR for unfunded | Aishwarya T | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 16:11 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 3 | Late | 4 | 4 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Approval Configure for PR for estimated cost | Aishwarya T | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 12:14 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 3 | Late | 4 | 4 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Client Visit on 14-Mar-2024 | Vignesh R | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 19:21 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Digital and leads sheet preparations | Mary Nisha | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 17:31 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 4 | Late | 5 | 5 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | EHV Integration with Lead App | Anusha V | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 14:42 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | call on PAyroll | Kiran Shrivastav | None | 2024-03-06 09:30 | 2024-03-07 19:00 | 2024-03-14 15:31 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 11 | Late | 13 | 13 | 2 | days
7.4981e+17 | ZOHO BOOKS SEMINAR | Rishikesh Gogha | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 14:56 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Business Structure form populate upload fields based on user inputs | Pavan S | None | 2024-03-13 09:30 | 2024-03-13 13:00 | 2024-03-14 12:52 | Ready for QC | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 845599619 | 845599619 | 5 | Late | 6 | 6 | 3.5 | hrs |  | Not Clear | Selva Bharathi
7.4981e+17 | Watching Meeting Recording - Music School | Ayush Singh | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 17:33 | In Progress | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Create Rejection Chart Report with Re-Work Qty for all Locations | Sachin Patil | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 17:52 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Weekly status update call | Swetha K | None |  |  | 2024-03-14 16:39 | To Do | No | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 |  | On Time |  | 0 | 0 | days |  | Clear | Dharanidharan C
7.4981e+17 | Mastering Full-Stack Technology: Navigating the Full Spectrum | Avinash Sah | None |  |  | 2024-03-14 13:29 | In Progress | No | 10% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Spring boot models and database connection | Anas Ahmed | None |  |  | 2024-03-14 09:52 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | hespl AMC MARCH 2024 | Sai Krishna | None | 2024-03-01 09:30 | 2024-03-29 19:00 | 2024-03-14 09:30 | To Do | No | 0% | AMC - VAlign | HESPL AMC - 2023 - 24 | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | -11 | On Time | 18 | 18 | 21 | days
7.4981e+17 | KYC Form Validations | Anusha V | None | 2024-03-14 09:30 | 2024-03-18 19:00 | 2024-03-14 08:59 | To Do | No | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 0 | On Time | 5 | 5 | 3 | days
7.4981e+17 | Scrum Call WE 14.03 | Stuti S. Kulshrestha | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 09:02 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Webinar & Seminar | P Renuka Choudhary,Naveen M | None |  |  | 2024-03-14 10:59 | To Do | No | 0% | Sales Activities | None | 7.4981e+17 | 7.4981e+17 |  | 829366386 | 765907894829366386 |  | On Time |  | 0 | 0 | days |  | Not Clear
7.4981e+17 | Go Live (Corporate Users) | Christ Bellarmine | High | 2024-03-29 09:30 | 2024-03-29 19:00 | 2024-03-13 21:09 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 | -11 | On Time | -10 | -10 | 1 | days
7.4981e+17 | Meeting with Sourabh Multi SSF Apis - Mindspark Maths | Ayush Singh | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 09:07 | In Progress | Yes | 0% | AMC - VAlign | First Meridian - Start Date - 01-05-2023 and End Date - 30-04-2024 | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | RCM and Currency addition in the Vendor and Bills | Shavi Thakur | None | 2024-03-13 16:30 | 2024-03-14 15:00 | 2024-03-13 18:51 | To Do | Yes | 0% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Three-Order Management System | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 4 | Late | 6 | 6 | 8 | hrs |  | Clear | Mohammed Yusha
7.4981e+17 | Management & Controls | Subash Samuthirapandiyan | None |  |  | 2024-03-13 16:58 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 770263143 | 770263143 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Onsite Meeting | P Renuka Choudhary,Naveen M,Manish | None |  |  | 2024-03-13 17:19 | To Do | No | 0% | Sales Activities | None | 7.4981e+17 | 7.4981e+17 |  | 829366386 | 7.659078948293664E26 |  | On Time |  | 0 | 0 | days |  | Not Clear
7.4981e+17 | Item Creation - Import Templet & Import Option Required | Sachin Patil | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 15:47 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | CPL Issue for disabling fields& API Issues Call with Vendor Team | Anusha V | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 16:31 | In Progress | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | Sales Doc Preparation | P Renuka Choudhary,Naveen M | None |  |  | 2024-03-13 13:35 | To Do | No | 0% | Sales Activities | None | 7.4981e+17 | 7.4981e+17 |  | 829366386 | 765907894829366386 |  | On Time |  | 0 | 0 | days |  | Not Clear
7.4981e+17 | PAYROLL - RECRUIT Integration | Rishikesh Gogha | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 14:46 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Cancel Purchase Indents - Back Update Budget Value to Buget Master | Sachin Patil | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 12:40 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Payment Integration | Kalyanasundaram L | None | 2024-03-11 09:30 | 2024-03-12 19:00 | 2024-03-13 11:29 | Development Complete | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 819676542 | 6 | Late | 8 | 8 | 2 | days |  | Clear
7.4981e+17 | MOM Preparation for the previous calls (Appraisal setup call and New requirement discussion) | Kiran Shrivastav | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-03-13 09:25 | In Progress | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | In Order Sheet, Re-Calculate the Total Amount and Quantity to Main Form once Remove Item from Subform | Sachin Patil | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 15:04 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Dashboard | Tanu Gupta,Omprakash Kumar | High | 2024-03-12 09:30 | 2024-03-15 19:00 | 2024-03-12 12:43 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522845321609 | 3 | Late | 7 | 7 | 4 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Other Ownership Consideration | Subash Samuthirapandiyan | None |  |  | 2024-03-12 21:39 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 770263143 | 770263143 |  | On Time |  | 0 | 0 | days |  | Not Clear
7.4981e+17 | Tech Call / Daily With Kris | Selva Bharathi | None | 2024-03-02 09:30 | 2024-03-02 19:00 | 2024-03-12 17:53 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573 | 16 | Late | 17 | 17 | 1 | days
7.4981e+17 | Weekly Meeting | Monik Chettiyar | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 16:32 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Mark vendor as active else create and update | Swetha K | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 12:55 | To Do | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 6 | Late | 7 | 7 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | CRM Analysis | P Renuka Choudhary,Naveen M | None |  |  | 2024-03-13 13:29 | In Progress | No | 0% | Sales Activities | None | 7.4981e+17 | 7.4981e+17 |  | 829366386 | 765907894,829366386 |  | On Time |  | 0 | 0 | days |  | Not Clear
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-13 11:53 | To Do | Yes | 0% | Machani Dedicated Resource extension | Milestone One-Dedicated Resource for March 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Testing | Supril Jain | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 10:49 | Development | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Develop Bot to export data from Creator and upload to Catalyst | Prableen Kaur | None | 2024-04-01 09:30 | 2024-04-03 19:00 | 2024-03-12 19:17 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 792886644 | 792886644 | -16 | On Time | -13 | -13 | 3 | days
7.4981e+17 | Sales Activities | unassigned | None |  |  | 2024-03-12 15:44 | To Do | No | 0% | Sales Activities | None | 7.4981e+17 | 7.4981e+17 |  | 765907894 | - |  | On Time |  | 0 | 0 | days |  | Not Clear
7.4981e+17 | Internal Team Calls on issues in Porjects | Anusha V | None |  |  | 2024-03-12 12:45 | To Do | No | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Update the Account details in Quotation templates | Aishwarya T | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 14:54 | To Do | Yes | 0% | AMC - VAlign | Non AMC Project Tasks | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Kick off call Juspay - Zoho Desk & Sales IQ | Mohammed Yusha,Tanu Gupta | High | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 10:58 | In Progress | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Subform population for fare and stay in tour creation | Swetha K | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 09:29 | In Progress | Yes | 0% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Changes Requirement in Zoho CRM | Maninder Singh | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 17:28 | In Progress | Yes | 0% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Link the purchase order with vendor bill in books while getting created from creator | Aishwarya T | None | 2024-03-12 09:30 | 2024-03-14 19:00 | 2024-03-12 13:04 | Development Complete | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 4 | Late | 7 | 7 | 3 | days |  | Clear | Sai Krishna
7.4981e+17 | Proj Management Call (Confirmation of Resource Reallocation view) | Stuti S. Kulshrestha | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 14:54 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 1 | Late | 2 | 2 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Kick- Off Meeting & Requirement Document Preparation | Mohammed Yusha | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 12:06 | Discovery Phase | Yes | 0% | Juspay - Zoho Desk & Zoho SalesIQ - PA | Milestone Two-Implementation of Zoho SalesIQ & Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Management and Controls - Function Creation for Insert record - Recertification Process | Amrutha H V | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 11:29 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 778475418 | 845600661 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | Re: Zoho Expense issue: Rahul Shinde | Rishikesh Gogha | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 10:23 | To Do | Yes | 0% | AMC - VAlign | HESPL AMC - 2023 - 24 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Spot award Requirement Discussion | Kiran Shrivastav | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 18:24 | To Do | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Adding Reports to All Migrated Data | Kalyanasundaram L,Pavan S,Vikram Pai V | None | 2024-03-12 15:45 | 2024-03-12 17:15 | 2024-03-12 15:40 | Development Complete | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 845599619 | 819676542,845599619,845596686 | 6 | Late | 7 | 7 | 1.5 | hrs |  | Not Clear | Selva Bharathi
7.4981e+17 | Atlas Zoho Books Template Discussion. | Devaraju S J | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 16:08 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | Email Campaigns - Zoho Connect and Email and Collaboration | Deepa Hireholi | None |  |  | 2024-03-13 09:50 | To Do | No | 0% | V-Align Marketing Activites | None | 7.4981e+17 | 7.4981e+17 |  | 800651184 | 800651184 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Design & Develop Corp Plus | unassigned | None | 2024-03-12 09:30 | 2024-03-19 19:00 | 2024-03-12 21:19 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | - | -1 | On Time | 7 | 7 | 6 | days
7.4981e+17 | Dashboard Changes and Service Tickets | Achyuth T M | None | 2024-03-07 09:30 | 2024-03-15 19:00 | 2024-03-12 10:58 | In Progress | Yes | 10% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 3 | Late | 12 | 12 | 7 | days |  | Clear
7.4981e+17 | Client Meeting - Quote Management | Mohammed Yusha,Tanu Gupta | High | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 11:09 | Discovery Phase | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Order Cancellation and automation using custom API and API Documentation creation for same | Vaikuntam Chowdary | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 09:32 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Auto checkout issue | Kiran Shrivastav | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 09:53 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Stock Adjustment, Sync Stock Adjustment to Book with Unit Rate | Sachin Patil | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 10:40 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Digital Campaign Module Workflow Check | Dharanidharan C | None | 2024-03-06 09:30 | 2024-03-07 19:00 | 2024-03-11 19:22 | To Do | Yes | 0% | Right Horizons Financial Services Pvt Ltd. - Zoho CRM, Creator, Analytics | None | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 11 | Late | 13 | 13 | 2 | days
7.4981e+17 | Customer Question | Devaraju S J | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 18:44 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Weekly Stand Up Call with client | Siddharth Sharma | None |  |  | 2024-03-11 14:50 | To Do | No | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Going through RPA basics from online resources | Vikram Pai V | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 09:42 | To Do | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 845596686 | 845596686 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Delta data migration of Wave1 council | Prableen Kaur | None | 2024-04-19 09:30 | 2024-04-22 19:00 | 2024-03-11 17:41 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | -35 | On Time | -31 | -31 | 2 | days
7.4981e+17 | Vendor Management feedback call with client 11-Mar-2023 | Sai Krishna,Aishwarya T,Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 14:10 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779,772989157,808004288,844784545 | 7 | Late | 8 | 8 | 1 | days |  | Clear
7.4981e+17 | Create Walkthrough of CRM | Dharanidharan C | None | 2024-03-12 09:30 | 2024-03-18 19:00 | 2024-03-12 04:24 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 701371504 | 0 | On Time | 7 | 7 | 5 | days
7.4981e+17 | Juspay ¦ Zoho Creator ¦ User setup in VMS | Tanu Gupta | High | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 16:29 | In Progress | Yes | 0% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | AMC-COA Import | Shiwani Kumari | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 10:03 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Zoho Payroll ¦ Employees Portal Error | Monik Chettiyar | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 17:10 | To Do | Yes | 0% | AMC - VAlign | FARM INDIA IMPEX ¦ Books, Creator, People, Payroll & Analytics ¦ 8-12-23 to 7-12-24 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Native Account De-Duplication | Supril Jain | None | 2024-03-11 09:30 | 2024-03-12 19:00 | 2024-03-11 15:30 | In Progress | Yes | 0% | AMC - VAlign | OSBORN LIPPERT INDIA PVT. LTD. - Zoho CRM ¦ 19-05-2023 ¦ 18-05-2024 | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 6 | Late | 8 | 8 | 2 | days
7.4981e+17 | Establish User Roles & Permissions for full staff | Dharanidharan C,Hiren Vakharia | None | 2024-03-11 09:30 | 2024-03-15 19:00 | 2024-03-11 14:24 | In Progress | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504,811424903 | 3 | Late | 8 | 8 | 5 | days
7.4981e+17 | Member Renewal Invoice Validation | Dharanidharan C | None | 2024-03-11 19:00 | 2024-03-15 19:00 | 2024-03-11 14:10 | To Do | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 3 | Late | 8 | 8 | 4 | days
7.4981e+17 | UAT changes suggested by Supreeth | Pavan S | None |  |  | 2024-03-11 12:19 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 845599619 | 845599619 |  | On Time |  | 0 | 0 | days |  | Not Clear
7.4981e+17 | Tax Query of Vikas - Zoho Expense Approval and Tax issue | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 11:13 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Five-Implementation of Zoho Expense - Employee Expense & Claims / Reimbursements | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288,844784545 | 3 | Late | 4 | 4 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Solutioning failure cases - Master Custom API | Anusuyadevi V | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 09:28 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Migration of Wave 1 Council Document to Zoho | Prableen Kaur,Kalyanasundaram L | None | 2024-03-19 09:30 | 2024-03-20 19:00 | 2024-03-08 19:50 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 792886644,819676542 | -2 | On Time | 0 | 0 | 2 | days
7.4981e+17 | Wishlist feature testing and Release | Selva Bharathi | None |  |  | 2024-03-08 16:41 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 701368573 | 701368573 |  | On Time |  | 0 | 0 | days |  | Not Clear
7.4981e+17 | Multi SSF in OMS V2 | Ayush Singh | None |  |  | 2024-03-11 10:01 | In Progress | No | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Order cancellation automations and DN, CN Zoho books to Zoho creator integration | Vaikuntam Chowdary | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 10:56 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Rectify phone number exceptions from source data | Vikram Pai V | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 16:30 | To Do | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 845596686 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Sending Invites to the MBEs | Kalyanasundaram L | None | 2024-03-08 09:30 | 2024-03-14 19:00 | 2024-03-10 19:33 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 4 | Late | 11 | 11 | 5 | days |  | Clear | Selva Bharathi
7.4981e+17 | Legal Workflow Issue | Ranjana Poojari | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 13:17 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Create Step by Step Training Document for Internal Trainer | Dharanidharan C | None | 2024-03-01 09:30 | 2024-03-13 19:00 | 2024-03-10 09:07 | In Progress | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 701371504 | 5 | Late | 18 | 18 | 9 | days
7.4981e+17 | Search Enhancement 2 (Features-------------------) | Christ Bellarmine | None |  |  | 2024-03-10 08:44 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Create Comms Method for Service Interruptions or Enhancements to Active Users | Christ Bellarmine | None | 2024-03-08 09:30 | 2024-03-15 19:00 | 2024-03-08 21:13 | To Do | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 | 3 | Late | 11 | 11 | 6 | days
7.4981e+17 | Women's Day Team Catchup & Digital Celebration | Stuti S. Kulshrestha | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 17:13 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Requirement Gathering and Discussions | Aman Kumar | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 12:53 | To Do | Yes | 0% | Sales Activities | None | 7.4981e+17 | 7.4981e+17 |  | 839251991 | 839251991 | 7 | Late | 8 | 8 | 1 | days |  | Clear
7.4981e+17 | Technical Discussion regarding PhonePe Integration with support team | Dharanidharan C,Sai Krishna,Tanu Gupta | High | 2024-03-11 09:30 | 2024-03-13 19:00 | 2024-03-11 11:03 | In Progress | Yes | 10% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701371504,753339779,790157522 | 5 | Late | 8 | 8 | 3 | days |  | Clear | Dharanidharan C
7.4981e+17 | Internal Discussion | Vignesh R | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 18:32 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 10 | Late | 11 | 11 | 1 | days |  | Clear
7.4981e+17 | Date of Confirmation Task to write Cutom Fucntion | Monik Chettiyar | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 14:15 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Service Tickets | Dharanidharan C,Mary Nisha | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 13:29 | In Progress | Yes | 10% | TMSB - Next-Gen Learning Transformation with Zoho Creator Enhancement | Milestone Two- Zoho Creator Existing system improvisation | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504,775643568 | 10 | Late | 11 | 11 | 1 | days |  | Clear
7.4981e+17 | Research on Zoho Books Queries | Stuti S. Kulshrestha | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 12:03 | Discovery Phase | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Set of Branches and Sales Receipts | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 09:55 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288,844784545 | 10 | Late | 11 | 11 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Validate Data Migrated for Wave1 & RMSDC | Constance Jones | None | 2024-03-21 09:30 | 2024-03-23 19:00 | 2024-03-07 22:06 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 811824790 | -5 | On Time | -2 | -2 | 3 | days
7.4981e+17 | Develop Script to get Exception Report for Missing Documents | Christ Bellarmine,Prableen Kaur | None | 2024-03-07 09:30 | 2024-03-08 19:00 | 2024-03-07 21:54 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486,792886644 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Confirm Data Mapping with field-level Validation | Kris Oswold | None | 2024-03-07 09:30 | 2024-03-08 19:00 | 2024-03-07 21:44 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 824545238 | 3 | Late | 5 | 5 | 2 | days
7.4981e+17 | References Section-Dynamic | Aman Kumar | None |  |  | 2024-03-07 20:37 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Business Information Section-Dynamic | Aman Kumar | None |  |  | 2024-03-07 20:33 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | For fellow extensions- we need to get a letter triggered for every extension form that is submitted | Kiran Shrivastav | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-03-08 09:30 | To Do | Yes | 0% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Process document for creating new category type in Bank Statement, Projects, Events,Legder | Tanu Gupta | High | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-07 14:23 | In Progress | Yes | 10% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 10 | Late | 11 | 11 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Project Initialization - Attachments & QA | Tanu Gupta | High | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 14:09 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 7 | Late | 8 | 8 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Client meetings | Supreeth R Kalluraya | None | 2024-03-08 09:30 | 2024-03-29 19:00 | 2024-03-08 13:04 | In Progress | No | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 788577227 | 788577227 | -11 | On Time | 11 | 11 | 16 | days |  | Clear
7.4981e+17 | Zoho CRM Quotes Module In words Error | Monik Chettiyar | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 10:43 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Hiding Unwanted Fields in the all the sub forms in the Application Forms | Kalyanasundaram L,Amrutha H V | None | 2024-03-07 09:30 | 2024-03-08 19:00 | 2024-03-08 09:43 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 819676542,845600661 | 10 | Late | 12 | 12 | 2 | days |  | Clear | Selva Bharathi
7.4981e+17 | Changing Save and Update Button Name to save as Draft and Hide Cancel and Reset Button | Kalyanasundaram L,Pavan S | None |  |  | 2024-03-08 09:29 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 819676542,845599619 |  | On Time |  | 0 | 0 | days |  | Clear | Selva Bharathi
7.4981e+17 | Dashboard page according to the Role | Swetha K | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 18:29 | To Do | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 11 | Late | 12 | 12 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Develop script and create exception reports for Decision makers, Management, Subsidiary, Annual Revenue | Pannaga H | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 12:19 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 792886644 | 795342015 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Ownership Details: Individials | Subash Samuthirapandiyan | None |  |  | 2024-03-07 20:02 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 770263143 | 770263143 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | General Information | Subash Samuthirapandiyan | None |  |  | 2024-03-07 19:59 | Ready for QC | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 770263143 | 770263143 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Report Fesiability Check | M S Satya | None | 2024-03-07 09:30 | 2024-03-08 19:00 | 2024-03-07 15:10 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 10 | Late | 12 | 12 | 2 | days |  | Clear
7.4981e+17 | support on CRM application FOr Quotes Moduele | Monik Chettiyar | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-07 12:21 | Done | No | 100% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Duplicate tickets landing on Customer Support Team Since - 05 March | Ayush Singh | None |  |  | 2024-03-07 12:13 | In Progress | No | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Presentation Practice with CEO/S | Shiwani Kumari | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-08 10:32 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Region Fields creation in Books and update from CRM to books | Ayush Singh | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 19:31 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 11 | Late | 12 | 12 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Meeting with Sourabh Multi SSF Apis | Ayush Singh | None |  |  | 2024-03-07 19:12 | In Progress | No | 0% | AMC - VAlign | First Meridian - Start Date - 01-05-2023 and End Date - 30-04-2024 | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 |  | On Time |  | 0 | 0 | days
7.4981e+17 | SO Bonded chnges after Demo(06/03) | Ranjana Poojari,Anusha V | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-03-08 12:16 | In Progress | Yes | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 778475421,795545761 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Creation of Request Payload and update in Master's Document | Anusuyadevi V | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 09:29 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Zoho Desk Discussion with Stellar Team | Sachin Patil | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-07 17:37 | To Do | Yes | 0% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Test Case Document for Incoming Payments | Anusuyadevi V | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 15:28 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Analytics Dashboard Points shared | Anusha V | High | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 12:20 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | Working On Edit New Customer Module Request | unassigned | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 10:08 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 840979277 | - | 11 | Late | 12 | 12 | 1 | days |  | Clear
7.4981e+17 | #6020 International Territory Concerns | Tanu Gupta | High | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 20:53 | Done | No | 100% | AMC - VAlign | HAPPY RELIABLE SURGERIES PRIVATE LIMITED - Zoho CRM and Zoho Form ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Issue for run down branch and null target | Tanu Gupta | High | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 20:39 | In Progress | Yes | 10% | IIFL Samasta Zoho Creator Score Card Enhancement | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 12 | Late | 13 | 13 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Write script to merge all Supplier and Application files | Vikram Pai V | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-06 12:59 | To Do | Yes | 0% | iDATALYTCS UI PATH | None | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 845596686 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | CRM & Books Integration Flow | Stuti S. Kulshrestha | None | 2024-03-13 09:30 | 2024-03-15 19:00 | 2024-03-06 19:45 | Discovery Phase | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 3 | Late | 6 | 6 | 3 | days
7.4981e+17 | Client call regarding approval and creator access issue | Mohammed Yusha,Shavi Thakur,Tanu Gupta | High | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 14:32 | In Progress | Yes | 0% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,773081417,790157522 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | R&D , Zoho Support | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-06 09:30 | 2024-03-07 19:00 | 2024-03-06 13:21 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Five-Implementation of Zoho Expense - Employee Expense & Claims / Reimbursements | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288,844784545 | 11 | Late | 13 | 13 | 2 | days |  | Clear
7.4981e+17 | Surya Enterprise KT | M S Satya | None | 2024-03-04 09:30 | 2024-03-08 19:00 | 2024-03-06 10:02 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 10 | Late | 15 | 15 | 5 | days |  | Clear
7.4981e+17 | Solutioning Custom API | Anusuyadevi V | None | 2024-03-06 09:30 | 2024-03-07 19:00 | 2024-03-06 10:30 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 3 | 3 | 2 | days
7.4981e+17 | KRA Adding | Kiran Shrivastav | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 09:30 | Done | No | 100% | AMC - VAlign | Neelgund Project Zoho HRMS Implementation | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | the highest and lowest selling products for the current month, current year, and provides a comparison between the current month and the previous month's sales. | Nikita Srivastava | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 12:58 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Multiple PO Hyperlink to be associated with Invoices | Rishikesh Gogha | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-06 10:10 | Done | No | 100% | AMC - VAlign | DEFSPACE_AMC_Zoho Books_09-02-2024 to 08-02-2025 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Video manuals | Rishikesh Gogha | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-06 09:48 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | demo and clarification call | Swetha K | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 18:50 | To Do | Yes | 0% | IIFL SAMASTA- Admin Module CR | Milestone One-Advance payment for Admin Module Change Request | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Report for Deals and SOW | Aishwarya T | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 16:27 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 12 | Late | 13 | 13 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-26 09:30 | 2024-03-15 19:00 | 2024-03-06 13:29 | Done | No | 100% | Machani Dedicated Resource extension | Milestone One-Dedicated Resource for March 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | -4 | On Time | 15 | 15 | 15 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-26 09:30 | 2024-03-15 19:00 | 2024-03-06 13:29 | Done | No | 100% | Machani Dedicated Resource extension | Milestone One-Dedicated Resource for March 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | -4 | On Time | 15 | 15 | 15 | days
7.4981e+17 | Work on, Converting to material consumption, Finalize material consumption and Canceling | Sachin Patil | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 09:39 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 12 | Late | 13 | 13 | 1 | days |  | Clear
7.4981e+17 | MBE search Catalyst code walk through | Anas Ahmed | None |  |  | 2024-03-05 17:06 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | MBE_Search_API | Omprakash Kumar | None | 2024-02-12 09:30 | 2024-02-13 19:00 | 2024-03-05 13:50 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 845321609 | 845321609 | 21 | Late | 23 | 23 | 2 | days
7.4981e+17 | iterations (If any) | Selva Bharathi,Supreeth R Kalluraya | None | 2024-03-29 09:30 | 2024-04-02 19:00 | 2024-03-04 21:35 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573,788577227 | -15 | On Time | -10 | -10 | 3 | days
7.4981e+17 | Reports Layouts | Pavan S | None | 2024-03-04 09:30 | 2024-04-03 19:00 | 2024-03-04 21:35 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 845599619 | -16 | On Time | 15 | 15 | 23 | days
7.4981e+17 | Development of reports required for Application Submission | Mallesh M S | None | 2024-03-12 09:30 | 2024-03-16 19:00 | 2024-03-04 21:35 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 778475418 | 2 | Late | 7 | 7 | 5 | days
7.4981e+17 | Integation of Zoho Creator with payment portal | Kalyanasundaram L | None | 2024-03-02 09:30 | 2024-03-05 19:00 | 2024-03-04 21:35 | Development Complete | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 819676542 | 13 | Late | 17 | 17 | 3 | days
7.4981e+17 | Integration of backend with Zoho Sign | Kalyanasundaram L | None | 2024-03-02 09:30 | 2024-03-02 19:00 | 2024-03-04 21:35 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 819676542 | 16 | Late | 17 | 17 | 1 | days
7.4981e+17 | Configure validation rules rules of Field Level for application form | Subash Samuthirapandiyan,Kalyanasundaram L | None | 2024-03-11 09:30 | 2024-03-13 19:00 | 2024-03-04 21:35 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 770263143,819676542 | 5 | Late | 8 | 8 | 3 | days
7.4981e+17 | Completion of Validation Rules for Application Form | Subash Samuthirapandiyan | None | 2024-03-02 09:30 | 2024-03-02 19:00 | 2024-03-04 21:35 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 770263143 | 16 | Late | 17 | 17 | 1 | days
7.4981e+17 | Client call -call with Ashwini for user roles & Permissions explaination | Tanu Gupta | High | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-06 09:24 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | ZOHO Expenses Training-D | Devaraju S J | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 18:40 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | User Permission Excel for Zoho Projects | Shavi Thakur | None | 2024-03-04 16:30 | 2024-03-04 19:00 | 2024-03-04 23:06 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 0 | Late | 1 | 1 | 2.5 | hrs
7.4981e+17 | Check working of Invoice Main Form Cancel | Sachin Patil | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 19:40 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | Zoho expense training | Shiwani Kumari | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 16:48 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Feasibility check for Job Requisition Form | Kiran Shrivastav | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 20:21 | Done | No | 100% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Support request : Export Access Required | Kiran Shrivastav | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 16:48 | Done | Yes | 10% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 14 | Late | 15 | 15 | 1 | days |  | Clear
7.4981e+17 | HESPL AMC Feb -24 | Sai Krishna | None | 2024-02-01 09:30 | 2024-02-29 19:00 | 2024-03-04 14:22 | Done | No | 100% | AMC - VAlign | HESPL AMC - 2023 - 24 | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 4 | Late | 33 | 33 | 21 | days
7.4981e+17 | Demo preparation for Mispa - Zoho Recruit | Kiran Shrivastav | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 12:30 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Intimation email to previous user | Swetha K | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 09:30 | Done | No | 100% | IIFL SAMASTA- Admin Module CR | Milestone One-Advance payment for Admin Module Change Request | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | ZOHO Expenses-D | Devaraju S J | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 18:50 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Going through codebase and running locally the catalyst codebase | Mohak Tripathi | None |  |  | 2024-03-06 18:37 | In Progress | No | 10% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 843614429 | 843614429 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Overview of vendor management TSD of CEEW/S | Shiwani Kumari | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 19:04 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Payment Received Status Back update to Creator | Shavi Thakur | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 23:20 | To Do | Yes | 0% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Four-Financial Accounting Management System | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 14 | Late | 15 | 15 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Creation of UI | unassigned | None |  |  | 2024-03-05 13:33 | In Progress | No | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 845321609 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Knowledge Transfer of AWS and Catalyst build MBE Search Project. | Mohak Tripathi | None |  |  | 2024-03-05 13:18 | In Progress | No | 10% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 |  | 843614429 | 843614429 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | MBE search for Text | Anas Ahmed | None |  |  | 2024-03-05 10:25 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | If a customer responds to a closed ticket, the ticket will be reopened | Sachin Patil | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 19:30 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Update UOM and Unit Price to Zoho Creator Inventory Items form Item Master | Sachin Patil | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 19:20 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 13 | Late | 14 | 14 | 1 | days |  | Clear
7.4981e+17 | Testing of flow from project discovery till approval | Mohammed Yusha,Tanu Gupta | None | 2024-03-04 09:30 | 2024-03-05 19:00 | 2024-03-05 12:30 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 13 | Late | 15 | 15 | 2 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Expense Req Gathering | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 11:06 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Five-Implementation of Zoho Expense - Employee Expense & Claims / Reimbursements | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288,844784545 | 2 | Late | 3 | 3 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | 20. The number of fraud reported during current financial year should auto populate based on the branch | Swetha K | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-05 09:56 | Done | No | 100% | IIFL SAMASTA - IMS Enhancement 3.5 | Milestone Two-Zoho Creator: Customization, Configuration, Testing and Go-Live of IMS enhancement | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Discovery Session 1 | Stuti S. Kulshrestha | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-05 09:21 | Done | No | 100% | FarmIndia_Zoho One | Milestone Three-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Overview of NGO/S | Shiwani Kumari | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 19:03 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Opening Balance Meeting -D | Devaraju S J | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 19:00 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | BA testing for Update requested | unassigned | None | 2024-03-01 09:30 | 2024-03-30 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | - | -12 | On Time | 18 | 18 | 22 | days
7.4981e+17 | Creation of update requested workflow | Twinkle Gupta | None | 2024-03-22 09:30 | 2024-03-27 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -9 | On Time | -3 | -3 | 4 | days
7.4981e+17 | BA Testing of Desk Audit Process | Supreeth R Kalluraya | None | 2024-03-01 09:30 | 2024-03-29 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 788577227 | -11 | On Time | 18 | 18 | 21 | days
7.4981e+17 | Validation for sending update request to BEs | Twinkle Gupta | None |  |  | 2024-03-04 21:27 | In Progress | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Validation for mode of interview allocation matrix | Twinkle Gupta | None | 2024-03-21 09:30 | 2024-03-22 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -4 | On Time | -2 | -2 | 2 | days
7.4981e+17 | Validation for mode of interview allocation matrix | Twinkle Gupta | None | 2024-03-20 09:30 | 2024-03-20 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -2 | On Time | -1 | -1 | 1 | days
7.4981e+17 | Completion of Assessment form (MBE,MCC,IFCP) And Automations | Twinkle Gupta | None | 2024-03-14 09:30 | 2024-03-15 19:00 | 2024-03-04 21:27 | Development Complete | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | 3 | Late | 5 | 5 | 2 | days
7.4981e+17 | Document Wise Approval And Rejection, Status Updates | Twinkle Gupta | None | 2024-03-06 09:30 | 2024-03-11 19:00 | 2024-03-04 21:27 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | 7 | Late | 13 | 13 | 4 | days
7.4981e+17 | Option for commenting, Status Update, View Old Inputs | Twinkle Gupta | None | 2024-03-08 19:00 | 2024-03-08 19:00 | 2024-03-04 21:27 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | 10 | Late | 11 | 11 | 0 | days
7.4981e+17 | Completion of Assessment form (MBE,MCC,IFCP) And Automations | Twinkle Gupta | None | 2024-03-06 09:30 | 2024-03-14 19:00 | 2024-03-04 21:27 | Development Complete | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | 4 | Late | 13 | 13 | 7 | days
7.4981e+17 | Audit Log Function | Aman Kumar | None | 2024-03-11 09:30 | 2024-03-12 19:00 | 2024-03-04 21:27 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 839251991 | 6 | Late | 8 | 8 | 2 | days
7.4981e+17 | development of allocation skill matrix of the application | Selva Bharathi,Aman Kumar | None | 2024-03-07 09:30 | 2024-03-08 19:00 | 2024-03-04 21:27 | Development Complete | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573,839251991 | 10 | Late | 12 | 12 | 2 | days
7.4981e+17 | Internal Team Catchup | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-06 09:30 | 2024-03-15 19:00 | 2024-03-06 09:45 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288,844784545 | 3 | Late | 13 | 13 | 8 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Internal meeting with Stuti/S | Shiwani Kumari | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 19:22 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Zoho Books to Zoho Creator Integration of VC,CN and Invoice | Vaikuntam Chowdary | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-05 09:27 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Show actual available capacity in a task | Vignesh R | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 17:23 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 14 | Late | 15 | 15 | 1 | days |  | Clear
7.4981e+17 | Page for Vendor Bill | Aishwarya T | None | 2024-03-01 09:30 | 2024-03-12 19:00 | 2024-03-04 12:27 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 2 | Late | 14 | 14 | 8 | days |  | Clear | Sai Krishna
7.4981e+17 | Department creation in New Branch under Zoho people | Kiran Shrivastav | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 11:00 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Integrate Zoho People Employee Module With Zoho Creator Emplyee Module | Shavi Thakur | None | 2024-03-01 11:30 | 2024-03-01 15:00 | 2024-03-03 21:24 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 3 | Late | 4 | 4 | 3.5 | hrs
7.4981e+17 | Byron Support Request March | M S Satya | None | 2024-03-01 09:30 | 2024-03-31 19:00 | 2024-03-04 08:58 | In Progress | No | 0% | AMC - VAlign | Byron Medical Pty Ltd ¦ Zoho One ¦ 01-10-2023 ¦ 30-09-2024 | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | -13 | On Time | 18 | 18 | 22 | days
7.4981e+17 | NAICS Redesign Functionality | Avinash Sah | None |  |  | 2024-02-29 18:18 | In Progress | No | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | FY population | Swetha K | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 09:30 | Done | No | 100% | IIFL SAMASTA - IMS Enhancement 3.5 | Milestone Two-Zoho Creator: Customization, Configuration, Testing and Go-Live of IMS enhancement | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | If GRN is in Open stage and user trying to create the New GRN then it will opens in Edit mo de and **DO Not create a New GRN**If GRN Closed PO Balance Qty will update (PO Bl Qty = PO Bl Qty - Qty), It will create GRN if qty is greater than 0 | Aishwarya T | None | 2024-02-29 09:30 | 2024-03-02 19:00 | 2024-03-01 10:36 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 5 | Late | 8 | 8 | 3 | days |  | Clear | Sai Krishna
7.4981e+17 | Grn to vendor bill, if the grn is marked as closed, vendor bill needs to be created with the grn line items | Aishwarya T | None | 2024-02-27 09:30 | 2024-02-29 19:00 | 2024-03-01 10:29 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 7 | Late | 10 | 10 | 3 | days |  | Clear | Sai Krishna
7.4981e+17 | Validation in purchase requisition form so that duplicate items cannot be selected in product details subform (With Alert Msg) , and Move Preferred vendor field to last in product details subform in purchase requisition form | Sai Krishna,Aishwarya T | None | 2024-02-27 09:30 | 2024-02-29 19:00 | 2024-03-01 10:22 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 7 | Late | 10 | 10 | 3 | days |  | Clear | Sai Krishna
7.4981e+17 | MBE Search | unassigned | None |  |  | 2024-02-29 16:41 | In Progress | No | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 843614429 | - |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | All Hands Meeting 01/03/2024 | Stuti S. Kulshrestha | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-01 18:06 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Check Books Integration of Bills, Bill Payments , Invoices, Debit Note and Credit Notes. | Vignesh R,Basavaraj Patil | None | 2024-02-28 09:30 | 2024-03-05 19:00 | 2024-03-01 16:56 | In Progress | Yes | 10% | Atlas - Zoho Creator - P & I, And OMS | None | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 704175602,781564441 | 13 | Late | 20 | 20 | 5 | days |  | Clear | Waheeba Khan
7.4981e+17 | UAT release 1 bug fixes | Dharanidharan C | None | 2024-02-01 09:30 | 2024-02-29 19:00 | 2024-03-01 12:41 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 18 | Late | 47 | 47 | 21 | days |  | Clear
7.4981e+17 | UAT release 1 and updates | Dharanidharan C | None | 2024-02-01 09:30 | 2024-02-29 19:00 | 2024-03-01 12:39 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 18 | Late | 47 | 47 | 21 | days |  | Clear
7.4981e+17 | FLOW CHART | Rishikesh Gogha | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-03-04 10:06 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Issue in ticket creation, invoice download, contact sync between crm & desk | Tanu Gupta | High | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-02 15:53 | Done | No | 100% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 2 | 2 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Update UOM to Creator Item Master from Zoho Books Items | Sachin Patil | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-01 19:39 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 17 | Late | 18 | 18 | 1 | days |  | Clear
7.4981e+17 | Document mapping- RMSDC | Prableen Kaur | None | 2024-02-28 09:30 | 2024-03-28 19:00 | 2024-03-01 17:31 | To Do | No | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | -10 | On Time | 20 | 20 | 22 | days
7.4981e+17 | Zoho Books to Zoho CRM Custom Module | Monik Chettiyar | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 20:28 | Done | No | 100% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Client Visit on 29-Feb-2024 | Vignesh R | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 18:44 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 18 | Late | 19 | 19 | 1 | days
7.4981e+17 | Purchase Module & Books Integration | unassigned | None | 2024-03-01 09:30 | 2024-03-04 19:00 | 2024-03-01 20:08 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Three-Order Management System | 7.4981e+17 | 7.4981e+17 |  | 701373265 | - | 0 | Late | 4 | 4 | 2 | days |  | Clear
7.4981e+17 | Quotation serial number to be separated in deal module to use as ascending or descending order views : Feasiblity check | M S Satya | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-03-01 09:39 | To Do | Yes | 0% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 18 | Late | 19 | 19 | 1 | days |  | Clear
7.4981e+17 | Zoho Books - Requirement Gathering - FinBook | Tanu Gupta | High | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 21:41 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Sequence no. for PO, PR | Sai Krishna,Aishwarya T | None | 2024-02-26 09:30 | 2024-02-29 19:00 | 2024-02-29 13:20 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 7 | Late | 11 | 11 | 4 | days |  | Clear | Sai Krishna
7.4981e+17 | Task details preparation and Sharing | Kiran Shrivastav | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-01 09:41 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | Implementing Copy Paste on drop down search input | Anas Ahmed | None |  |  | 2024-02-29 19:39 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | NAICS drop down search functionality and UI | Anas Ahmed | None |  |  | 2024-02-29 19:34 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Data table handling with UI and export | Anas Ahmed | None |  |  | 2024-02-29 19:30 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | UI creation for basic tree structure | Anas Ahmed | None |  |  | 2024-02-29 19:05 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | None | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | File handling in Redux for Business info (main page) and Level 1 of Tree Structure | Anas Ahmed | None |  |  | 2024-02-29 18:49 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | UI for Level 2 - Tree Structure | Anas Ahmed | None |  |  | 2024-02-29 18:43 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Report Schedular and call with jyothi for check-in/out report | Kiran Shrivastav | None | 2024-02-28 09:30 | 2024-02-29 19:00 | 2024-02-29 18:35 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 18 | Late | 20 | 20 | 2 | days
7.4981e+17 | HQ location basis attendance Report | Kiran Shrivastav | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-02-29 14:21 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 19 | 19 | 2 | days
7.4981e+17 | Appraisee view not available in iphone | Kiran Shrivastav | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-02-29 14:21 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 19 | 19 | 2 | days
7.4981e+17 | Second shift attendance issue is not resolved (pending since more than 2 months) | Kiran Shrivastav | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-02-29 14:18 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 19 | 19 | 2 | days
7.4981e+17 | Inventory Selection Layout Rules | Supril Jain | None | 2024-02-28 09:30 | 2024-03-05 19:00 | 2024-02-29 09:44 | Development | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 13 | Late | 20 | 20 | 5 | days
7.4981e+17 | Territory Management UAT Feedback | Siddharth Sharma | None | 2024-02-19 09:30 | 2024-03-01 19:00 | 2024-02-29 09:17 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | Milestone Two-Implementation of Zoho CRM - Sales & Service Management Application | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 | 17 | Late | 29 | 29 | 10 | days |  | Clear
7.4981e+17 | Zoho Books UAT Discussion Meeting | Shavi Thakur | None | 2024-02-28 14:30 | 2024-02-28 16:30 | 2024-02-28 22:20 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Four-Financial Accounting Management System | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 0 | Late | 1 | 1 | 2 | hrs |  | Clear | Mohammed Yusha
7.4981e+17 | Req Discovery Session 2 | Stuti S. Kulshrestha | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 17:08 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 8 | Late | 9 | 9 | 1 | days |  | Clear
7.4981e+17 | UAT Points and query resolution | M S Satya | None |  |  | 2024-02-28 09:53 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Demo Checkmate Functionality | Christ Bellarmine | None | 2024-02-27 09:30 | 2024-03-05 19:00 | 2024-02-27 23:03 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 | 2 | Late | 10 | 10 | 6 | days
7.4981e+17 | Create a Custom button in Books to redirect to Zoho Creator | Shavi Thakur | None | 2024-02-26 13:30 | 2024-02-26 16:00 | 2024-02-26 18:31 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 0 | Late | 1 | 1 | 2.5 | hrs
7.4981e+17 | Fesiability Check | unassigned | None |  |  | 2024-02-26 21:27 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Zoho Creator - New Requirement for Visa & Immigration Services | Tanu Gupta | High | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 19:28 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 21 | Late | 22 | 22 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | UAT Feedback & Improvizations | Shavi Thakur,Tanu Gupta | High | 2024-02-28 09:30 | 2024-02-29 19:00 | 2024-02-26 19:08 | To Do | Yes | 0% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 773081417,790157522 | 18 | Late | 20 | 20 | 2 | days
7.4981e+17 | Workflow Automations | Shavi Thakur,Tanu Gupta | High | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-26 19:03 | Done | No | 100% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 773081417,790157522 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Internal Meeting | Devaraju S J | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 18:28 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | User Training for sales team | Rishikesh Gogha | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-29 09:45 | To Do | Yes | 0% | Airowire - Zoho Expense | None | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Vendor Master, Invoice & Bills Books Integration | Vaikuntam Chowdary | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-28 19:08 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | Ledger Block and Payment Object Changes and API document creation | Vaikuntam Chowdary | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 18:55 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Issue Resolution | Siddharth Sharma | None |  |  | 2024-02-28 09:26 | To Do | No | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | OBD CALL | Nikita Srivastava | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-27 18:16 | In Progress | Yes | 0% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | PMD ICAC and CCO Template updations and corrections | Mary Nisha | High | 2024-02-26 09:30 | 2024-02-27 19:00 | 2024-02-26 16:01 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 20 | Late | 22 | 22 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | terms clarification ¦ Investment Declaration | Rishikesh Gogha | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 10:55 | To Do | Yes | 0% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Re: Not able to submit the report | Rishikesh Gogha | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-28 09:35 | To Do | Yes | 0% | AMC - VAlign | HESPL AMC - 2023 - 24 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Split payments response and insert into Incoming Payments and auto allocate customer | Anusuyadevi V | None | 2024-02-27 09:30 | 2024-02-28 19:00 | 2024-02-28 09:28 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Client Meeting Zoho CRM and Books Issue & Development Time | Monik Chettiyar | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-27 19:18 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Job Requisition Form Customization | Kiran Shrivastav | None | 2024-02-27 09:30 | 2024-03-08 19:00 | 2024-02-27 18:53 | To Do | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 10 | Late | 21 | 21 | 9 | days
7.4981e+17 | Study on Endpoint creation in zoho creator and reaching out support for solutioning | Anusuyadevi V | None | 2024-02-23 09:30 | 2024-02-26 19:00 | 2024-02-27 09:23 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 5 | 5 | 2 | days
7.4981e+17 | Internal Team Catchup | Stuti S. Kulshrestha | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 11:16 | Done | No | 100% | FarmIndia_Zoho One | Milestone Three-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Satya KT | unassigned | None |  |  | 2024-02-29 09:01 | To Do | No | 0% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 789497933 | - |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Payment Received Import in ZOHO Books and Data Validation | Ayush Singh | None | 2024-02-28 09:30 | 2024-02-29 19:00 | 2024-02-28 18:38 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 18 | Late | 20 | 20 | 2 | days |  | Clear
7.4981e+17 | Progress Demo & Timesheet File | Mohammed Yusha,Tanu Gupta | High | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 15:22 | Done | No | 100% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Shift/Schedule template functions | Mary Nisha | High | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-27 15:01 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 20 | Late | 21 | 21 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Match Zoho Creator Vendors with Zoho Books Vendor and Sync | Sachin Patil | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 19:22 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 21 | Late | 22 | 22 | 1 | days |  | Clear
7.4981e+17 | Zoho CRM Intgration With ZOho Boooks | Monik Chettiyar | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 13:32 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | New Profile for the user and testing | Swetha K | None |  |  | 2024-02-28 19:38 | Done | No | 100% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 |  | On Time |  | 0 | 0 | days |  | Clear | Dharanidharan C
7.4981e+17 | Zoho Books - Client Meeting & Internal Solution | Mohammed Yusha | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 18:55 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Four-Financial Accounting Management System | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | API/creator integration function instead insert record for creation invoice - | Swetha K | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 10:36 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 15 | Late | 16 | 16 | 1 | days
7.4981e+17 | Project Management - Progress Demo | Mohammed Yusha,Vignesh R,Tanu Gupta | High | 2024-02-27 09:30 | 2024-02-29 19:00 | 2024-02-28 09:28 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,704175602,790157522 | 6 | Late | 9 | 9 | 3 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Setup of Trip Option | Rishikesh Gogha | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-27 15:58 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Vendor Management Flow Updation + Books Solutioning | Stuti S. Kulshrestha | None | 2024-02-26 09:30 | 2024-02-29 19:00 | 2024-02-26 16:21 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 18 | Late | 22 | 22 | 4 | days |  | Clear
7.4981e+17 | Rename,rearrangement and disable of fields | Swetha K | None | 2024-02-26 19:00 | 2024-02-26 19:00 | 2024-02-26 09:33 | Done | No | 100% | IIFL SAMASTA - IMS Enhancement 3.5 | Milestone Two-Zoho Creator: Customization, Configuration, Testing and Go-Live of IMS enhancement | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 8 | Late | 9 | 9 | 0 | days
7.4981e+17 | Exit Checklist Demo meeting | Monik Chettiyar | Medium | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-23 21:20 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 38 | Late | 39 | 39 | 1 | days
7.4981e+17 | Zoho Peopleplus Support Call | Monik Chettiyar | None | 2024-02-07 09:30 | 2024-02-29 19:00 | 2024-02-23 21:04 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 18 | Late | 41 | 41 | 17 | days
7.4981e+17 | Weekly Scrum Meeting - Feb 2024 | Mohammed Yusha,Vignesh R,Sai Krishna,Tanu Gupta | High | 2024-02-23 09:30 | 2024-02-29 19:00 | 2024-02-26 09:41 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,704175602,753339779,790157522 | 6 | Late | 13 | 13 | 5 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Sales Order Line Items Fetch from Zoho Books Sales Order | Sachin Patil | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 19:43 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 24 | Late | 25 | 25 | 1 | days |  | Clear
7.4981e+17 | Send Second Communication to Wave 1 MBE's | Stefan Bradham | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-02-22 22:00 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 836353936 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Push Payment Received back to Creator | Shavi Thakur | None | 2024-02-23 16:30 | 2024-02-23 19:00 | 2024-02-26 02:13 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 3 | Late | 4 | 4 | 2.5 | hrs
7.4981e+17 | Zoho Analytics Customer call | Rishikesh Gogha | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-23 09:41 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 25 | Late | 26 | 26 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Proforma invoice-D | Devaraju S J | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 18:27 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Client Meeting - Zoho Desk | Monik Chettiyar | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-26 11:25 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Zoho CRM Accounts Module Data is not getting push | Monik Chettiyar | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-26 11:09 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Match Zoho Creator Customers with Zoho Books Customers | Sachin Patil | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 09:35 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 21 | Late | 22 | 22 | 1 | days |  | Clear
7.4981e+17 | Automation For Email notification | Shiwani Kumari | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 18:08 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | Thoucentric Scrum call | Kiran Shrivastav | None | 2024-02-23 09:30 | 2024-03-29 19:00 | 2024-02-23 11:30 | To Do | No | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | -11 | On Time | 25 | 25 | 26 | days
7.4981e+17 | Import Invoice/S | Shiwani Kumari | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 18:26 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | RE: New employee not reflecting in payroll | Rishikesh Gogha | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-26 09:39 | To Do | Yes | 0% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | TNIPL Zoho Books Integration testing | Vignesh R | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 17:57 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | Zoho Purchase and Inventory | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 24 | Late | 25 | 25 | 1 | days |  | Clear
7.4981e+17 | #5989 Fixing ZOHO Sheet & Corporate Leads Assigning Issues | Maninder Singh | High | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 11:48 | Done | No | 100% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Solution Demo | Tanu Gupta | High | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-22 23:26 | To Do | Yes | 0% | IIFL Samasta Zoho Creator Score Card Enhancement | Milestone One-Implementation of Score Card Enhancement | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 24 | Late | 25 | 25 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Support request : Unable to apply comp off | Kiran Shrivastav | None |  |  | 2024-02-26 10:18 | Done | No | 100% | AMC - VAlign | Neelgund Project Zoho HRMS Implementation | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Internal Meeting 2 | Aishwarya T | None | 2024-02-05 09:30 | 2024-02-09 19:00 | 2024-02-23 18:30 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 38 | Late | 43 | 43 | 5 | days |  | Clear | Sai Krishna
7.4981e+17 | Requirement Gathering Session 3 | Sai Krishna,Aishwarya T | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-02-23 16:18 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 33 | Late | 34 | 34 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | JSW-JODL Interview | Stuti S. Kulshrestha | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 19:23 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | UAT and Client Meeting 23/02/24 | M S Satya | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 16:52 | In Progress | Yes | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | Modeling Incoming Payments | Anusuyadevi V | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-22 09:49 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Dashboards - Analytics Integration | Anusha V | High | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-22 09:34 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Wedding Leaves | Stuti S. Kulshrestha | None | 2024-01-29 09:30 | 2024-02-20 19:00 | 2024-02-21 10:04 | To Do | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 27 | Late | 50 | 50 | 17 | days
7.4981e+17 | Internal KT /Follow up of internal documents (POC) | Stuti S. Kulshrestha | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 08:38 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 21 | Late | 22 | 22 | 1 | days |  | Clear
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-21 09:54 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | P&I Form Creation and Automations | Shavi Thakur | None | 2024-02-20 13:30 | 2024-02-20 16:00 | 2024-02-21 05:35 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 6 | Late | 7 | 7 | 2.5 | hrs
7.4981e+17 | Revised Quotation flow once deal is closed | Tanu Gupta | High | 2024-02-20 09:30 | 2024-02-23 19:00 | 2024-02-21 09:41 | Discovery Phase | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 24 | Late | 28 | 28 | 4 | days
7.4981e+17 | Import COA | Rishikesh Gogha | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-21 10:27 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Schedule Wave 2 Training Webinars | Kris Oswold | None | 2024-02-26 09:30 | 2024-02-28 19:00 | 2024-02-20 22:00 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 824545238 | 824545238 | 9 | Late | 12 | 12 | 3 | days
7.4981e+17 | Import Customer and vendor-D | Devaraju S J | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 18:08 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Proforma invoice creation-D | Devaraju S J | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-22 09:35 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | CTW Kick off meeting | Tanu Gupta,Kiran Shrivastav | High | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-21 14:48 | Done | No | 100% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522,791842987 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Need clarity redirect to RA and back to request user report | Swetha K | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 19:05 | Done | No | 100% | IIFL SAMASTA- Admin Module CR | Milestone One-Advance payment for Admin Module Change Request | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 23 | Late | 24 | 24 | 1 | days
7.4981e+17 | PMD CCO/ CCO - Phone No customization in the template | Ayush Singh | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-21 19:39 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 26 | Late | 27 | 27 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Zoho people account issue_Longitude | Kiran Shrivastav | None | 2024-02-21 09:30 | 2024-02-23 19:00 | 2024-02-21 14:21 | In Progress | Yes | 0% | AMC - VAlign | Longitude Exports Pvt Ltd - Zoho CRM, Zoho People & Zoho Payroll ¦ 09-08-2023 ¦ 08-02-2024 | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 24 | Late | 27 | 27 | 3 | days
7.4981e+17 | External Meeting with Durian Team and WordPress Team for Integration of New Form(Door Pop-Up and Furniture Pop-Up) on 20 Feb 24 | Sachin Patil | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 19:26 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Employee profile update for Archana and Arfath | Kiran Shrivastav | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-21 15:50 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | Status Update Meeting | Vignesh R | None | 2024-02-20 09:30 | 2024-02-23 19:00 | 2024-02-20 18:45 | In Progress | Yes | 10% | KSport_Zoho Creator | Milestone Two-Implementation of Zoho Creator – Custom App Development | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 24 | Late | 28 | 28 | 4 | days |  | Clear
7.4981e+17 | Import of item master/S | Shiwani Kumari | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 18:32 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | zoho desk call suport | Monik Chettiyar | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 10:01 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Data Migration for FCO module. | Supril Jain | None | 2023-10-03 09:30 | 2023-12-20 19:00 | 2024-02-21 10:55 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 78 | Late | 157 | 157 | 57 | days
7.4981e+17 | Re: Implementation of Automatic Absence Notification Emails for Employees | Kiran Shrivastav | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-21 09:53 | Done | No | 100% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 15 | Late | 16 | 16 | 1 | days
7.4981e+17 | Accounts import in CRM with Member IDs | Ayush Singh | None | 2024-02-19 09:30 | 2024-02-20 19:00 | 2024-02-20 09:38 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 27 | Late | 29 | 29 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Template updations | Mary Nisha | High | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 10:40 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 28 | Late | 29 | 29 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Tax master field level automation | Aishwarya T | None | 2024-02-22 09:30 | 2024-02-23 19:00 | 2024-02-19 12:28 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 24 | Late | 26 | 26 | 2 | days |  | Clear
7.4981e+17 | Approval process setup for purchase order | Sai Krishna,Aishwarya T | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-19 12:00 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 27 | Late | 28 | 28 | 1 | days |  | Clear
7.4981e+17 | Validation Setup for purchase requisition | Sai Krishna,Aishwarya T | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-19 11:56 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 31 | Late | 32 | 32 | 1 | days |  | Clear
7.4981e+17 | UAT Improvisation/ Suport | Sai Krishna,Aishwarya T | None | 2024-03-20 09:30 | 2024-03-21 19:00 | 2024-02-19 11:41 | To Do | No | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | -3 | On Time | -1 | -1 | 2 | days |  | Clear
7.4981e+17 | Button automation to send portal invitation to vendor on vendor registration | Sai Krishna,Aishwarya T | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-19 10:51 | In Progress | Yes | 90% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 35 | Late | 36 | 36 | 1 | days |  | Clear
7.4981e+17 | Add Push to Books in the Quote Report | Shavi Thakur | None | 2024-02-16 09:30 | 2024-02-16 13:00 | 2024-02-19 09:27 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 3 | Late | 4 | 4 | 3.5 | hrs
7.4981e+17 | Zoho recruit Interview Log Report Creation | Monik Chettiyar | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 13:58 | To Do | Yes | 0% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Document mapping with template | Prableen Kaur | None | 2024-02-19 09:30 | 2024-02-21 19:00 | 2024-02-20 12:40 | In Progress | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 26 | Late | 29 | 29 | 3 | days
7.4981e+17 | Final development of Conventional version | M S Satya | None |  |  | 2024-02-16 18:30 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Add Search Criteria in the Juspay Dashboard | Shavi Thakur,Tanu Gupta | None | 2024-02-19 09:30 | 2024-02-19 14:00 | 2024-02-19 10:37 | In Progress | Yes | 0% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417,790157522 | 28 | Late | 29 | 29 | 4.5 | hrs
7.4981e+17 | TSD | Rishikesh Gogha | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-19 13:50 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | Issue Downloading Payslip on Mobile - Support Assistance Required | Kiran Shrivastav | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 11:17 | To Do | Yes | 0% | AMC - VAlign | Neelgund Developers LLP ¦ Zoho People, Recruit & Payroll ¦ 19-10-2023 ¦ 18-10-2024 | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Zoho Recruit Revamp request | Kiran Shrivastav | None | 2024-02-19 09:30 | 2024-02-23 19:00 | 2024-02-19 23:31 | In Progress | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 24 | Late | 29 | 29 | 5 | days
7.4981e+17 | External Meeting with Durian Team and WordPress Team for Integration of New Form(Door Pop-Up and Furniture Pop-Up) | Sachin Patil | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 19:07 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 22 | Late | 23 | 23 | 1 | days
7.4981e+17 | Meeting with Manish/S | Shiwani Kumari | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 18:42 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Correction on View allocation | Vignesh R | None | 2024-02-23 19:00 | 2024-02-23 19:00 | 2024-02-16 20:07 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 24 | Late | 25 | 25 | 0 | days |  | Clear
7.4981e+17 | Efforts allocation based on the activity and Budgeted days and hours calculation | Vignesh R | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 20:00 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 31 | Late | 32 | 32 | 1 | days |  | Clear
7.4981e+17 | Certifcation UI development for Creator. | Rahul S S | None |  |  | 2024-02-16 19:41 | In Progress | No | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 830176551 | 830176551 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Training | Kiran Shrivastav | None | 2024-01-29 09:30 | 2024-02-16 19:00 | 2024-02-16 16:48 | Development | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 31 | Late | 50 | 50 | 15 | days
7.4981e+17 | Zoho CRM New Changes 02 | Rajesh Shindagi | None | 2024-02-16 09:30 | 2024-02-29 19:00 | 2024-02-18 14:11 | In Progress | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 18 | Late | 32 | 32 | 10 | days
7.4981e+17 | UAT : Project Management | Vignesh R,Tanu Gupta | High | 2024-03-11 09:30 | 2024-03-13 19:00 | 2024-02-16 19:06 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 704175602,790157522 | 5 | Late | 8 | 8 | 3 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Multi-level Approver for Timesheet | Vignesh R,Tanu Gupta | High | 2024-03-12 09:30 | 2024-03-15 19:00 | 2024-02-16 18:54 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 704175602,790157522 | 3 | Late | 7 | 7 | 4 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Budget : Team specific | Tanu Gupta | High | 2024-02-16 09:30 | 2024-02-19 19:00 | 2024-02-16 18:45 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 17 | Late | 21 | 21 | 2 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Proforma invoice-D | Devaraju S J | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 18:20 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | Zoho Creator - Various Updates and Profile updates | Tanu Gupta | High | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-20 09:37 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 28 | Late | 29 | 29 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Re: Issue in ledger balance. | Rishikesh Gogha | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 18:31 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Automation for Invoice for the academic year - 2024 | Swetha K | None | 2024-02-19 09:30 | 2024-02-20 19:00 | 2024-02-20 09:35 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 23 | Late | 25 | 25 | 2 | days
7.4981e+17 | Automation-D | Devaraju S J | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 18:33 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Incoming payouts external call | Anusuyadevi V | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-19 11:09 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Discussion on Inventory Report | Waheeba Khan | None |  |  | 2024-02-16 09:45 | To Do | No | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | When the time of edit Sales Order Item, Cost Price cannot be changed | Sachin Patil | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 19:16 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | Bulk Adjustment/S | Shiwani Kumari | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 18:13 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Ocimum Client Visit - 15/02/24 | M S Satya | None |  |  | 2024-02-15 14:50 | Done | No | 100% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Issue in Duplicated application | Ranjana Poojari | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 18:14 | Done | No | 100% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | MBE Application form creation | Mary Nisha | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 14:14 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 32 | Late | 33 | 33 | 1 | days |  | Clear
7.4981e+17 | Quote Integration Based on Line Item Concetination | Shavi Thakur | None | 2024-02-15 13:30 | 2024-02-15 15:00 | 2024-02-16 07:57 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 1 | Late | 2 | 2 | 1.5 | hrs
7.4981e+17 | Zoho Projects TSD | Shavi Thakur | None | 2024-02-14 13:30 | 2024-02-14 16:00 | 2024-02-14 21:13 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 0 | Late | 1 | 1 | 2.5 | hrs
7.4981e+17 | Vendor Bills form | Aishwarya T | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 18:59 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 15 | Late | 16 | 16 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Internal meeting with Rishikesh/S | Shiwani Kumari | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:32 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Banking/S | Shiwani Kumari | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:24 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Dashboard and Reports for EA and Member Renewal | Dharanidharan C | None | 2024-01-22 09:30 | 2024-02-15 19:00 | 2024-02-13 16:19 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 32 | Late | 57 | 57 | 19 | days |  | Clear
7.4981e+17 | EA assignment and Member renewal UAT Preparation - Release notes and Video manual | Dharanidharan C | None | 2024-01-22 09:30 | 2024-02-15 19:00 | 2024-02-13 16:16 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 32 | Late | 57 | 57 | 19 | days |  | Clear
7.4981e+17 | development coventional verison 2 | M S Satya | None |  |  | 2024-02-13 15:35 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Map certificates data based on new template | Pannaga H | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-13 18:26 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 795342015 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Member Company Details data Migration | Kalyanasundaram L | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-13 10:10 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 819676542 | 35 | Late | 36 | 36 | 1 | days |  | Clear
7.4981e+17 | Credit Note API and Credit Note Automation | Anusuyadevi V | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-15 20:40 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Recurring journals-D | Devaraju S J | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 18:14 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Identify the Issues in View Allocation Data | Mohammed Yusha,Tanu Gupta | High | 2024-02-14 09:30 | 2024-02-23 19:00 | 2024-02-14 20:46 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 0 | Late | 10 | 10 | 8 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Resource allocation flow development | Mohammed Yusha,Tanu Gupta | High | 2024-02-13 09:30 | 2024-02-15 19:00 | 2024-02-13 19:40 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 21 | Late | 24 | 24 | 3 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Project Budgeting and Management Template Discussion | Mohammed Yusha,Tanu Gupta | High | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:26 | In Progress | Yes | 10% | Bahwan IT LLC - Zoho one | Milestone Five - Project Budgeting & Project management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 34 | Late | 35 | 35 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Inventory Management/S | Shiwani Kumari | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 18:07 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Changes in Sales Return PDF | Vignesh R | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 19:14 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Approved for make payment/Marking bills as paid - For grand total 0 mark paid need not be there bt update in books | Swetha K | None | 2024-02-15 09:30 | 2024-02-16 19:00 | 2024-02-15 19:04 | Done | No | 100% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 20 | Late | 22 | 22 | 2 | days |  | Clear | Waheeba Khan
7.4981e+17 | Detailing the requirements and Testing | unassigned | None |  |  | 2024-02-14 09:36 | To Do | No | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 671373250 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Banking-D | Devaraju S J | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:22 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Feedback Calls & Feasibility checks | unassigned | High | 2024-02-14 09:30 | 2024-03-01 19:00 | 2024-02-15 09:58 | In Progress | Yes | 0% | Prodevans - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 795545761 | - | 17 | Late | 34 | 34 | 13 | days
7.4981e+17 | Boldfit - Weekly Status Update Call - Feb 2024 | Supril Jain,Tanu Gupta | High | 2024-02-14 09:30 | 2024-02-28 19:00 | 2024-02-14 18:52 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 756836914,790157522 | 19 | Late | 34 | 34 | 11 | days |  | Clear | Supril Jain
7.4981e+17 | System glitch Tour claim TE - 202400230 | Swetha K | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 13:33 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 29 | Late | 30 | 30 | 1 | days
7.4981e+17 | Customer Master, Item Master Sync and Quote Sync from Creator to Books | Shavi Thakur,Tanu Gupta | Medium | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 17:27 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 773081417,790157522 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Go-Live Support - Client Meeting | Mohammed Yusha,Tanu Gupta | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 18:44 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Implement Google Analytics for Data Gathering | Albert Diaz | None | 2024-02-06 09:30 | 2024-03-15 19:00 | 2024-02-13 22:53 | In Progress | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 809116687 | 3 | Late | 42 | 42 | 29 | days
7.4981e+17 | Sales return management-d | Devaraju S J | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:34 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Item Master and Vendor Masters Integration to Zoho Books | Vaikuntam Chowdary | None | 2024-02-12 09:30 | 2024-02-13 19:00 | 2024-02-12 18:31 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 34 | Late | 36 | 36 | 2 | days
7.4981e+17 | Zoho CRM API Documentation | Rajesh Shindagi | None | 2024-03-04 09:30 | 2024-03-08 19:00 | 2024-02-12 16:26 | In Progress | Yes | 0% | Dr Reddy’s - Zoho CRM, Desk, SalesIQ | Milestone One-Advance payment for Zoho project initiation [Zoho Desk & Zoho SalesIQ, Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 10 | Late | 15 | 15 | 5 | days
7.4981e+17 | Configuration of Automations for linking records | Rajesh Shindagi | None | 2024-02-12 09:30 | 2024-02-14 19:00 | 2024-02-12 16:26 | In Progress | Yes | 0% | Dr Reddy’s - Zoho CRM, Desk, SalesIQ | Milestone One-Advance payment for Zoho project initiation [Zoho Desk & Zoho SalesIQ, Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 33 | Late | 36 | 36 | 3 | days
7.4981e+17 | Sales Return - A | Akshay Parameshwara Hegde | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:39 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784261 | 844784261 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Sales return/S | Shiwani Kumari | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:28 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 35 | Late | 36 | 36 | 1 | days
7.4981e+17 | Roles and Profiles Setup | M S Satya | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 15:28 | In Progress | Yes | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 35 | Late | 36 | 36 | 1 | days
7.4981e+17 | Hide, Show, Enabled and Disabled Gate Entry fields | Sachin Patil | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:06 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | In rejection Entry- Cost want to Showing based on GRN No Rate | Sachin Patil | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 11:18 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Internal Discussion | Vignesh R | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 20:48 | To Do | Yes | 0% | Ecovinal Project 3 - Farmer Management | Milestone Two-Zoho Creator – Farmer Operations: Configuration and customisation, Software demo | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 35 | Late | 36 | 36 | 1 | days |  | Not Clear
7.4981e+17 | Demo call with thoughtfocus | Kiran Shrivastav | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 12:27 | To Do | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Adding New users to payroll | Kiran Shrivastav | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 09:24 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Zoho CRM Subform Level Calculation Error from margin Amount | Monik Chettiyar | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:41 | Development Complete | Yes | 10% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 35 | Late | 36 | 36 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | Segregation of Material & Process Cost | Vignesh R | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 21:30 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Hide, Show, Enabled and Disabled Bill Fields | Sachin Patil | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 19:15 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Pdf component File handling with redux | unassigned | None |  |  | 2024-02-14 18:35 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176551 | - |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-01 09:30 | 2024-02-15 19:00 | 2024-02-14 10:56 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 19 | 19 | 11 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-01 09:30 | 2024-02-15 19:00 | 2024-02-14 10:56 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 19 | 19 | 11 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-01 09:30 | 2024-02-15 19:00 | 2024-02-14 10:56 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 19 | 19 | 11 | days
7.4981e+17 | PO Version | Ranjana Poojari | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 10:41 | Done | No | 100% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | Portal creation and button customization | Aishwarya T | None | 2024-02-13 09:30 | 2024-02-29 19:00 | 2024-02-13 15:22 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 0 | Late | 17 | 17 | 13 | days |  | Clear | Sai Krishna
7.4981e+17 | Feasibility study on new requirements | Kiran Shrivastav | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-02-12 13:04 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Search Customer and Items API preparation | Anusuyadevi V | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 18:56 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Five-Payment for April 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | UI POC | Anusuyadevi V | None | 2024-02-07 09:30 | 2024-02-09 19:00 | 2024-02-08 18:52 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Five-Payment for April 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 3 | 3 | 3 | days
7.4981e+17 | Item and Inventory/S | Shiwani Kumari | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 18:46 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Item and Inventory - A | Akshay Parameshwara Hegde | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 18:45 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784261 | 844784261 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Data Clean-up Project Management | Ranjana Poojari | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 12:20 | Done | No | 100% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778475421 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | fellow extension workflow | Kiran Shrivastav | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 17:03 | Done | No | 100% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | 1 Rupee difference in offer letter | Kiran Shrivastav | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 10:42 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Thoucentric Support Meeting | Monik Chettiyar | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-12 01:25 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Zoho CRM Quotes to Books data is not pushing there | Monik Chettiyar | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-12 01:12 | QA level 1 Completed | Yes | 0% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 45 | Late | 46 | 46 | 1 | days |  | Clear
7.4981e+17 | Changes format and add additional fields in Bill of supply print page | Maninder Singh | None | 2024-02-12 09:30 | 2024-02-14 19:00 | 2024-02-09 11:32 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 26 | Late | 29 | 29 | 3 | days |  | Clear | Supril Jain
7.4981e+17 | Internal Meetings | Waheeba Khan,Devaraju S J,Akshay Parameshwara Hegde,Shiwani Kumari | None | 2024-02-08 09:30 | 2024-02-15 19:00 | 2024-02-08 18:39 | In Progress | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784261 | 671373250,844783967,844784261,844784545 | 32 | Late | 40 | 40 | 6 | days
7.4981e+17 | Zoho CRM Data Update | Monik Chettiyar | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 11:17 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 35 | Late | 36 | 36 | 1 | days
7.4981e+17 | Deal Management Blueprint | Nikita Srivastava | None | 2024-02-12 09:30 | 2024-02-13 19:00 | 2024-02-12 10:05 | In Progress | Yes | 0% | Accorian - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 774653652 | 34 | Late | 36 | 36 | 2 | days
7.4981e+17 | Hide, Show, Enabled and Disabled Purchase Order fields | Sachin Patil | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 19:13 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Update Version control for all user stories | Supreeth R Kalluraya | None | 2024-02-08 09:30 | 2024-02-14 19:00 | 2024-02-08 14:06 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 788577227 | 788577227 | 33 | Late | 40 | 40 | 5 | days |  | Clear
7.4981e+17 | Update Service Type on Purchase Order when Convert PI to PO based on Selected Vendor | Sachin Patil | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 18:54 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Non Day functionalities For Opportunity and CCO | Mary Nisha | High | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 11:22 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 38 | Late | 39 | 39 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Add logics for Weightage Merger | Tanu Gupta | High | 2024-02-09 09:30 | 2024-02-22 19:00 | 2024-02-09 19:37 | In Progress | Yes | 10% | IIFL Samasta Zoho Creator Score Card Enhancement | Milestone One-Implementation of Score Card Enhancement | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 25 | Late | 39 | 39 | 10 | days |  | Clear | Selva Bharathi
7.4981e+17 | Meeting with Servetel, Zoho Team and Boldfit team for custom module linking | Tanu Gupta | High | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 19:24 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Four-Implementation of Zoho CRM Application | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 38 | Late | 39 | 39 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Local Claim Report Issue | Achyuth T M | High | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-12 10:57 | Done | No | 100% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Debit Note / Credit Note and Vendor Master Creation and API Documentation | Vaikuntam Chowdary | None | 2024-02-09 09:30 | 2024-02-12 19:00 | 2024-02-12 09:26 | To Do | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 35 | Late | 39 | 39 | 2 | days
7.4981e+17 | Import data Setup | Anusha V | High | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-09 19:39 | In Progress | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 41 | Late | 42 | 42 | 1 | days
7.4981e+17 | Internal KT | Vaikuntam Chowdary | None | 2024-02-06 09:30 | 2024-02-09 19:00 | 2024-02-09 09:31 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 38 | Late | 42 | 42 | 4 | days |  | Clear
7.4981e+17 | Client call for scorecard enhancements | Tanu Gupta | High | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 23:30 | In Progress | Yes | 10% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 39 | Late | 40 | 40 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | PO integration to Books disable for now | Swetha K | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 13:44 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 39 | Late | 40 | 40 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Byron Support Request - #5909 | unassigned | None |  |  | 2024-02-08 10:53 | In Progress | No | 0% | AMC - VAlign | Byron Medical Pty Ltd ¦ Zoho One ¦ 01-10-2023 ¦ 30-09-2024 | 7.4981e+17 | 7.4981e+17 |  | 789497933 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Button Functionality For Creating SO & Testing | Anusha V | High | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-07 19:44 | Done | No | 100% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Create New Redeployment Schedule | Kris Oswold | None | 2024-02-06 09:30 | 2024-02-13 19:00 | 2024-02-06 22:41 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 824545238 | 7 | Late | 15 | 15 | 6 | days
7.4981e+17 | Daily Standup Meeting | Vaikuntam Chowdary | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-07 11:36 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Five-Payment for April 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 41 | Late | 42 | 42 | 1 | days
7.4981e+17 | A - Company Set up | Akshay Parameshwara Hegde | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:29 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784261 | 844784261 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | In Finance PO team report - Close PO option | Swetha K | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:30 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 41 | Late | 42 | 42 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Solutioning Masters and Seller documents | Anusuyadevi V | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-07 10:44 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Lead Status Report for CRM | Achyuth T M | High | 2024-02-05 09:30 | 2024-02-07 19:00 | 2024-02-06 19:02 | In Progress | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 40 | Late | 43 | 43 | 3 | days
7.4981e+17 | Requirement Discovery Session & Solutioning | Mohammed Yusha,Vignesh R,Tanu Gupta | None | 2024-02-05 09:30 | 2024-02-09 19:00 | 2024-02-05 19:26 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,704175602,790157522 | 10 | Late | 15 | 15 | 5 | days |  | Clear
7.4981e+17 | Country and state validation Tasks | Mary Nisha | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 10:06 | QA level 1 Completed | Yes | 30% | Educational Initiatives - P&I CR | None | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 40 | Late | 41 | 41 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Support request : #5895 Leave Issue | Kiran Shrivastav | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:45 | Done | No | 100% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Call on Skill set and Nine-Box matrix discussion | Kiran Shrivastav | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 21:55 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 18 | Late | 19 | 19 | 1 | days
7.4981e+17 | Auto Update field in Lead/Potential | Nikita Srivastava | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 17:18 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Dashboard UI development. | Rahul S S | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 17:02 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 830176551 | 830176551 | 8 | Late | 9 | 9 | 1 | days |  | Clear
7.4981e+17 | Issue in Stock Adjustment | Vignesh R | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-05 18:37 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 45 | Late | 46 | 46 | 1 | days
7.4981e+17 | Changing the status of Po/So/Grn/ inv etc, renavigates the page back to a different page as opposed to the same page. | Maninder Singh | High | 2024-02-07 09:30 | 2024-02-12 19:00 | 2024-02-07 09:21 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 782721491 | 782721491 | 28 | Late | 34 | 34 | 4 | days |  | Clear
7.4981e+17 | Master flow reporting for creating User Manual | Vignesh R | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 21:50 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 40 | Late | 41 | 41 | 1 | days
7.4981e+17 | Contacts and customers -D | Devaraju S J | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 18:36 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Changes in Inventory report & Color coding | Vignesh R | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 22:25 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 41 | Late | 42 | 42 | 1 | days
7.4981e+17 | Mark Lead as Qualified | unassigned | None |  |  | 2024-02-06 19:55 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 701371504 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Create notes for a lead | unassigned | None |  |  | 2024-02-06 19:54 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 701371504 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Edit Lead Information | unassigned | None |  |  | 2024-02-06 19:54 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 701371504 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | The 'Business Sector' field should be mandatory for Lead and Opportunity | Sachin Patil | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 18:45 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Import Option for Item Master-To Import Production Control Information Field | Sachin Patil | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 18:36 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Modified Date Issue - 07-02-2024 | Ranjana Poojari | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 13:04 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Add Panel in Operations Dashboard for Slow, Service and Other Stock (Operations Dashboard S1, S2 and S3) | Sachin Patil | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:53 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 35 | Late | 36 | 36 | 1 | days
7.4981e+17 | A - Introduction to Zoho Books | Akshay Parameshwara Hegde | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 17:56 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784261 | 844784261 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Golive | Selva Bharathi | None | 2024-02-21 09:30 | 2024-02-27 19:00 | 2024-02-05 18:25 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573 | 20 | Late | 27 | 27 | 5 | days |  | Clear
7.4981e+17 | Deployment | Selva Bharathi | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-05 18:19 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573 | 40 | Late | 41 | 41 | 1 | days |  | Clear
7.4981e+17 | Data refinement for Wave 1 regions | Prableen Kaur,Pannaga H | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-02-05 18:07 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644,795342015 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Understanding the Requirment | M S Satya | None |  |  | 2024-02-07 10:26 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Project Customization | M S Satya | None |  |  | 2024-02-07 10:17 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Zoho Recruit Offer Template Salary Correction | Monik Chettiyar | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-06 01:54 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Zoho CRM Template Changes for calculation From Quotes Module | Monik Chettiyar | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-06 01:33 | In Progress | Yes | 0% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 46 | Late | 47 | 47 | 1 | days |  | Clear
7.4981e+17 | Zoho People Support Meeting | Monik Chettiyar | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-06 01:26 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Add 'Customer GST No' new field in Invoice and Update all old invoice with GST No | Sachin Patil | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 19:12 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Vendor Master Approval - error on approval | Swetha K | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 18:02 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 38 | Late | 39 | 39 | 1 | days
7.4981e+17 | User and Profile Settings | Anusha V | High | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-06 09:33 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | Resolve issue with Invoice for tax % and Adjustments | Tanu Gupta | High | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 20:52 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 42 | Late | 43 | 43 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Solution discovery on the Queries shared | Anusuyadevi V | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 20:30 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Create Homepage For Finance | Dharanidharan C | None | 2024-02-06 09:30 | 2024-02-20 19:00 | 2024-02-02 17:20 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 2 | Late | 17 | 17 | 11 | days
7.4981e+17 | Portal Co-ordinator Homepage - To add and provide access to Users | Dharanidharan C | None | 2024-02-05 09:30 | 2024-02-20 19:00 | 2024-02-02 17:14 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 2 | Late | 18 | 18 | 12 | days
7.4981e+17 | Client Meeting | Aishwarya T | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 15:08 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 45 | Late | 46 | 46 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | Scrum Call - 01-02-2024 | Ranjana Poojari | None |  |  | 2024-02-02 18:16 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-25 09:30 | 2024-02-02 19:00 | 2024-02-02 10:48 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 17 | Late | 26 | 26 | 7 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-25 09:30 | 2024-02-02 19:00 | 2024-02-02 10:46 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 17 | Late | 26 | 26 | 7 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-02-02 10:36 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | MR2 Series Data Upload | Ranjana Poojari | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 10:32 | Done | No | 100% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | Chain Bucket Configuration on BOM | Kalyanasundaram L | None | 2024-02-01 09:30 | 2024-02-06 19:00 | 2024-02-04 20:01 | To Do | Yes | 0% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 41 | Late | 47 | 47 | 4 | days |  | Clear
7.4981e+17 | In PO unutilized amount negative | Swetha K | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 09:35 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 42 | Late | 43 | 43 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Quotations mandatory refinement of error: Quotation amount excluding gst and not including | Swetha K | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 19:00 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 45 | Late | 46 | 46 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | GRN and VB from PO - GSTIN not changing according to VB | Swetha K | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-02 09:57 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 46 | Late | 47 | 47 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | System Audit -P&I and Production | Mohammed Yusha,Vignesh R | Medium | 2024-02-01 09:30 | 2024-02-09 19:00 | 2024-02-01 19:03 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,704175602 | 38 | Late | 47 | 47 | 7 | days
7.4981e+17 | Project Management POC Flow Review | Mohammed Yusha,Vignesh R,Tanu Gupta | None | 2024-02-02 09:30 | 2024-02-06 19:00 | 2024-02-02 19:12 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,704175602,790157522 | 10 | Late | 15 | 15 | 3 | days |  | Clear
7.4981e+17 | Pan India Score calculation issue | Tanu Gupta | High | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 19:26 | Development Complete | Yes | 10% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 790157522 | 790157522 | 46 | Late | 47 | 47 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Field Level Validation | Nawaz Sharief | None |  |  | 2024-02-02 18:14 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 841115370 | 841115370 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Feedback Points on - 02-02-2024 | Ranjana Poojari | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 10:50 | Done | No | 100% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 3 | Late | 4 | 4 | 1 | days |  | Clear
7.4981e+17 | Push Bill Memo and Narration to zoho books for all current financial year | Vignesh R | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 20:30 | In Progress | Yes | 10% | Trimble Group_Zoho Books & Zoho Creator | Zoho Purchase and Inventory | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 46 | Late | 47 | 47 | 1 | days |  | Clear
7.4981e+17 | Sahaas User Manual | Mary Nisha | High | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 19:02 | Done | No | 100% | AMC - VAlign | FARM INDIA IMPEX ¦ Books, Creator, People, Payroll & Analytics ¦ 8-12-23 to 7-12-24 | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | r &d sql query and reportsin zoho analytics | Nikita Srivastava | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 19:48 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 42 | Late | 43 | 43 | 1 | days
7.4981e+17 | Client Visit | Basavaraj Patil | None | 2024-01-16 09:30 | 2024-02-09 19:00 | 2024-02-02 17:01 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 38 | Late | 63 | 63 | 19 | days |  | Clear | Waheeba Khan
7.4981e+17 | Import Vendor details. | Basavaraj Patil | None | 2024-01-23 09:30 | 2024-02-02 19:00 | 2024-02-02 16:45 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 45 | Late | 56 | 56 | 9 | days |  | Clear | Waheeba Khan
7.4981e+17 | Zoho Books Customer API and Zoho Creator Customer API Document Creation | Anusuyadevi V | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 21:23 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Zoho creator forms Customization | Anusha V | High | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 20:26 | Done | No | 100% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Meeting with client and Zoho Team : Issue with Bundles | Tanu Gupta | High | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 19:12 | Done | No | 100% | (BoldFit) Sasvat_Zoho One | Milestone Three-Implementation of Zoho Inventory | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | OB Adjustments for items | Rishikesh Gogha | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-02-01 11:35 | To Do | Yes | 0% | Good Will Enterprises - Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 47 | Late | 48 | 48 | 1 | days
7.4981e+17 | PRO Template Correction | Vaikuntam Chowdary | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-02-01 09:21 | In Progress | Yes | 10% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 47 | Late | 48 | 48 | 1 | days |  | Clear
7.4981e+17 | Form Creation - Customer Master, Currency, Contact Persons, Payment Terms | Anusuyadevi V | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-02-01 10:05 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Custom scheduler to send Daily Donation report, html page to generate report | Sai Krishna,Tanu Gupta | High | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 21:46 | In Progress | Yes | 10% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 790157522 | 753339779,790157522 | 47 | Late | 48 | 48 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Excel sheet with modules and fields of Vendor Management | Aishwarya T | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 12:09 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 35 | Late | 36 | 36 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Vendor Bill w/o PO RM approval | Swetha K | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 18:19 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 47 | Late | 48 | 48 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | PMD CCO deposit amount alignmentssignature part will move to next page if its not fixed in 1 | Ayush Singh | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-02-01 11:00 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 47 | Late | 48 | 48 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Client Visit on 31-Jan-2024 | Vignesh R | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 19:00 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 47 | Late | 48 | 48 | 1 | days
7.4981e+17 | Fwd: Probation confirmed | Kiran Shrivastav | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 14:56 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 46 | Late | 47 | 47 | 1 | days
7.4981e+17 | Re: Location tracking in Attendance sheet | Kiran Shrivastav | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 12:58 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Acceptable range for purchase invoice should be PO +5% in create purchase invoice | Maninder Singh | None | 2024-01-30 09:30 | 2024-02-12 19:00 | 2024-01-30 14:06 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 28 | Late | 42 | 42 | 10 | days |  | Clear | Supril Jain
7.4981e+17 | Assign Deal Owner for Facebook Campaign New Deals (Vadodara, Chadigarh and Gurugram) | Sachin Patil | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 19:25 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Profile page update and Dashboard QA | Dharanidharan C | None | 2024-01-29 09:30 | 2024-01-30 19:00 | 2024-01-29 17:38 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 14 | Late | 16 | 16 | 2 | days |  | Clear
7.4981e+17 | zoho people Change the General (Bangalore ) to Unilever (BLR) | Monik Chettiyar | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 10:51 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 49 | Late | 50 | 50 | 1 | days
7.4981e+17 | User and Role Permissions | Anusuyadevi V | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-31 09:43 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Zoho Books - Requirement Gathering - Acculeap Advisors | Tanu Gupta | High | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 20:17 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 30 | Late | 31 | 31 | 1 | days
7.4981e+17 | Client Meeting & Internal Meeting | Mohammed Yusha,Tanu Gupta | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 19:01 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 22 | Late | 23 | 23 | 1 | days
7.4981e+17 | User Creation | unassigned | High | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-29 09:30 | Done | No | 100% | Prodevans - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 795545761 | - | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Create Purchase Invoice Summary report in zoho analytics and embed into zoho creator | Maninder Singh | Medium | 2024-01-31 09:30 | 2024-02-12 19:00 | 2024-01-31 09:20 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 28 | Late | 41 | 41 | 9 | days
7.4981e+17 | EHV - API Document | Ranjana Poojari,Anusha V | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 18:12 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421,795545761 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Deep dive into Zoho RPA Bot | Prableen Kaur | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 18:30 | To Do | Yes | 0% | RPA Master Plan | None | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 53 | Late | 54 | 54 | 1 | days |  | Clear
7.4981e+17 | Other Redemption Categories flow testing | Mohammed Yusha,Vaikuntam Chowdary | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 18:40 | Done | No | 100% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 701373265,778472746 | 28 | Late | 29 | 29 | 1 | days |  | Clear
7.4981e+17 | Requirement Calls/Clarifications | unassigned | High | 2024-01-29 09:30 | 2024-01-31 19:00 | 2024-01-30 10:19 | In Progress | Yes | 0% | Prodevans - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 795545761 | - | 47 | Late | 50 | 50 | 3 | days
7.4981e+17 | Import Bank Statements and PhonePe Statements | Sai Krishna,Tanu Gupta | High | 2024-01-29 09:30 | 2024-02-02 19:00 | 2024-01-29 21:29 | In Progress | Yes | 10% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 790157522 | 753339779,790157522 | 45 | Late | 50 | 50 | 5 | days |  | Clear | Dharanidharan C
7.4981e+17 | Admin access and Chat with Zoho Support to rename Application name | Anusuyadevi V | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 19:14 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | RTO Follow Client Demo | Mohammed Yusha | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 18:49 | Done | No | 100% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Inventory and RTO Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | Update Email Notification Recipient | Supril Jain | None | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-31 09:25 | Done | No | 100% | AMC - VAlign | Global Learning service LLP - Zoho CRM ¦ 05-05-2023 ¦ 04-05-2024 | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 40 | Late | 42 | 42 | 2 | days
7.4981e+17 | Redux Refactoring | Nawaz Sharief | None |  |  | 2024-01-29 19:40 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 841115370 | 841115370 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Under dropdown “Trainer Name” Kindly add “B2B trainer”Under Dropdown “Payment Mode” Kindly add “Purchase Order” . | Maninder Singh | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 09:38 | Done | No | 100% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Inventory / Non-Inventory tracking item mismatch in creator and books | Vignesh R | None | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-30 22:00 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 47 | Late | 49 | 49 | 2 | days
7.4981e+17 | Feedback points | Aishwarya T | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 15:09 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 48 | Late | 49 | 49 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | Email issue | Nikita Srivastava | None | 2023-10-19 09:30 | 2023-10-19 19:00 | 2024-01-30 09:58 | Development Complete | Yes | 0% | All Time Support - CR - Billing Operations | Milestone Two-Change request on Zoho Creator & Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 774653652 | 151 | Late | 152 | 152 | 1 | days |  | Clear
7.4981e+17 | Creator - Section Customization | Ayush Singh | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 21:38 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 49 | Late | 50 | 50 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Zoho People Custom Module Development And Funtions | Monik Chettiyar | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-28 18:05 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | ZOho CRM Call issue Pop erroe | Monik Chettiyar | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-28 17:41 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | Zoho CRM and Books Discussion | unassigned | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-28 17:31 | In Progress | Yes | 10% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | - | 60 | Late | 61 | 61 | 1 | days |  | Clear
7.4981e+17 | Create Custom Function for Enabled/Disabled Rate field for Manually Entered Rate in Invoice And Fetch Rate Item Price List | Sachin Patil | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 19:08 | Development Complete | Yes | 10% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 53 | Late | 54 | 54 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Presales call with Renuka (Advisor Labs) | Kiran Shrivastav | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 12:54 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 48 | Late | 49 | 49 | 1 | days
7.4981e+17 | RE: PL Approval issue | Kiran Shrivastav | None |  |  | 2024-01-29 17:05 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Material Issue not pushing to zoho books | Vignesh R | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 18:07 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 53 | Late | 54 | 54 | 1 | days
7.4981e+17 | WordPress Form Integartion with CRM And Deal Owner Assign (Veneer Doors New Lead Page) | Sachin Patil | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 19:34 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Template corrections and automations | Mary Nisha | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 10:41 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 49 | Late | 50 | 50 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Dashboards Customization | unassigned | High | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-31 09:21 | In Progress | Yes | 0% | Prodevans - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 795545761 | - | 49 | Late | 50 | 50 | 1 | days
7.4981e+17 | Internal meeting and Email response | Mohammed Yusha,Shavi Thakur,Tanu Gupta | High | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 20:27 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,773081417,790157522 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Create Sales Return, Credit Note and Refund for Fulfilled Item Refund | Anusuyadevi V | None | 2024-01-27 09:30 | 2024-01-27 19:00 | 2024-01-27 20:03 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Create Test Orders to check Partial fulfillment and its impact on ZI | Anusuyadevi V | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-26 21:25 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Client Call for #5860 - Zoho Creator ¦ VMS Changes | Mohammed Yusha,Tanu Gupta | High | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-26 20:42 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Reversal of Invoices | Swetha K | None | 2024-01-31 09:30 | 2024-02-07 19:00 | 2024-01-30 12:54 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 36 | Late | 44 | 44 | 6 | days
7.4981e+17 | Updating Reporting Tags for Journals - LE | Swetha K | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 11:40 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Changing the status of Po/So/Grn/ inv etc, renavigates the page back to a different page as opposed to the same page.in all tabs | Maninder Singh | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-24 11:35 | In Progress | Yes | 0% | AMC - VAlign | FARM INDIA IMPEX ¦ Books, Creator, People, Payroll & Analytics ¦ 8-12-23 to 7-12-24 | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 53 | Late | 54 | 54 | 1 | days
7.4981e+17 | Add Balance quantity in Approved PO's report | Maninder Singh | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-24 11:30 | In Progress | Yes | 0% | AMC - VAlign | FARM INDIA IMPEX ¦ Books, Creator, People, Payroll & Analytics ¦ 8-12-23 to 7-12-24 | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 54 | Late | 55 | 55 | 1 | days
7.4981e+17 | Workflow and Automation to fetch the data form CRM - CCO and PMD CCO | Ayush Singh | None | 2024-01-23 09:30 | 2024-01-24 19:00 | 2024-01-23 20:37 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 54 | Late | 56 | 56 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Client Visit on 23-Jan-2024 | Vignesh R | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 18:37 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 55 | Late | 56 | 56 | 1 | days
7.4981e+17 | #5869 Sales Monthly Report | Tanu Gupta | High | 2024-01-24 09:30 | 2024-01-25 19:00 | 2024-01-24 20:25 | Done | No | 100% | AMC - VAlign | HAPPY RELIABLE SURGERIES PRIVATE LIMITED - Zoho CRM and Zoho Form ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 3 | 3 | 2 | days
7.4981e+17 | Desk Flow Integration Corrections | Vaikuntam Chowdary | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 18:07 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 55 | Late | 56 | 56 | 1 | days |  | Clear
7.4981e+17 | ABMPL-Zoho Creator Purchase Flow Demo | Vaikuntam Chowdary | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-23 09:25 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 56 | Late | 57 | 57 | 1 | days |  | Clear
7.4981e+17 | Offboarding Module Custom Function Data Update | Monik Chettiyar | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-24 10:59 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 54 | Late | 55 | 55 | 1 | days
7.4981e+17 | Analytics Data Sync issue | Nikita Srivastava | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 17:57 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Push bills to books and add purchase order stock to inventory without approval for samsung warehouse | Sachin Patil | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-24 19:14 | To Do | Yes | 0% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 54 | Late | 55 | 55 | 1 | days |  | Clear
7.4981e+17 | Execute script for GI Migration | Pannaga H | None | 2024-01-21 09:30 | 2024-01-24 19:00 | 2024-01-24 13:30 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 795342015 | 0 | Late | 4 | 4 | 4 | days
7.4981e+17 | Hide the fields in Quotes and Enquiry module for all the layouts as well | Aishwarya T | None | 2024-01-24 09:30 | 2024-01-25 19:00 | 2024-01-24 10:48 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | R & d payroll | Nikita Srivastava | None |  |  | 2024-01-24 19:30 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Button - PDF Preview and Push attachment in Creator | Ayush Singh | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-22 21:48 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 56 | Late | 57 | 57 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | External Lead App Historical data Discussion | Anusha V | None | 2024-01-23 09:30 | 2024-02-02 19:00 | 2024-01-25 09:21 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 34 | Late | 45 | 45 | 9 | days
7.4981e+17 | Addition Of Branch Name in RM/RL Masters , functionality and scheduler Testing | Anusha V | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-22 20:13 | In Progress | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 59 | Late | 60 | 60 | 1 | days
7.4981e+17 | CCO and ICAC Funtionalities and Field Validations | Mary Nisha | None | 2024-01-24 09:30 | 2024-01-25 19:00 | 2024-01-24 15:46 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 53 | Late | 55 | 55 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Declaring refinement rules for RMSDC | Prableen Kaur | None | 2024-01-16 09:30 | 2024-01-17 19:00 | 2024-01-24 11:06 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 7 | Late | 9 | 9 | 2 | days
7.4981e+17 | RPA- Test Cases development | Stuti S. Kulshrestha | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-22 19:24 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 56 | Late | 57 | 57 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Create Users and Logins for Zoho CRM | Dharanidharan C | None | 2024-01-22 09:30 | 2024-01-23 19:00 | 2024-01-22 18:03 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 21 | Late | 23 | 23 | 2 | days |  | Clear
7.4981e+17 | Existing data to be uploaded - Renewal Deals from master file along with renewal Date | Dharanidharan C,M S Satya | None | 2024-01-24 09:30 | 2024-02-02 19:00 | 2024-01-22 17:32 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504,789497933 | 11 | Late | 21 | 21 | 8 | days |  | Clear
7.4981e+17 | Payment Integration Setup | Dharanidharan C | None | 2024-01-22 09:30 | 2024-02-20 19:00 | 2024-01-22 17:32 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 27 | Late | 57 | 57 | 22 | days |  | Clear
7.4981e+17 | Status and field updation to CRM | Mallesh M S | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-22 13:32 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 15 | Late | 16 | 16 | 1 | days |  | Clear
7.4981e+17 | Application form Integration - Accounts | Mallesh M S | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-22 13:32 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 21 | Late | 22 | 22 | 1 | days |  | Clear
7.4981e+17 | NMSDC - User Management Video preparation | Deepa Hireholi | None |  |  | 2024-01-23 09:59 | To Do | No | 0% | V-Align Marketing Activites | None | 7.4981e+17 | 7.4981e+17 |  | 800651184 | 800651184 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Major Holiday and Minor Holiday adding functionalities | Mary Nisha | High | 2024-01-22 09:30 | 2024-01-23 19:00 | 2024-01-22 16:55 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 55 | Late | 57 | 57 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Client Call ¦ Zoho Desk ¦ Customer Happiness Issue | Tanu Gupta | High | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 19:00 | Done | No | 100% | AMC - VAlign | Synup Digital Pvt Ltd - Zoho CRM & Desk ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Disable the subform delete option for records after the SBU Approval status | Swetha K | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 16:10 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Invoice Sync Issue in Zoho Books | Swetha K | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 09:59 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Stock Aging Report | Achyuth T M,Pannaga H | High | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-22 12:30 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Five-Advance Reports & Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094,795342015 | 4 | Late | 5 | 5 | 1 | days |  | Clear
7.4981e+17 | all meeting this month open and closed tasks remove todays lead on going project value and quote value except lost status, for all the users KPI | Aishwarya T | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 12:21 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Create Analytics Report in Creator | Sachin Patil | None | 2024-01-19 09:30 | 2024-01-22 19:00 | 2024-01-19 18:35 | Done | No | 100% | Stanzen_Zoho_Creator Change Request 4 | Milestone One-Implementation of Zoho Creator Change Request 4 | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 10 | Late | 14 | 14 | 2 | days
7.4981e+17 | Creation of MG Renewal in purchase and inventory. | Mary Nisha | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 14:08 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 775643568 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Analyse adapt one document's sheet with template and create report | Prableen Kaur | None | 2024-01-18 09:30 | 2024-01-19 19:00 | 2024-01-18 18:32 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 4 | Late | 6 | 6 | 2 | days
7.4981e+17 | Track Central Database Use Decrease through Sunset (4/1/24) | Albert Diaz | None | 2024-02-01 09:30 | 2024-02-22 19:00 | 2024-01-20 05:54 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 809116687 | 15 | Late | 37 | 37 | 16 | days
7.4981e+17 | Send Communication to Wave 1 Corp Members and RMSDC's | stefan bradham | None | 2024-01-22 09:30 | 2024-02-16 19:00 | 2024-01-20 05:37 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 836353936 | 4 | Late | 30 | 30 | 20 | days
7.4981e+17 | Revise and Polish Corp Email Content for Marcom Distribution | Kris Oswold | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-20 05:25 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 824545238 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Go Live Activities | Tanu Gupta | High | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-19 20:01 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 53 | Late | 54 | 54 | 1 | days
7.4981e+17 | Vigilance Masters Creation and Functionalities Updation | Anusha V | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 15:11 | In Progress | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 59 | Late | 60 | 60 | 1 | days
7.4981e+17 | Workflow Automation and custom function for Triggering Mails when form is filled | Anusha V | High | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-19 15:05 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 66 | Late | 67 | 67 | 1 | days
7.4981e+17 | Issues in Raising the Invoices | Swetha K | None | 2024-01-31 09:30 | 2024-02-07 19:00 | 2024-01-22 11:11 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 36 | Late | 44 | 44 | 6 | days
7.4981e+17 | UAT Changes(29-01-2024) | Shavi Thakur | None | 2024-01-29 09:30 | 2024-01-29 14:00 | 2024-01-19 09:40 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Five-Advance Reports & Analytics | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 11 | Late | 12 | 12 | 4.5 | hrs |  | Clear | Mohammed Yusha
7.4981e+17 | Call with Boldfit and Servetel Team for Reports | Tanu Gupta | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 20:16 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Four-Implementation of Zoho CRM Application | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 59 | Late | 60 | 60 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | SBU and Project wise Amount - Books vs Creator | Achyuth T M | High | 2024-01-19 09:30 | 2024-01-24 19:00 | 2024-01-19 14:34 | In Progress | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 54 | Late | 60 | 60 | 4 | days
7.4981e+17 | Zoho Desk Blueprint Customization | Tanu Gupta | High | 2024-01-18 09:30 | 2024-01-19 19:00 | 2024-01-18 23:01 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 59 | Late | 61 | 61 | 2 | days |  | Clear | Supril Jain
7.4981e+17 | Data analysis of application module pdfs | Prableen Kaur,Pannaga H | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 18:29 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644,795342015 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Pre Sales Support | Supril Jain | None | 2024-01-18 09:30 | 2024-01-24 19:00 | 2024-01-19 07:16 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 54 | Late | 61 | 61 | 5 | days
7.4981e+17 | Client Visit on 18-Jan-2023 | Vignesh R | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 19:23 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 60 | Late | 61 | 61 | 1 | days
7.4981e+17 | Create data template for Contacts and Accounts | Aishwarya T | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 17:40 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 60 | Late | 61 | 61 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | Data Management | Avinash Sah | None |  |  | 2024-01-20 23:22 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Activation Team API Integrations | Sai Krishna | None | 2024-01-22 09:30 | 2024-01-23 19:00 | 2024-01-19 09:54 | Done | No | 100% | QUICK HEAL - Zoho CRM & Zoho Marketing Automation | Milestone Two-Implementation of Zoho CRM – API Integrations | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 16 | Late | 18 | 18 | 2 | days
7.4981e+17 | PDF Templates - Color Coding | Ayush Singh | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-22 10:29 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 56 | Late | 57 | 57 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | PID Creation & Review | Mohammed Yusha | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 19:44 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 6 | Late | 7 | 7 | 1 | days |  | Clear
7.4981e+17 | Updating Document | Rishikesh Gogha | None | 2024-01-18 09:30 | 2024-01-19 19:00 | 2024-01-19 09:58 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Two-Payment for January2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 46 | Late | 48 | 48 | 2 | days
7.4981e+17 | Quotation creation issue | Swetha K | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 10:07 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Digitalization of order hard copies(Sales order/Service order/POB) (OTP) - Report Template | Nirmalkrishnan H | None | 2024-01-08 09:30 | 2024-01-08 17:30 | 2024-01-17 11:46 | QA level 1 Completed | Yes | 10% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 838472289 | 840979277 | 70 | Late | 71 | 71 | 8 | hrs |  | Clear | Siddharth Sharma
7.4981e+17 | UI screen for Virtual Interview | Supreeth R Kalluraya | None | 2024-01-12 09:30 | 2024-01-31 19:00 | 2024-01-18 12:54 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | Milestone Four : Development completion and Go Live of CS Certification Portal. | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 788577227 | 788577227 | 47 | Late | 67 | 67 | 14 | days |  | Clear
7.4981e+17 | UI Screen for Application review | Supreeth R Kalluraya | None | 2024-01-31 19:00 | 2024-01-31 19:00 | 2024-01-17 16:57 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | Milestone Four : Development completion and Go Live of CS Certification Portal. | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 788577227 | 788577227 | 47 | Late | 48 | 48 | 0 | days |  | Clear | Christ Bellarmine
7.4981e+17 | ABMPL-Zoho Creator Order management Demo | Vaikuntam Chowdary | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-18 09:24 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 61 | Late | 62 | 62 | 1 | days |  | Clear
7.4981e+17 | Update Payment Status in Purchase Order | Shavi Thakur | None | 2024-01-18 09:30 | 2024-01-18 13:00 | 2024-01-18 09:50 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 7 | Late | 8 | 8 | 3.5 | hrs
7.4981e+17 | #5830 Change in Confirmation Letter | Aishwarya T | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 16:32 | In Progress | Yes | 10% | Karam Safety_Zoho ONE | Milestone Five-Implementation of Zoho People | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 62 | Late | 63 | 63 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | Application Page Automation | Mallesh M S | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 09:40 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 27 | Late | 28 | 28 | 1 | days |  | Clear
7.4981e+17 | Data Import on Zoho Creator Employee Master(Field Engineer and Store Manager) And add Users | Sachin Patil | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 19:04 | Terminated/Cancelled | No | 100% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 14 | Late | 15 | 15 | 1 | days |  | Clear
7.4981e+17 | Page3&Page4 i insert functions for Application Form Workflows | Mary Nisha | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 15:31 | Development Complete | Yes | 0% | VSINTERCONNECT CR for Estore | Milestone Two-Development, UAT & Go Live of Estore CR | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 62 | Late | 63 | 63 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Testing for Quote Module | Mohammed Yusha,Tanu Gupta | High | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 23:36 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Send List of first 200 Corp to be rolled out in Wave 1 | Christ Bellarmine | None | 2024-01-17 09:30 | 2024-01-20 19:00 | 2024-01-18 01:01 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 | 2 | Late | 6 | 6 | 4 | days
7.4981e+17 | Issue with Quote 167 for ticket | Tanu Gupta | High | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 23:52 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 61 | Late | 62 | 62 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Zoho support call for unexpected error during import | Tanu Gupta | High | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 23:42 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 790157522 | 790157522 | 61 | Late | 62 | 62 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Offer Letter Changes in Recruit | Monik Chettiyar | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-17 20:31 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Zoho CRM to Zoho Books Customer Master Mass update | Monik Chettiyar | None | 2024-01-10 09:30 | 2024-01-11 19:00 | 2024-01-17 20:21 | QA level 1 Completed | Yes | 10% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 67 | Late | 69 | 69 | 2 | days |  | Clear
7.4981e+17 | Punch Access ¦ Geo Restriction | Kiran Shrivastav | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 22:31 | Done | No | 100% | AMC - VAlign | Neelgund Developers LLP ¦ Zoho People, Recruit & Payroll ¦ 19-10-2023 ¦ 18-10-2024 | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | ICICI API Test in Postman | Shavi Thakur | None | 2024-01-16 15:30 | 2024-01-16 18:00 | 2024-01-16 18:04 | In Progress | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 62 | Late | 63 | 63 | 2.5 | hrs
7.4981e+17 | create data template for Deals and SOW | Aishwarya T | None | 2024-01-17 09:30 | 2024-01-18 19:00 | 2024-01-18 10:40 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 60 | Late | 62 | 62 | 2 | days |  | Clear | Irshad Pasha
7.4981e+17 | Layout rules and validation in LEads and Deals with Mappings | Aishwarya T | None | 2024-01-16 09:30 | 2024-01-17 19:00 | 2024-01-18 10:32 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 61 | Late | 63 | 63 | 2 | days |  | Not Clear | Irshad Pasha
7.4981e+17 | #5182 Reassigning the Reporting Manager | Maninder Singh | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 09:39 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | #5819 Leads created not Visible - North 3 | Maninder Singh | Medium | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 16:10 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Push process code to Bundle | Sachin Patil | None | 2024-01-17 09:30 | 2024-01-18 19:00 | 2024-01-17 17:17 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 12 | Late | 14 | 14 | 2 | days
7.4981e+17 | Page1&Page2 i insert functions for Application Form Workflows | Mary Nisha | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 10:59 | Development Complete | Yes | 0% | VSINTERCONNECT CR for Estore | Milestone Two-Development, UAT & Go Live of Estore CR | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 62 | Late | 63 | 63 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Dharani Feedback points 11/1/24 | M S Satya | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-12 00:17 | QA level 1 Completed | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 67 | Late | 68 | 68 | 1 | days |  | Clear
7.4981e+17 | HRMS Demo_Alain Charles | Kiran Shrivastav | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 14:56 | Done | No | 100% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Solution for Debit Notes | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Solution for Payment received | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Solution for Advance Blocks | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | By Payment Entry | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | with Advance Blocks | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Item integration Testing | Waheeba Khan | None |  |  | 2024-01-16 10:36 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Two-Payment for January2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Payin Log History | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Payout and Refunds | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Payout Log History | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Auto create refund entries against credit note | Tanu Gupta | High | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-15 18:26 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Client call on trial balance update | Sai Krishna,Tanu Gupta | High | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-15 18:13 | In Progress | Yes | 10% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 753339779,790157522 | 66 | Late | 67 | 67 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | IMS support to close incident | Swetha K | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 19:43 | To Do | Yes | 0% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 66 | Late | 67 | 67 | 1 | days
7.4981e+17 | Bills Migration | Rishikesh Gogha | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-12 09:48 | To Do | Yes | 0% | Furnishka - Zoho Books | Milestone Two-Zoho Books Improvisation Services | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 59 | Late | 60 | 60 | 1 | days
7.4981e+17 | Screen Design | Avinash Sah | None |  |  | 2024-01-16 11:42 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear | Uday Desai
7.4981e+17 | Materials used during Warranty period | Shavi Thakur | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 09:21 | Development Complete | Yes | 10% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Five-Advance Reports & Analytics | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 62 | Late | 63 | 63 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Push Multiple GSTIN's in Bill from Creator to Books | Shavi Thakur,Tanu Gupta | None | 2024-01-12 16:30 | 2024-01-12 19:00 | 2024-01-12 15:00 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417,790157522 | 6 | Late | 7 | 7 | 2.5 | hrs
7.4981e+17 | #5698 Lead Performance Widget issue | Maninder Singh | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 09:28 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Dashboard - UI | Nawaz Sharief | None | 2024-01-10 09:30 | 2024-01-11 19:00 | 2024-01-11 19:03 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 841115370 | 56 | Late | 58 | 58 | 2 | days |  | Clear | Selva Bharathi
7.4981e+17 | Backend -Business Description | Nawaz Sharief | None | 2024-01-31 09:30 | 2024-02-05 19:00 | 2024-01-11 18:56 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 841115370 | 31 | Late | 37 | 37 | 4 | days |  | Not Clear
7.4981e+17 | Backend - General Info Screens | Nawaz Sharief | None | 2024-01-26 09:30 | 2024-01-30 19:00 | 2024-01-11 18:48 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 841115370 | 37 | Late | 42 | 42 | 3 | days |  | Not Clear
7.4981e+17 | Production Activity Log Stock Adjustment Issue | Vignesh R | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 11:28 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 62 | Late | 63 | 63 | 1 | days
7.4981e+17 | CRM Deployment and testing | Siddharth Sharma,Aishwarya T | None | 2024-01-11 09:30 | 2024-01-12 19:00 | 2024-01-11 21:12 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 756762742,772989157 | 13 | Late | 15 | 15 | 2 | days
7.4981e+17 | Lead Performance Widget issue | Nikita Srivastava | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 14:17 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Project status Report WE12/01 | Supreeth R Kalluraya,Stuti S. Kulshrestha | None |  |  | 2024-01-11 23:30 | In Progress | No | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 788577227 | 788577227,808004288 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Only difference item details need to show in Creator Vs Books Reports | Sachin Patil | None | 2024-02-02 09:30 | 2024-02-05 19:00 | 2024-01-12 18:50 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 42 | Late | 46 | 46 | 2 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-12 10:29 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-09 09:30 | 2024-01-10 19:00 | 2024-01-12 10:29 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 2 | Late | 4 | 4 | 2 | days
7.4981e+17 | CRM Deal to Creator SO Creation | Vaikuntam Chowdary | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-16 09:50 | In Progress | Yes | 10% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 66 | Late | 67 | 67 | 1 | days |  | Clear
7.4981e+17 | Scheduled Emails Config | Achyuth T M | High | 2024-01-24 09:30 | 2024-01-25 19:00 | 2024-01-12 13:41 | To Do | Yes | 0% | Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 53 | Late | 55 | 55 | 2 | days
7.4981e+17 | Cash Flow Query Table | Achyuth T M | High | 2024-01-17 09:30 | 2024-01-18 19:00 | 2024-01-12 13:36 | To Do | Yes | 0% | Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 60 | Late | 62 | 62 | 2 | days
7.4981e+17 | Post go live support Jan 2024 | Mohammed Yusha,Tanu Gupta | High | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 19:26 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Test from Irshad | Irshad Pasha | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 18:59 | Development Complete | Yes | 30% | Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 701341459 | 67 | Late | 68 | 68 | 1 | days |  | Clear | Sudheendra S Murthy
7.4981e+17 | Feedback on Dashboard for users | Aishwarya T | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 14:47 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 15 | Late | 16 | 16 | 1 | days
7.4981e+17 | Option to Change Lead Layout | Sai Krishna | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-10 09:53 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 67 | Late | 68 | 68 | 1 | days |  | Clear
7.4981e+17 | UI Validation Rules -Management & Controls | Avinash Sah | None | 2024-01-17 09:30 | 2024-01-23 19:00 | 2024-01-11 12:41 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176894 | 44 | Late | 51 | 51 | 5 | days |  | Clear
7.4981e+17 | Reference Screen | Rahul S S | None | 2024-01-19 09:30 | 2024-01-23 19:00 | 2024-01-11 12:34 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176551 | 44 | Late | 49 | 49 | 3 | days |  | Clear
7.4981e+17 | User Story 1 Reports rework - 11/01/24 | M S Satya | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 10:35 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 789497933 | 789497933 | 67 | Late | 68 | 68 | 1 | days |  | Clear
7.4981e+17 | Custom Function for the code validation for Portal users, customer details | unassigned | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 10:05 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | - | 67 | Late | 68 | 68 | 1 | days |  | Clear
7.4981e+17 | From Bills, can't able to create purchase return (SE1/QC/2324/13650) | Sachin Patil | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 20:00 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Not able to log pre-installation visit call. | Nikita Srivastava | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 10:13 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 56 | Late | 57 | 57 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | If I don’t put any station then system should not allow to submit details.(Pre Installation) | Nikita Srivastava | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 10:07 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 57 | Late | 58 | 58 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | PMD CCO/ICAC attchment return back to CRM and automations | Mary Nisha | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 16:08 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 68 | Late | 69 | 69 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Zing Issues - EHV - 11-01-2024 | Ranjana Poojari | None |  |  | 2024-01-11 09:56 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 |  | On Time |  | 0 | 0 | days
7.4981e+17 | School type auto populate based on Academic year | Swetha K | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 09:40 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Zoho Creator - Create Report for Estimated Cost vs Actual Cost | Tanu Gupta | High | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 21:43 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 68 | Late | 69 | 69 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Jsupay - Call with Janani for Bill View | Tanu Gupta | High | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 19:26 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Push Sales Return from shopify to Zoho Inventory | Anusuyadevi V,Tanu Gupta | None | 2024-01-09 09:30 | 2024-01-10 19:00 | 2024-01-09 20:04 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 786479121,790157522 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Auto update Payment Receipt and capture payment method | Mohammed Yusha,Anusuyadevi V,Tanu Gupta | High | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 19:37 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,786479121,790157522 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Email Correction points | Ayush Singh | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 20:43 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 68 | Late | 69 | 69 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Feedback Review | Supril Jain | None | 2024-01-10 09:30 | 2024-01-11 19:00 | 2024-01-11 08:48 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 56 | Late | 58 | 58 | 2 | days |  | Clear
7.4981e+17 | Scrum call | Kiran Shrivastav | None | 2024-01-10 09:30 | 2024-01-31 19:00 | 2024-01-10 19:10 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 34 | Late | 56 | 56 | 16 | days
7.4981e+17 | Support request on Re: Urgent : payroll processing | Irshad Pasha,Kiran Shrivastav | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 12:37 | Done | No | 100% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 701341459,791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Internal meeting with Mr. Sudhi regarding Boldfit, ICAD, and Verto | Tanu Gupta | Medium | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 19:37 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Zoho CRM Template HTML &CSS Placeholder and Testing | Monik Chettiyar | None | 2024-01-09 09:30 | 2024-01-10 19:00 | 2024-01-09 19:19 | In Progress | Yes | 10% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 68 | Late | 70 | 70 | 2 | days |  | Clear
7.4981e+17 | Lead to Deals and contact convertion | Monik Chettiyar | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-09 18:49 | QA level 1 Completed | Yes | 10% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 73 | Late | 74 | 74 | 1 | days |  | Clear
7.4981e+17 | Zoho Recruit - Email Template Changes | Monik Chettiyar | None | 2024-01-03 09:30 | 2024-01-05 19:00 | 2024-01-09 18:35 | To Do | Yes | 0% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 73 | Late | 76 | 76 | 3 | days
7.4981e+17 | Admin Access required for | Kiran Shrivastav | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 14:19 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Change the Order Status DropDown field options | Sachin Patil | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 19:05 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Order Processing Demo Application | Supril Jain | None | 2024-01-05 09:30 | 2024-01-10 19:00 | 2024-01-09 17:33 | Done | No | 100% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 61 | Late | 67 | 67 | 4 | days
7.4981e+17 | Update Vendor module with Active or Inactive Status in Zoho Creator | Shavi Thakur,Tanu Gupta | High | 2024-01-10 09:30 | 2024-01-10 12:00 | 2024-01-09 18:15 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 773081417,790157522 | 0 | Late | 1 | 1 | 2.5 | hrs
7.4981e+17 | Profit and Loss Query Table 2 | Achyuth T M | High | 2024-01-11 09:30 | 2024-01-12 19:00 | 2024-01-09 17:22 | Done | No | 100% | Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 6 | Late | 8 | 8 | 2 | days
7.4981e+17 | Zoho Creator - Multicurrency invoice | Maninder Singh,Tanu Gupta | High | 2024-01-22 09:30 | 2024-01-23 19:00 | 2024-01-09 18:36 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 782721491,790157522 | 55 | Late | 57 | 57 | 2 | days |  | Clear | Supril Jain
7.4981e+17 | Zoho Creator - Quotes Module Changes | Tanu Gupta | High | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-09 18:27 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 68 | Late | 69 | 69 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Oracle Report Changes | Achyuth T M,Pannaga H | High | 2024-01-08 09:30 | 2024-01-09 19:00 | 2024-01-09 10:11 | In Progress | Yes | 10% | Trimble Group_Zoho Books & Zoho Creator | Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094,795342015 | 69 | Late | 71 | 71 | 2 | days |  | Clear
7.4981e+17 | EHV - Zing Retry Method | Ranjana Poojari | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 09:58 | Done | No | 100% | IIFL Samasta: Zoho Creator Employee House Visit (EHV) Change Request | Milestone One- Advance Payment Zoho Creator Employee House Visit (EHV) Change Request | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 7 | Late | 8 | 8 | 1 | days |  | Clear
7.4981e+17 | Webform and page for PArtner LEads | Aishwarya T | None | 2024-01-08 09:30 | 2024-01-09 19:00 | 2024-01-08 13:30 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 69 | Late | 71 | 71 | 2 | days
7.4981e+17 | Deal module issue fixing | Anusuyadevi V | None | 2024-01-08 10:00 | 2024-01-08 11:30 | 2024-01-09 09:10 | Done | No | 100% | AMC - VAlign | Infifresh 01-01-2024 to 31-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1.5 | hrs
7.4981e+17 | CGRM enhancement for Digital lending department | Swetha K | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 14:21 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Reopen option for customer through link in closure email in all template | Swetha K | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-08 09:39 | Done | No | 100% | IIFL SAMASTA -Zoho Creator_Helpdesk CR | Milestone One-Customization and Development of Change Request for Zoho Help Desk | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 1 | Late | 2 | 2 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Capture Payment Method from shopify order | Tanu Gupta | High | 2024-01-08 09:30 | 2024-01-09 19:00 | 2024-01-08 21:06 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 3 | 3 | 2 | days
7.4981e+17 | Download PDF Feature | Subash Samuthirapandiyan | None |  |  | 2024-01-08 20:17 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | None | 7.4981e+17 | 7.4981e+17 |  | 770263143 | 770263143 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Client call for various issue in Bills | Mohammed Yusha,Shavi Thakur,Tanu Gupta | High | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-06 18:08 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,773081417,790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | MBE Search Video - Changes | Deepa Hireholi,Stuti S. Kulshrestha | None | 2024-01-08 09:30 | 2024-01-24 19:00 | 2024-01-08 14:17 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 800651184,808004288 | 54 | Late | 71 | 71 | 13 | days |  | Clear
7.4981e+17 | EQ BOM | Kalyanasundaram L | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-05 16:27 | In Progress | Yes | 10% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 74 | Late | 75 | 75 | 1 | days |  | Not Clear
7.4981e+17 | Daily Data Migration | Kalyanasundaram L | None | 2024-01-05 09:30 | 2024-01-15 19:00 | 2024-01-06 19:31 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 63 | Late | 74 | 74 | 7 | days |  | Clear
7.4981e+17 | Daily Data Migration | Pannaga H | None | 2024-01-05 09:30 | 2024-01-25 19:00 | 2024-01-05 18:35 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 795342015 | 53 | Late | 74 | 74 | 15 | days |  | Clear
7.4981e+17 | Sandbox to Live - DCL New branch | Swetha K | None | 2024-02-07 09:30 | 2024-02-08 19:00 | 2024-01-05 16:37 | In Progress | Yes | 0% | IIFL SAMASTA -New Branch Survey Enhancement | Milestone Two-Development, Configuration UAT and Go-Live of New Branch Survey Enhancement | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 39 | Late | 41 | 41 | 2 | days |  | Clear | Selva Bharathi
7.4981e+17 | TDS and TCS solutioning | Waheeba Khan | None | 2024-01-02 09:30 | 2024-01-03 19:00 | 2024-01-05 09:53 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Two-Payment for January2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 62 | Late | 64 | 64 | 2 | days
7.4981e+17 | Supply chain Zoho books | Waheeba Khan | None | 2024-01-02 09:30 | 2024-01-03 19:00 | 2024-01-04 19:08 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Two-Payment for January2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 62 | Late | 64 | 64 | 2 | days
7.4981e+17 | Configuration of Reports | Rajesh Shindagi | None | 2024-01-24 09:30 | 2024-01-25 19:00 | 2024-01-04 18:47 | In Progress | Yes | 10% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 53 | Late | 55 | 55 | 2 | days |  | Clear
7.4981e+17 | Call on Requirement gathering document | Kiran Shrivastav | None | 2024-01-08 09:30 | 2024-01-09 19:00 | 2024-01-08 15:00 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 2 | Late | 4 | 4 | 2 | days
7.4981e+17 | EI Support Tasks | Mary Nisha | None | 2024-01-10 09:30 | 2024-02-06 19:00 | 2024-01-08 11:27 | In Progress | Yes | 10% | Educational Initiatives - P&I CR | None | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 41 | Late | 69 | 69 | 20 | days |  | Clear | Dharanidharan C
7.4981e+17 | CRM - Rate Scheduler update in related submittals | Ayush Singh | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 11:03 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 70 | Late | 71 | 71 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Create the function to generate the Member ID, Associate,Alumni,Employee and Percharak id. | Nikita Srivastava | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 13:01 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 73 | Late | 74 | 74 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Client Call on New Business unit | Sai Krishna | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-05 09:42 | Done | No | 100% | AMC - VAlign | STEER Engineering Private Limited - Zoho CRM And Analytics ¦ 05-07-2023 ¦ 04-07-2024 | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 753339779 | 753339779 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Client call for tsd sign off and Quote Multicurrency Query | Mohammed Yusha,Tanu Gupta | High | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 20:35 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Remove Add and Edit Quote Item options for Approver | Anusuyadevi V | None | 2024-01-16 09:30 | 2024-01-17 19:00 | 2024-01-08 09:25 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | #5757 Client Meeting | Mohammed Yusha,Tanu Gupta | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 19:48 | Done | No | 100% | AMC - VAlign | HAPPY RELIABLE SURGERIES PRIVATE LIMITED - Zoho CRM and Zoho Form ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Client Meeting For Zoho Project Training | Mohammed Yusha,Tanu Gupta | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-01-05 16:13 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 16 | Late | 17 | 17 | 1 | days
7.4981e+17 | Requirement Discovery | Mohammed Yusha,Tanu Gupta | None | 2024-01-18 09:30 | 2024-01-19 19:00 | 2024-01-05 16:06 | Discovery Phase | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 59 | Late | 61 | 61 | 2 | days
7.4981e+17 | UI design for The NMSDC Hub landing/navigation page: all functionality and all users | Christ Bellarmine | Medium | 2024-02-08 09:30 | 2024-02-27 19:00 | 2024-01-04 21:01 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 824545238 | 81581486 | 13 | Late | 33 | 33 | 14 | days
7.4981e+17 | Year-end Zoho Updates newsletter | Deepa Hireholi | None |  |  | 2024-01-05 09:55 | To Do | No | 0% | V-Align Marketing Activites | None | 7.4981e+17 | 7.4981e+17 |  | 800651184 | 800651184 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Infifresh ¦ Zoho Invoice and Zoho CRM Integration Process | Mohammed Yusha,Tanu Gupta | High | 2024-01-04 09:30 | 2024-01-05 19:00 | 2024-01-04 22:26 | In Progress | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 73 | Late | 75 | 75 | 2 | days
7.4981e+17 | Changes in Farmer Summary | Mallesh M S | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-08 17:32 | To Do | Yes | 0% | Ecovinal Project 3 - Farmer Management | Milestone Two-Zoho Creator – Farmer Operations: Configuration and customisation, Software demo | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 778475418 | 62 | Late | 63 | 63 | 1 | days |  | Clear
7.4981e+17 | Update Mobile Number in unique ID form by Guest, Members and Associate Portal. | Nikita Srivastava | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 13:30 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 70 | Late | 71 | 71 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Develop Certification Revenue Reporting System | Christ Bellarmine | None | 2024-01-05 09:30 | 2024-03-22 19:00 | 2024-01-06 02:25 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 | -4 | On Time | 74 | 74 | 56 | days
7.4981e+17 | Project Plan WE 01/05 | Supreeth R Kalluraya,Stuti S. Kulshrestha | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 15:17 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 788577227,808004288 | 73 | Late | 74 | 74 | 1 | days |  | Clear
7.4981e+17 | Lead Notification Mails for Sam P | Nikita Srivastava | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 10:39 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | R&D on Zoho Backstage | Supril Jain | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 09:48 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 73 | Late | 74 | 74 | 1 | days
7.4981e+17 | CRM - Rate Scheduler Delete in related submittals | Ayush Singh | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 09:38 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 69 | Late | 70 | 70 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Preffered Currency option Sync in Books and Creator | Ayush Singh | None |  |  | 2024-01-05 14:11 | In Progress | No | 0% | AMC - VAlign | LAL 10 - Zoho Creator and Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Deal owner not assigned correctly for Toll free (Enquiry Source) | Sachin Patil | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 18:46 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Call with Aprajitha | Tanu Gupta | High | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 18:49 | Done | No | 100% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 2 | 2 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Client Meeting for project progress | Mohammed Yusha,Tanu Gupta | High | 2024-01-08 09:30 | 2024-01-12 19:00 | 2024-01-08 18:39 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 0 | Late | 5 | 5 | 5 | days
7.4981e+17 | CF to update the deal on revision of an estimate: fetch user for assignment | Rajesh Shindagi | Medium | 2024-01-05 09:30 | 2024-01-08 19:00 | 2024-01-04 18:16 | Development Complete | Yes | 10% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 70 | Late | 74 | 74 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | December Payroll | Kiran Shrivastav | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-04 14:37 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | People & Payroll integration | Kiran Shrivastav | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-04 14:17 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Statutory details | Kiran Shrivastav | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-04 14:17 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | Performance Module implementation | Kiran Shrivastav | None | 2024-01-22 09:30 | 2024-01-24 19:00 | 2024-01-04 14:12 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 26 | Late | 29 | 29 | 3 | days
7.4981e+17 | Separation Flow | Kiran Shrivastav | None | 2024-01-15 09:30 | 2024-01-19 19:00 | 2024-01-04 14:00 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 31 | Late | 36 | 36 | 5 | days
7.4981e+17 | Attendance Management | Kiran Shrivastav | None | 2024-01-15 09:30 | 2024-01-17 19:00 | 2024-01-04 13:58 | Development | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 61 | Late | 64 | 64 | 3 | days
7.4981e+17 | Technical Solution Document | Kiran Shrivastav | None | 2024-01-08 09:30 | 2024-01-09 19:00 | 2024-01-04 13:57 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 69 | Late | 71 | 71 | 2 | days
7.4981e+17 | Scope of Work/TSD Document | Kiran Shrivastav | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-04 13:33 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 67 | Late | 68 | 68 | 1 | days
7.4981e+17 | Interview Names | Kiran Shrivastav | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-04 13:30 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 67 | Late | 68 | 68 | 1 | days
7.4981e+17 | Status | Kiran Shrivastav | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-04 13:30 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 67 | Late | 68 | 68 | 1 | days
7.4981e+17 | Study in Institute details, click on Add new-> CLick on "Done without entering any details, one blank row is added in form. | Nikita Srivastava | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-04 12:37 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 774653652 | 69 | Late | 70 | 70 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | "Selected Yes in "Are You Interested in 80G Benefit" and submit without entering any details, validation shows PAN name is mandatory" but both PAn details fields are disappear.retest | Maninder Singh | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-04 12:30 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 69 | Late | 70 | 70 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Data Analysis Pacific South West, Puerto Rico, Southern California | Pannaga H | None | 2024-01-11 09:30 | 2024-01-12 19:00 | 2024-01-04 14:00 | Terminated/Cancelled | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 792886644 | 795342015 | 11 | Late | 13 | 13 | 2 | days
7.4981e+17 | Data Analysis- Capital Region, Carolinas Virginia,Chicago | Prableen Kaur | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 13:40 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 792886644 | 792886644 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Color Code for Premium customers meeting | Nikita Srivastava | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 13:50 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Support Activity | Mohammed Yusha,Tanu Gupta | None | 2024-01-22 09:30 | 2024-01-23 19:00 | 2024-01-04 12:14 | To Do | Yes | 0% | AMC - VAlign | Infifresh 01-01-2024 to 31-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 55 | Late | 57 | 57 | 2 | days
7.4981e+17 | Configuration of Canvas | Rajesh Shindagi | None | 2024-01-08 09:30 | 2024-01-25 19:00 | 2024-01-04 12:08 | Terminated/Cancelled | No | 100% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | -21 | On Time | -3 | -3 | 14 | days |  | Not clear
7.4981e+17 | Configuration of Wizards | unassigned | None |  |  | 2024-01-04 12:08 | To Do | No | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | - |  | On Time |  | 0 | 0 | days |  | Not clear
7.4981e+17 | Configuration of Marketing Attribution | unassigned | None |  |  | 2024-01-04 12:07 | To Do | No | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | - |  | On Time |  | 0 | 0 | days |  | Not clear
7.4981e+17 | Configuration of Schedules | Rajesh Shindagi,Monik Chettiyar | None | 2024-01-08 09:30 | 2024-01-08 16:00 | 2024-01-04 12:07 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363,792262192 | 70 | Late | 71 | 71 | 6.5 | hrs |  | Not clear
7.4981e+17 | Insert Certification Data into zoho catalyst, create new table. | Basavaraj Patil | None | 2024-01-02 09:30 | 2024-01-05 19:00 | 2024-01-04 09:59 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 73 | Late | 77 | 77 | 4 | days |  | Clear | Christ Bellarmine
7.4981e+17 | Update email -> I can enter same email ID in two different users, this should not happen, Email must be unique. | Maninder Singh | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-04 12:13 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 70 | Late | 71 | 71 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Training call | Kiran Shrivastav | None | 2024-01-04 09:30 | 2024-01-04 11:30 | 2024-01-04 10:39 | Done | No | 100% | Karam Safety_Zoho ONE | Milestone Six-Implementation of Zoho Recruit | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 2 | hrs |  | Clear
7.4981e+17 | Sign Up ->After OTP verified successfully done Mobile number field should be disable | Maninder Singh | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-04 10:29 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 73 | Late | 74 | 74 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Rate scheduler will create or update in related submittal on create and edit action | Ayush Singh,Mary Nisha | None | 2024-01-04 09:30 | 2024-01-08 19:00 | 2024-01-04 09:36 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679,775643568 | 70 | Late | 75 | 75 | 3 | days |  | Clear | Dharanidharan C
7.4981e+17 | Need to add the Item details in the Subform in "Contract Price Lists" | Vignesh R | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-03 21:56 | In Progress | Yes | 10% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 66 | Late | 67 | 67 | 1 | days |  | Clear
7.4981e+17 | Client Visit on 09-Jan-2024 | Vignesh R | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-03 21:47 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 69 | Late | 70 | 70 | 1 | days
7.4981e+17 | Rounding off to the nearest rupee for all transactions | Vignesh R | None | 2024-01-05 09:30 | 2024-01-08 19:00 | 2024-01-03 21:37 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | Zoho Purchase and Inventory | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 70 | Late | 74 | 74 | 2 | days |  | Clear
7.4981e+17 | Remove the Discount from Debit Note | Vignesh R | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-03 21:29 | In Progress | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 73 | Late | 74 | 74 | 1 | days |  | Clear
7.4981e+17 | Create Zone wise dashboard | Aishwarya T | None | 2024-01-04 09:30 | 2024-01-05 19:00 | 2024-01-04 13:00 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 3 | Late | 5 | 5 | 2 | days
7.4981e+17 | Credit Note Books Integration | Aaftab Ahmad | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-04 10:24 | Development Complete | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 776475994 | 67 | Late | 68 | 68 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Bills Books Integration | Aaftab Ahmad | None | 2024-01-08 09:30 | 2024-01-09 19:00 | 2024-01-04 10:24 | Development Complete | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 776475994 | 69 | Late | 71 | 71 | 2 | days |  | Clear | Waheeba Khan
7.4981e+17 | TCS Books Integration | Aaftab Ahmad | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 10:24 | Development Complete | Yes | 10% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 776475994 | 74 | Late | 75 | 75 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Customer Master Books Integration | Aaftab Ahmad | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-04 10:24 | Development Complete | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 776475994 | 73 | Late | 74 | 74 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Digitalization of Installation Report (OTP)Report Template | Siddharth Sharma,Vishnu D A | None | 2024-01-09 09:30 | 2024-01-11 19:00 | 2024-01-04 09:55 | In Progress | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742,838472289 | 67 | Late | 70 | 70 | 3 | days |  | Clear
7.4981e+17 | iDatalytics Scrum Meeting | Stuti S. Kulshrestha | None | 2024-01-04 16:30 | 2024-01-04 19:00 | 2024-01-03 16:55 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 808004288 | 74 | Late | 75 | 75 | 2.5 | hrs |  | Clear
7.4981e+17 | Internal Meeting | Vishnu D A | None | 2024-01-01 09:30 | 2024-01-31 19:00 | 2024-01-03 15:50 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 838472289 | 838472289 | 47 | Late | 78 | 78 | 23 | days |  | Not Clear
7.4981e+17 | Custom Reports & Dashboards- Renewal | Dharanidharan C | None | 2024-01-18 09:30 | 2024-01-19 19:00 | 2024-01-03 18:25 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 10 | Late | 12 | 12 | 2 | days
7.4981e+17 | Configuration Member Opportunity Module (i.e. Deals Module)- Renewal | Dharanidharan C | None | 2024-01-17 09:30 | 2024-01-19 19:00 | 2024-01-03 17:32 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 10 | Late | 13 | 13 | 3 | days
7.4981e+17 | Custom Reports & Dashboards- Portal | Dharanidharan C | None | 2024-01-11 09:30 | 2024-02-16 19:00 | 2024-01-03 17:23 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | -14 | On Time | 23 | 23 | 27 | days
7.4981e+17 | QA - Release 3 | Dharanidharan C,Stuti S. Kulshrestha | None | 2024-01-11 09:30 | 2024-02-19 19:00 | 2024-01-03 17:17 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504,808004288 | -17 | On Time | 23 | 23 | 28 | days
7.4981e+17 | Creation of Industry Matrix and allocation | Dharanidharan C | None | 2024-01-03 09:30 | 2024-01-17 19:00 | 2024-01-03 17:14 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 12 | Late | 27 | 27 | 11 | days
7.4981e+17 | Integration of CRM To Zoho Books (new account and removal of old POC ) | Dharanidharan C | None |  |  | 2024-01-03 17:10 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Workflow & Automations- Application Submission Stage | Dharanidharan C | None | 2023-12-26 09:30 | 2024-01-17 19:00 | 2024-01-03 17:08 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 12 | Late | 35 | 35 | 17 | days
7.4981e+17 | UI & Creation of Membership Application Form | Christ Bellarmine,Dharanidharan C | None | 2024-01-01 19:00 | 2024-03-29 19:00 | 2024-01-03 17:05 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 81581486,701371504 | -11 | On Time | 78 | 78 | 64 | days
7.4981e+17 | QA - User Story 1 & 2- Internal | Christ Bellarmine,Dharanidharan C,Stuti S. Kulshrestha | None | 2024-01-02 19:00 | 2024-01-17 19:00 | 2024-01-03 16:53 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 81581486,701371504,808004288 | 12 | Late | 28 | 28 | 11 | days
7.4981e+17 | Create User Profiles & Permissions to be set | Dharanidharan C | None | 2023-12-18 09:30 | 2024-03-15 19:00 | 2024-01-03 16:08 | In Progress | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 3 | Late | 92 | 92 | 65 | days
7.4981e+17 | Configuration Member Inquiry Layout (i.e. in Leads Module) | Dharanidharan C | None | 2023-12-18 09:30 | 2024-01-22 19:00 | 2024-01-03 16:04 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | -12 | On Time | 24 | 24 | 26 | days
7.4981e+17 | Data Migration - Payment Module/Historical reports | Dharanidharan C | None | 2024-01-05 09:30 | 2024-02-09 19:00 | 2024-01-03 15:42 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 13 | Late | 49 | 49 | 26 | days
7.4981e+17 | Visits not getting locked after 7 days | Nikita Srivastava | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 10:54 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Leads Conversion Changes and development | M S Satya | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-04 12:12 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 73 | Late | 74 | 74 | 1 | days |  | Clear
7.4981e+17 | EMail integration not possible - 4995 | Supril Jain | None | 2024-01-04 09:30 | 2024-01-08 19:00 | 2024-01-04 09:38 | To Do | Yes | 0% | AMC - VAlign | OSBORN LIPPERT INDIA PVT. LTD. - Zoho CRM ¦ 19-05-2023 ¦ 18-05-2024 | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 70 | Late | 75 | 75 | 3 | days
7.4981e+17 | I can submit scholarship form multiple time for same student. (don't allow multiple times). | Maninder Singh | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-03 11:03 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 74 | Late | 75 | 75 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Digital coordinator login -> Scholarship Digital Coordinator Report-> why we are giving option to duplicate entry? | Maninder Singh | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 10:58 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 75 | Late | 76 | 76 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Client Visit 03-Jan-2023 | Vignesh R | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 10:23 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 75 | Late | 76 | 76 | 1 | days
7.4981e+17 | Farmer summary Changes | Mallesh M S | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-04 10:06 | In Progress | Yes | 10% | Ecovinal Project 3 - Farmer Management | None | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 66 | Late | 67 | 67 | 1 | days |  | Clear
7.4981e+17 | Zoho Campaign to CRM Integration | Nikita Srivastava | None | 2024-01-11 09:30 | 2024-01-12 19:00 | 2024-01-03 23:32 | To Do | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 774653652 | 66 | Late | 68 | 68 | 2 | days
7.4981e+17 | Assignment Rule - Enquiry | Nikita Srivastava | None | 2024-01-10 09:30 | 2024-01-12 19:00 | 2024-01-03 23:26 | To Do | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 774653652 | 66 | Late | 69 | 69 | 3 | days
7.4981e+17 | Client Visit on 03-Jan-2024 | Vignesh R | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 14:35 | Done | No | 100% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 1 | Late | 2 | 2 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Assign owner to deal for new FB Campaign Form deal | Sachin Patil | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 18:31 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Scheduler : Update email message in V5 | Ayush Singh | None | 2024-01-11 09:30 | 2024-01-12 19:00 | 2024-01-03 18:20 | Done | No | 100% | AMC - VAlign | First Meridian - Start Date - 01-05-2023 and End Date - 30-04-2024 | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | -7 | On Time | -5 | -5 | 2 | days
7.4981e+17 | Scheduler : To update the status if ends date passed | Ayush Singh | None | 2024-01-10 09:30 | 2024-01-11 19:00 | 2024-01-03 17:08 | Done | No | 100% | AMC - VAlign | First Meridian - Start Date - 01-05-2023 and End Date - 30-04-2024 | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | -6 | On Time | -4 | -4 | 2 | days
7.4981e+17 | Permission Access Modifications | Mary Nisha | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 14:32 | Development Complete | Yes | 10% | Educational Initiatives - P&I CR | None | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 75 | Late | 76 | 76 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Ticket #5800: Fix the Vendor and Bill Integration | Shavi Thakur,Tanu Gupta | None | 2024-01-04 09:30 | 2024-01-04 13:00 | 2024-01-04 16:59 | Done | No | 100% | AMC - VAlign | JUSPAY technologies | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417,790157522 | 14 | Late | 15 | 15 | 3.5 | hrs
7.4981e+17 | Post Go Live Support Meeting | Anusuyadevi V,Tanu Gupta | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-04 10:41 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121,790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | R&d Zoho Expense | Nikita Srivastava | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 19:52 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | Purchase Management Flow testing | Mohammed Yusha,Vaikuntam Chowdary | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-03 17:21 | Done | No | 100% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 701373265,778472746 | 10 | Late | 11 | 11 | 1 | days |  | Clear
7.4981e+17 | Weekly Project Status Update Meeting | Irshad Pasha,Mohammed Yusha,Tanu Gupta | High | 2024-01-03 09:30 | 2024-02-01 19:00 | 2024-01-03 16:50 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701341459,701373265,790157522 | 0 | Late | 30 | 30 | 22 | days
7.4981e+17 | Supply Workflow Solutioning | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | EffortHours and Solution on Advance and Credit Blocks | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Advane and Credit blocks - Use case Understanding and mapping with Phase one | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Advane and Credit blocks - Requirments | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Zoho - Way - Ahead | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Phase I discussion | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Zoho CRM Template Creation | Monik Chettiyar | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 19:13 | In Progress | Yes | 10% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 76 | Late | 77 | 77 | 1 | days |  | Clear
7.4981e+17 | RFQ/BOM Modification | Sai Krishna | None | 2024-01-10 09:30 | 2024-01-11 19:00 | 2024-01-03 09:35 | To Do | Yes | 0% | AMC - VAlign | VSI-Estore | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 67 | Late | 69 | 69 | 2 | days
7.4981e+17 | VSI AMC Support Jan 24 FF | Sai Krishna | None | 2024-01-02 09:30 | 2024-01-15 19:00 | 2024-01-03 09:26 | To Do | Yes | 0% | AMC - VAlign | VSI-Estore | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 63 | Late | 77 | 77 | 10 | days
7.4981e+17 | 3CDN AMC Support Jan 23 FF | Sai Krishna | None | 2024-01-02 09:30 | 2024-01-15 19:00 | 2024-01-03 09:21 | Done | No | 100% | AMC - VAlign | CTW Systems Private Limited ¦ Zoho One ¦ 27-09-2023 ¦ 26-092024 | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 49 | Late | 63 | 63 | 10 | days
7.4981e+17 | Internal meeting with achyuth for effort estimations | Achyuth T M,Tanu Gupta | High | 2024-01-02 09:30 | 2024-01-05 19:00 | 2024-01-02 23:27 | In Progress | Yes | 0% | AMC - VAlign | ICAD AMC Support Issue | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 708853094,790157522 | 73 | Late | 77 | 77 | 4 | days
7.4981e+17 | Discussion on 2nd shift attendance error | Kiran Shrivastav | None | 2024-01-04 09:30 | 2024-01-05 19:00 | 2024-01-03 09:56 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Working on the Buglist points | Nikita Srivastava | None | 2024-01-02 09:30 | 2024-01-03 19:00 | 2024-01-02 18:55 | Terminated/Cancelled | No | 100% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 1 | Late | 3 | 3 | 2 | days |  | Clear
7.4981e+17 | Export as PDF in tile view | Avinash Sah | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 18:29 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 | 76 | Late | 77 | 77 | 1 | days |  | Clear
7.4981e+17 | MBE Search - Training video manual | unassigned | None |  |  | 2024-01-03 09:50 | To Do | No | 0% | V-Align Marketing Activites | None | 7.4981e+17 | 7.4981e+17 |  | 800651184 | - |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | UAT Changes In Vendor Bill, PO, Vendor Master | Aaftab Ahmad | None | 2024-01-02 09:30 | 2024-01-08 19:00 | 2024-01-02 18:03 | In Progress | Yes | 0% | Educational Initiatives - P&I CR | None | 7.4981e+17 | 7.4981e+17 |  | 776475994 | 776475994 | 70 | Late | 77 | 77 | 5 | days |  | Clear | Waheeba Khan
7.4981e+17 | Client Meeting | Vishnu D A | None | 2024-01-02 09:30 | 2024-01-31 19:00 | 2024-01-02 16:01 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 838472289 | 838472289 | 47 | Late | 77 | 77 | 22 | days |  | Clear
7.4981e+17 | Packages and Shipment Training | Rishikesh Gogha | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-03 07:58 | Done | No | 100% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 11 | Late | 12 | 12 | 1 | days |  | Clear
7.4981e+17 | PICKLISTING FEATURE | Rishikesh Gogha | None | 2023-12-21 09:30 | 2023-12-21 19:00 | 2024-01-02 14:59 | Done | No | 100% | SPERA - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | BETTERPLACE: Adding bank acc and categorizing | Rishikesh Gogha | None | 2023-12-12 09:30 | 2023-12-12 19:00 | 2024-01-02 14:38 | Done | No | 100% | AMC - VAlign | Betterplace | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 23 | Late | 24 | 24 | 1 | days
7.4981e+17 | RE: Re:RE: Re:[## 93497350 ##] Request For Call Back [ Im stuck, need assistance ] | Rishikesh Gogha | None | 2023-12-07 09:30 | 2023-12-07 19:00 | 2024-01-02 14:18 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | MSME TAG LINE FOR ALL INVOICES-ALL ENTITIES | Mohan Kumar | None | 2023-12-28 09:30 | 2023-12-29 19:00 | 2024-01-02 10:37 | Done | No | 100% | Machani Dedicated Resource | Milestone Ten-December 2023 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 5 | Late | 7 | 7 | 2 | days |  | Clear
7.4981e+17 | Purchase Order - Mapping | Mallesh M S | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-02 10:27 | To Do | Yes | 0% | The Yarn Bazar - TYBZ - CR001 | Milestone Two-Completion of Solution Development, Testing and Zoho Creator CR Go - Live | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 73 | Late | 74 | 74 | 1 | days |  | Clear
7.4981e+17 | EI Queries | Waheeba Khan | None | 2023-10-20 09:30 | 2023-10-20 19:00 | 2024-01-02 11:49 | In Progress | Yes | 0% | Educational Initiatives - P&I CR | None | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 150 | Late | 151 | 151 | 1 | days |  | Clear
7.4981e+17 | Re-Quotation Functionality | Anusuyadevi V,Tanu Gupta | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-02 10:37 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121,790157522 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Quote Module Form Creation | Anusuyadevi V,Tanu Gupta | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 10:35 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121,790157522 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | PDF Level Fields Creation and Customization | Ayush Singh,Mary Nisha | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 10:30 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679,775643568 | 76 | Late | 77 | 77 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Payroll support request by Surekha Mainkar | Kiran Shrivastav | None | 2023-12-29 09:30 | 2023-12-29 19:00 | 2024-01-02 10:29 | Done | No | 100% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Import of COA | Stuti S. Kulshrestha | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 18:05 | To Do | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Trips / Travel Requirement Gathering Call | Mohammed Yusha,Sai Krishna,Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 09:39 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Five-Implementation of Zoho Expense - Employee Expense & Claims / Reimbursements | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 7.013732657533397E35 | 3 | Late | 4 | 4 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Change the img tag src from development stage | Pavan S | None | 2024-03-16 10:00 | 2024-03-16 14:00 | 2024-03-16 12:55 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 845599619 | 845599619 | 2 | Late | 3 | 3 | 4 | hrs |  | Not Clear
7.4981e+17 | CGRM and Admin module master data support | Swetha K | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 17:45 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Reversal of invoice - 5002504 Temp/INV/2027 | Swetha K | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 11:52 | To Do | Yes | 0% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Zoho Books- Issue with user accessibility | Tanu Gupta | High | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 18:07 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 3 | Late | 4 | 4 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | students are not showingup in joinee but in attendance they are. | Ayush Singh | None |  |  | 2024-03-15 13:14 | In Progress | No | 10% | TMSB - Next-Gen Learning Transformation with Zoho Creator Enhancement | Milestone Two- Zoho Creator Existing system improvisation | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 |  | On Time |  | 0 | 0 | days |  | Clear | Dharanidharan C
7.4981e+17 | Meeting with Sourabh Multi SSF Apis - Asset | Ayush Singh | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 09:23 | In Progress | Yes | 0% | AMC - VAlign | First Meridian - Start Date - 01-05-2023 and End Date - 30-04-2024 | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Validate Output Report of CRM Data from Zoho | Hiren Vakharia | High | 2024-03-15 09:30 | 2024-03-18 19:00 | 2024-03-15 21:05 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 828527327 | 811424903 | -3 | On Time | 1 | 1 | 2 | days
7.4981e+17 | Create Function in Desk to fetch Warranty Period from Products On Ticket and Update to Ticket based on Invoice Date | Sachin Patil | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 17:21 | To Do | Yes | 0% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Form Structure creation for the Product Code Generation | Kalyanasundaram L | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-15 11:52 | In Progress | Yes | 10% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Two-Zoho Creator – OrderManagementApplication | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 819676542 | 3 | Late | 4 | 4 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Made changes into the Internal Comment form as discussed with selva | Twinkle Gupta | None |  |  | 2024-03-15 10:31 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 848014979 | 848014979 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Dash Board Creation | M S Satya | None | 2024-03-14 09:30 | 2024-03-15 19:00 | 2024-03-15 01:15 | In Progress | Yes | 10% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 3 | Late | 5 | 5 | 2 | days |  | Clear
7.4981e+17 | Auto Payment knock off Form and Solution payouts | Waheeba Khan | None |  |  | 2024-03-15 16:18 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Zoho Support call | Mohammed Yusha,Kiran Shrivastav | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-15 13:59 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 701373265791842987 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | References | Subash Samuthirapandiyan | None |  |  | 2024-03-14 21:12 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 770263143 | 770263143 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Testing Project Discovery till Project Initialization | Mohammed Yusha,Tanu Gupta | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 17:48 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265790157522 | 4 | Late | 5 | 5 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Testing mapped fields | Vikram Pai V | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 15:16 | Done | No | 100% | iDATALYTCS UI PATH | None | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 845596686 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Client Meeting For Zoho Desk | Monik Chettiyar | None | 2024-03-14 19:00 | 2024-03-14 19:00 | 2024-03-14 16:00 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 4 | Late | 5 | 5 | 0 | days
7.4981e+17 | Mail preparation for Scope of Zoho recruit Revamp | Kiran Shrivastav | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 11:59 | To Do | Yes | 0% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Ownership Details(CBI,IOBI,TBI) form populate upload fields based on user inputs | Pavan S | None | 2024-03-13 09:30 | 2024-03-14 19:00 | 2024-03-14 12:55 | Ready for QC | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 845599619 | 845599619 | 4 | Late | 6 | 6 | 2 | days |  | Not Clear | Selva Bharathi
7.4981e+17 | POC Creation for NMSDC Zoho Connect | Manish | None |  |  | 2024-03-14 18:27 | To Do | No | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 833052784 | 833052784 |  | On Time |  | 0 | 3 | hrs
7.4981e+17 | Bonded User Manual | Waheeba Khan,Anusha V | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-03-14 13:27 | To Do | Yes | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250795545761 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Excel sheet preparation ofr PR and VO | Aishwarya T | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 16:48 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 4 | Late | 5 | 5 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Add New Field 'Re-Work Quantity' to Rejection Entry and Add Validation on Re-Work Quantity | Sachin Patil | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 14:56 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Learning Creator | Pavan S | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 10:52 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 845599619 | 845599619 | 4 | Late | 5 | 5 | 1 | days |  | Not Clear
7.4981e+17 | Internal call | Sai Krishna | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-14 09:34 | To Do | Yes | 0% | QUICK HEAL - Zoho CRM & Zoho Marketing Automation | Milestone Three-Implementation of Zoho Marketing Automation –Assistance on Building Journeys | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Machani Dedicated Resource. | Mohan Kumar | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 09:05 | In Progress | Yes | 0% | Machani Dedicated Resource extension | Milestone One-Dedicated Resource for March 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Change address to subfotm | Anusuyadevi V | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 09:31 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Add button on Books Items Report, to Adjust Stock to Zoho Creator Inventory | Sachin Patil | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 11:24 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 4 | Late | 5 | 5 | 1 | days |  | Clear
7.4981e+17 | KickOff meeting | M S Satya | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 23:26 | Done | No | 100% | Prodevans - Zoho Projects | Milestone Three-AMC for Software support charges (Yearly Billing) - Zoho Projects (50 Hours) | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Feasibility check call with Zoho support for 9 box and Spot award | Kiran Shrivastav | None | 2024-03-14 09:30 | 2024-03-14 19:00 | 2024-03-14 09:22 | To Do | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | OMSDC -Data mapping | Pannaga H | None |  |  | 2024-03-14 09:34 | To Do | No | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 795342015 | 795342015 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Discussion on Open Issues | Vignesh R | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 17:24 | In Progress | Yes | 10% | Trimble Group_Zoho Books & Zoho Creator | Zoho Purchase and Inventory | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | Customer Queries | Rishikesh Gogha | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 17:26 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | Discussion with Client | Waheeba Khan,Vignesh R,Basavaraj Patil | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 16:11 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 6.713732507041757E26 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | Weekly Scrum Call [13-03-2024] | Mohammed Yusha,Tanu Gupta | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 16:38 | Discovery Phase | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265790157522 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Supply Chain Analytics | Supril Jain | None | 2024-03-11 09:30 | 2024-03-27 19:00 | 2024-03-13 13:48 | To Do | No | 0% | (BoldFit) Sasvat_Zoho One | Milestone Six-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | -9 | On Time | 8 | 8 | 13 | days |  | Clear
7.4981e+17 | Marketing Activities | Deepa Hireholi | None |  |  | 2024-03-13 15:00 | To Do | No | 0% | V-Align Marketing Activites | None | 7.4981e+17 | 7.4981e+17 |  | 800651184 | 800651184 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Journal Deletion Issue | Rishikesh Gogha | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 14:15 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 5 | Late | 6 | 6 | 1 | days |  | Not Clear | Waheeba Khan
7.4981e+17 | Payment Matrix From Creation and Dynamic Amount Calculation | Kalyanasundaram L | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 11:33 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 819676542 | 5 | Late | 6 | 6 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Call on 9 box matrix with Archana | Kiran Shrivastav | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-03-13 09:25 | In Progress | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Show alert if budget amount is exceeded while creating purchase indent and sending approval | Sachin Patil | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 16:59 | To Do | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | AI/ML/NLP weekly discussion. | Rishikesh Gogha | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 12:45 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Document Exploration | Aman Kumar | None |  |  | 2024-03-13 15:06 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Field level updation in functions | Mary Nisha | High | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 18:16 | In Progress | Yes | 10% | StaffDocs | None | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 6 | Late | 7 | 7 | 1 | days |  | Clear
7.4981e+17 | Call with Samasta Team and Scrum Call | Ranjana Poojari | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 16:39 | In Progress | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Testing of Incoming Payments | Anusuyadevi V | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 14:56 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Sales Stand-up Meeting | P Renuka Choudhary,Naveen M | None |  |  | 2024-03-13 13:30 | To Do | No | 0% | Sales Activities | None | 7.4981e+17 | 7.4981e+17 |  | 829366386 | 765907894,829366386 |  | On Time |  | 0 | 0 | days |  | Not Clear
7.4981e+17 | Full Stack Development Discussion | Rajesh Shindagi,Prableen Kaur,Aman Kumar | None |  |  | 2024-03-13 12:31 | In Progress | No | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363,792886644,839251991 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Internal Meeting | Pavan S,Amrutha H V | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 10:53 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 845599619 | 845599619,845600661 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Working on March Deliverables | Nirmalkrishnan H | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 09:08 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 840979277 | 840979277 | 5 | Late | 6 | 6 | 1 | days |  | Not Clear
7.4981e+17 | Develop Bot to download data from Adapt One and migrate data to NMSDC Hub | Prableen Kaur | None | 2024-03-19 09:30 | 2024-03-21 19:00 | 2024-03-12 19:08 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 792886644 | 792886644 | -3 | On Time | 0 | 0 | 3 | days
7.4981e+17 | Man Power Gap Module Support & Clarifications | Anusha V | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 13:03 | In Progress | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 6 | Late | 7 | 7 | 1 | days |  | Clear
7.4981e+17 | Feedback points customization of Vendor Onboarding | Aishwarya T | None | 2024-03-13 09:30 | 2024-03-30 19:00 | 2024-03-13 15:20 | QA level 2 in progress | No | 60% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | -12 | On Time | 6 | 6 | 14 | days |  | Clear | Sai Krishna
7.4981e+17 | UAT support | Swetha K | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 11:37 | To Do | Yes | 0% | IIFL SAMASTA - IMS Enhancement 3.5 | Milestone Two-Zoho Creator: Customization, Configuration, Testing and Go-Live of IMS enhancement | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Spring boot controllers and Services | Anas Ahmed | None |  |  | 2024-03-13 09:46 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Make the subform Mandatory by layout rule for accounts module | Nikita Srivastava | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 09:16 | In Progress | Yes | 0% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Payment made to be updated from books to creator against a vendor bill in a subform | Sai Krishna,Aishwarya T | None | 2024-03-12 09:30 | 2024-03-22 19:00 | 2024-03-12 13:06 | QA level 2 in progress | No | 60% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | -4 | On Time | 7 | 7 | 9 | days |  | Clear | Sai Krishna
7.4981e+17 | zoho support meeting | Monik Chettiyar | None | 2024-03-13 19:00 | 2024-03-13 19:00 | 2024-03-13 15:55 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 5 | Late | 6 | 6 | 0 | days
7.4981e+17 | Solutioning For RCM & Currency | Mohammed Yusha | None | 2024-03-13 09:30 | 2024-03-14 19:00 | 2024-03-13 12:52 | In Progress | Yes | 0% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Four-Financial Accounting Management System | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 4 | Late | 6 | 6 | 2 | days |  | Clear
7.4981e+17 | Business Description - Function Creation for Insert record - Recertification Process | Amrutha H V | None | 2024-03-13 09:30 | 2024-03-14 19:00 | 2024-03-13 11:30 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 778475418 | 845600661 | 4 | Late | 6 | 6 | 2 | days |  | Clear
7.4981e+17 | General Information - Function Creation for Insert record - Recertification Process | Mallesh M S | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 11:24 | Development Complete | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 778475418 | 778475418 | 5 | Late | 6 | 6 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Call with ZOho Support team for Calendar issue | Kiran Shrivastav | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 18:24 | To Do | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Boldfit ¦ Zoho Books ¦ Call to align team for Data Migration | Rishikesh Gogha,Tanu Gupta,Shiwani Kumari | High | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 16:27 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 745115006,790157522,844784545 | 6 | Late | 7 | 7 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Status Update API Creation and Cashback API Creation | Anusuyadevi V | None | 2024-03-13 09:30 | 2024-03-13 19:00 | 2024-03-13 16:16 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Daily Stand Up call with client | Siddharth Sharma | None |  |  | 2024-03-13 10:21 | To Do | No | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Migrate Corp Plus Data | unassigned | None | 2024-03-12 09:30 | 2024-03-22 19:00 | 2024-03-12 21:21 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | - | -4 | On Time | 7 | 7 | 9 | days
7.4981e+17 | Zoho CRM API Integration | Monik Chettiyar | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 11:14 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Push to IRP, Generate IRN ,Acknowledgement Date and No and show in Invoice. | Basavaraj Patil | None | 2024-03-11 09:30 | 2024-03-15 19:00 | 2024-03-12 10:25 | To Do | Yes | 10% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 3 | Late | 8 | 8 | 5 | days |  | Clear | Waheeba Khan
7.4981e+17 | Daily stand up call | Sai Krishna,Aishwarya T | None | 2024-03-11 09:30 | 2024-03-29 19:00 | 2024-03-12 10:10 | To Do | No | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | -11 | On Time | 8 | 8 | 15 | days |  | Clear | Sai Krishna
7.4981e+17 | Approval flow issue | Kiran Shrivastav | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 09:53 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Zoho Books Internal call | Rishikesh Gogha | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 10:55 | To Do | Yes | 0% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 6 | Late | 7 | 7 | 1 | days |  | Clear
7.4981e+17 | POB details – live dashboard FLSP wise which needs to be a built up for Region and Zone . All parameters (inclusive of all pack size) – This is required to drive the campaigns live during the field working time. | Siddharth Sharma | None |  |  | 2024-03-12 09:30 | To Do | No | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Preparation of Demo | Devaraju S J | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 18:45 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | For IGL new branch, split branch, or premise change in the admin module DM should be taking action, if it is for IL, instead of DM should be CSM (cluster sales manager) and if it is DCL, instead of DM it should be CM. Please check on this because while going through one of the live cases, we noticed for IGL, instead of DM it was showing CSM. | Swetha K | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 15:07 | Done | No | 100% | IIFL SAMASTA- Admin Module CR | None | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Hierarchy Set , Integration with MM Module | Anusha V | High | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 10:01 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 20:47 | In Progress | Yes | 0% | Machani Dedicated Resource extension | Milestone One-Dedicated Resource for March 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Change of Approval Process for Operations team | Rishikesh Gogha | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 17:09 | To Do | Yes | 0% | Airowire - Zoho Expense | None | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Demo Walkthrough of CRM | Dharanidharan C | None | 2024-03-12 09:30 | 2024-03-19 19:00 | 2024-03-12 04:24 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 701371504 | -1 | On Time | 7 | 7 | 6 | days
7.4981e+17 | Enable the Make Payment Option & SVG Percentage Dinamic - Applicant Dashboard Dynamic | Mallesh M S | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 16:42 | Ready for QC | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 778475418 | 778475418 | 7 | Late | 8 | 8 | 1 | days |  | Clear
7.4981e+17 | Zoho Payroll integration fetch salary info | Tanu Gupta | High | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 10:05 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 2 | Late | 3 | 3 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | check the feasibility to track the how many email is sent to user by manually | Nikita Srivastava | None | 2024-03-12 09:30 | 2024-03-12 19:00 | 2024-03-12 09:27 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Support with Item Master | Tanu Gupta | Medium | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 16:35 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 7 | Late | 8 | 8 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Establish Roll out plan by User Type | Dharanidharan C,Hiren Vakharia | None | 2024-03-11 09:30 | 2024-03-18 19:00 | 2024-03-11 14:24 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504,811424903 | 0 | On Time | 8 | 8 | 6 | days
7.4981e+17 | Pipeline Data Migration | Dharanidharan C | None | 2024-01-09 09:30 | 2024-03-13 19:00 | 2024-03-11 14:13 | In Progress | Yes | 90% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 5 | Late | 70 | 70 | 47 | days
7.4981e+17 | Not Able to Approve the Pending Payment For Approval | Swetha K | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 13:15 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Creation of Request Payload for Douments - with Custom API | Anusuyadevi V | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 11:23 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Internal Team Catchup | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-11 09:30 | 2024-03-15 19:00 | 2024-03-11 09:40 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288,844784545 | 3 | Late | 8 | 8 | 5 | days
7.4981e+17 | Workflow/rules for fields-Management Description | Aman Kumar | None |  |  | 2024-03-08 20:01 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | WOVA - International Women's Day Celebration | Tanu Gupta | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 16:57 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-26 09:30 | 2024-03-15 19:00 | 2024-03-11 10:44 | Done | No | 100% | Machani Dedicated Resource extension | Milestone One-Dedicated Resource for March 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | -4 | On Time | 15 | 15 | 15 | days
7.4981e+17 | Pre Sales Call IITPL | Supril Jain | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 11:02 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Dashboard Analytics Issue | Supril Jain | None | 2024-03-05 09:30 | 2024-03-12 19:00 | 2024-03-11 09:29 | In Progress | Yes | 0% | AMC - VAlign | Global Learning service LLP - Zoho CRM ¦ 05-05-2023 ¦ 04-05-2024 | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 6 | Late | 14 | 14 | 6 | days
7.4981e+17 | Sending Invites on Mar 8 | Kalyanasundaram L | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-10 19:35 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 819676542 | 2 | Late | 3 | 3 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Changes in Resource Allocation while creating project | Vignesh R | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 13:21 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 7 | Late | 8 | 8 | 1 | days |  | Clear
7.4981e+17 | WOVA - International Women's Day Celebration | Shavi Thakur | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-10 23:04 | To Do | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Search Enhancement 3 (Features-------------------) | Christ Bellarmine | None |  |  | 2024-03-10 08:45 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Create Certified Shared Database Refresh Process | Hiren Vakharia | None | 2024-03-08 09:30 | 2024-03-29 19:00 | 2024-03-08 21:17 | To Do | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 811424903 | -11 | On Time | 11 | 11 | 16 | days
7.4981e+17 | Project name not synecd to Books item details | Swetha K | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 19:03 | To Do | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 10 | Late | 11 | 11 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Fix the issue of failed custom functions to zoho books | Sachin Patil | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-11 12:56 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 7 | Late | 8 | 8 | 1 | days |  | Not Clear
7.4981e+17 | Inventory Report and SO Adress Changes | Ranjana Poojari,Anusha V | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-03-11 11:43 | In Progress | Yes | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 778475421,795545761 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | ABM Dashboard Feasibility Checks and Support Team Discussion | Anusha V | None | 2024-03-06 09:30 | 2024-03-26 19:00 | 2024-03-11 09:35 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | -14 | On Time | 7 | 7 | 15 | days
7.4981e+17 | Proj Management (Timesheet Brainstorming) | Stuti S. Kulshrestha | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 15:32 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 6 | Late | 7 | 7 | 1 | days |  | Clear
7.4981e+17 | Zoho Configuration- Annual Appraisal Timelines- 2024 | Kiran Shrivastav | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-08 14:00 | Done | Yes | 10% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 14 | Late | 15 | 15 | 1 | days |  | Clear
7.4981e+17 | Weekly project status creation WE 03/08 | Supreeth R Kalluraya | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 13:08 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 788577227 | 788577227 | 10 | Late | 11 | 11 | 1 | days |  | Clear
7.4981e+17 | Set up of Branches in Expense | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 09:56 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Five-Implementation of Zoho Expense - Employee Expense & Claims / Reimbursements | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288,844784545 | 10 | Late | 11 | 11 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Demo Final Checkmate | Dharanidharan C | None | 2024-03-07 09:30 | 2024-03-13 19:00 | 2024-03-07 22:37 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 701371504 | -2 | On Time | 5 | 5 | 5 | days
7.4981e+17 | Validate Exception Report for Missing Documents | Hiren Vakharia | None | 2024-03-08 09:30 | 2024-03-11 19:00 | 2024-03-07 21:55 | In Progress | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 811424903 | 7 | Late | 11 | 11 | 2 | days
7.4981e+17 | Share field-level mapping to (NMSDC) | Christ Bellarmine | None | 2024-02-28 09:30 | 2024-03-07 19:00 | 2024-03-07 21:46 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 | 0 | Late | 9 | 9 | 7 | days
7.4981e+17 | Business Description Section- Creation of fields in HTML | Aman Kumar | None |  |  | 2024-03-07 20:50 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Management & Controls Section-Dynamic | Aman Kumar | None |  |  | 2024-03-07 20:34 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 839251991 | 839251991 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Client Call - Unicommerce Integration with Zoho Inventory | Supril Jain,Tanu Gupta | High | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 13:53 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Three-Implementation of Zoho Inventory | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 756836914,790157522 | 11 | Late | 12 | 12 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Display dynamic audit logs for "General Information" and "Contact Information" on the audit log page. | Maninder Singh | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-07 20:18 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 10 | Late | 11 | 11 | 1 | days |  | Clear
7.4981e+17 | CEEW ¦ Internal Team Catchup for Project way forward | Mohammed Yusha,Sai Krishna,Tanu Gupta | High | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 14:11 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,753339779,790157522 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Form level updations and pdf updations | Mary Nisha | High | 2024-03-07 09:30 | 2024-03-12 19:00 | 2024-03-07 12:17 | In Progress | Yes | 10% | StaffDocs | None | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 6 | Late | 12 | 12 | 4 | days |  | Clear
7.4981e+17 | Employee Master Integration - Zoho People to Creator | Tanu Gupta | High | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 11:01 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 6 | Late | 7 | 7 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Creating PPT on User Story and Use Case | Pavan S | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 09:50 | Done | No | 100% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 845599619 | 845599619 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Adding Close button to all Popup window opening in the Certification Portal | Kalyanasundaram L,Pavan S | None |  |  | 2024-03-08 09:32 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 819676542,845599619 |  | On Time |  | 0 | 0 | days |  | Clear | Selva Bharathi
7.4981e+17 | RMSDC Data Migration for 5 Company | Kalyanasundaram L | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 19:47 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 11 | Late | 12 | 12 | 1 | days |  | Clear
7.4981e+17 | TP Dash board: Date wise TP update with Area Name , No of customers per area, No of high potential customers / customer met during last 60 days / Equipment prospect per area in numbers / Reagent prospect per area in numbers | Vishnu D A,Nirmalkrishnan H | None | 2024-03-07 09:30 | 2024-03-08 18:00 | 2024-03-07 12:46 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 838472289 | 838472289,840979277 | 10 | Late | 12 | 12 | 18 | hrs |  | Not Clear | Siddharth Sharma
7.4981e+17 | Reports Creation | M S Satya | None | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-03-07 23:43 | In Progress | Yes | 10% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 3 | Late | 4 | 4 | 1 | days |  | Clear
7.4981e+17 | Business Structure | Subash Samuthirapandiyan | None |  |  | 2024-03-07 20:00 | Development Complete | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 770263143 | 770263143 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Zoho CRM Dashboard’s Meeting | Monik Chettiyar | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 15:31 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | ZOho Recruit Report Creation For candidate Module | Monik Chettiyar | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-07 12:22 | To Do | Yes | 0% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | Zoho Desk API Intgration | Monik Chettiyar | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 12:15 | To Do | Yes | 0% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | NMSDC Daily standup meeting Morning | Maninder Singh | None | 2024-03-08 09:30 | 2024-04-30 19:00 | 2024-03-08 10:57 | To Do | No | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | -43 | On Time | 11 | 11 | 38 | days
7.4981e+17 | Real-time TAT, call AVG, customer rating, spare process status, complaints, and so on | Siddharth Sharma | None |  |  | 2024-03-08 09:00 | To Do | No | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Review Summary Page UI | Avinash Sah | None | 2024-03-08 09:30 | 2024-03-11 19:00 | 2024-03-07 19:13 | Ready for QC | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 830176894 | 7 | Late | 11 | 11 | 2 | days
7.4981e+17 | Wishlist Feature UI development | Rahul S S | None |  |  | 2024-03-07 11:28 | In Progress | No | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176551 | 830176551 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Verify Creator Inventory Stock with Books Inventory Stock and Update | Sachin Patil | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-03-08 10:20 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 10 | Late | 11 | 11 | 1 | days |  | Clear
7.4981e+17 | Zoho Books Demo | Devaraju S J | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 19:11 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | Project Management Discussion with client | Mohammed Yusha,Vignesh R,Tanu Gupta | High | 2024-03-08 09:30 | 2024-03-18 19:00 | 2024-03-07 15:56 | In Progress | No | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 701373265,704175602,790157522 | 0 | On Time | 11 | 11 | 7 | days |  | Clear
7.4981e+17 | Hide and Disable Fields and Button on Credit Note(Audit) | Sachin Patil | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 13:09 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Integration Flow from Creator to Expense | Stuti S. Kulshrestha | None | 2024-03-07 09:30 | 2024-03-08 19:00 | 2024-03-07 10:15 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Five-Implementation of Zoho Expense - Employee Expense & Claims / Reimbursements | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 10 | Late | 12 | 12 | 2 | days |  | Clear
7.4981e+17 | Next follow up date : field : mandatory : a task with reminder to be created for the date. the reminder should be at 4:00 PM and 9:00 AM | M S Satya | None | 2024-03-06 09:30 | 2024-03-08 19:00 | 2024-03-07 09:24 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 10 | Late | 13 | 13 | 3 | days |  | Clear
7.4981e+17 | Modify the function to link Credit notes with Sales returns | Tanu Gupta | High | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 20:40 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Weekly Scrum Call [06-03-2024] | Irshad Pasha,Mohammed Yusha,Rishikesh Gogha,Tanu Gupta | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 17:32 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701341459,701373265,745115006,790157522 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Fields lelve customization and Custom functions to update the Contacts | Ayush Singh | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-07 09:15 | QA level 1 Completed | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 12 | Late | 13 | 13 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | restrict export for MBE, RMSDC users | Avinash Sah | None |  |  | 2024-03-06 15:32 | In Progress | No | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | ICAC CCO - Templates correction | Ayush Singh | None | 2024-03-05 09:30 | 2024-03-06 19:00 | 2024-03-06 13:28 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 12 | Late | 14 | 14 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | System Testing | M S Satya | None | 2024-03-04 09:30 | 2024-03-08 19:00 | 2024-03-06 10:04 | In Progress | Yes | 10% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 10 | Late | 15 | 15 | 5 | days |  | Clear
7.4981e+17 | Internal Discussion | Mohammed Yusha,Vignesh R,Tanu Gupta | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 11:05 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 701373265,704175602,790157522 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | API gateways and Catalyst Serverless understanding | Anas Ahmed | None |  |  | 2024-03-07 09:51 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Emai template support | Nikita Srivastava | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 17:09 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Testing & UAT | Anusha V | High | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-03-06 10:10 | To Do | Yes | 0% | IIFL Samasta: Shop Keeper Onboarding CR | Milestone One-Configuration, Development, Testing and Go-Live of Shopkeeper Onboarding CR | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | Viraj Patel ¦ Remove from portal | Rishikesh Gogha | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-06 10:00 | To Do | Yes | 0% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | IMS move to next stage and employee creation request | Swetha K | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 18:52 | To Do | Yes | 0% | IIFL SAMASTA - IMS Enhancement 3.5 | Milestone Two-Zoho Creator: Customization, Configuration, Testing and Go-Live of IMS enhancement | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Update Stock to Inventory after Add or Update Sales Return Item | Sachin Patil | None | 2024-03-06 09:30 | 2024-03-07 19:00 | 2024-03-06 16:57 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 5 | Late | 7 | 7 | 2 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-26 09:30 | 2024-03-15 19:00 | 2024-03-06 13:29 | Done | No | 100% | Machani Dedicated Resource extension | Milestone One-Dedicated Resource for March 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | -4 | On Time | 15 | 15 | 15 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-26 09:30 | 2024-03-15 19:00 | 2024-03-06 13:29 | Done | No | 100% | Machani Dedicated Resource extension | Milestone One-Dedicated Resource for March 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | -4 | On Time | 15 | 15 | 15 | days
7.4981e+17 | Working on UAT Feedback (Point Number: 19,20, 53 & 59) | Nirmalkrishnan H | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 10:44 | In Progress | Yes | 10% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 840979277 | 840979277 | 12 | Late | 13 | 13 | 1 | days |  | Clear | Siddharth Sharma
7.4981e+17 | Client call for issue in ticket notification due to wrong account access | Tanu Gupta | High | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-06 09:28 | Done | No | 100% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Pagination | Omprakash Kumar | None | 2024-02-14 09:30 | 2024-02-15 19:00 | 2024-03-05 13:53 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 845321609 | 845321609 | 19 | Late | 21 | 21 | 2 | days
7.4981e+17 | Go Live of Application Submission Process | Selva Bharathi,Supreeth R Kalluraya | None | 2024-04-03 09:30 | 2024-04-03 19:00 | 2024-03-04 21:35 | In Progress | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573,788577227 | -16 | On Time | -15 | -15 | 1 | days
7.4981e+17 | BA Testing of Application Submission forms and Workflows | Supreeth R Kalluraya | None | 2024-02-23 09:30 | 2024-03-19 19:00 | 2024-03-04 21:35 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 788577227 | -1 | On Time | 25 | 25 | 18 | days
7.4981e+17 | HTML Page Dynamic data Populations / Automations | unassigned | None |  |  | 2024-03-04 21:35 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Notifications for payment process | Kalyanasundaram L | None | 2024-03-02 09:30 | 2024-03-05 19:00 | 2024-03-04 21:35 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 819676542 | 13 | Late | 17 | 17 | 3 | days
7.4981e+17 | Tree Structure Dynamic | Mallesh M S | None | 2024-03-02 09:30 | 2024-03-02 19:00 | 2024-03-04 21:35 | Ready for QC | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 778475418 | 16 | Late | 17 | 17 | 1 | days
7.4981e+17 | Validation of Auto population of data from CRM to Creator | Kalyanasundaram L | None | 2024-03-11 09:30 | 2024-03-11 19:00 | 2024-03-04 21:35 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 819676542 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Applicant Dashbard UI | Rahul S S | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 21:35 | Ready for QC | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 830176551 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Open concerns on creator - GST for invoice no 99, crm to desk issue, creator to books info sync | Tanu Gupta | High | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-06 09:27 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 13 | Late | 14 | 14 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Presentation Practice-D | Devaraju S J | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 18:42 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Old records deletion in samasta global | Mary Nisha | High | 2024-03-04 09:30 | 2024-03-05 19:00 | 2024-03-05 10:04 | Done | No | 100% | AMC - VAlign | Columbia Pacific Communities | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 10 | Late | 12 | 12 | 2 | days
7.4981e+17 | Check working of Invoice Main Form Cancel | Sachin Patil | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 19:40 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | Check TeleCMI and Zoho CRM Integration | Sachin Patil | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 19:32 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | Call with Zoho Support for feasibility check | Kiran Shrivastav | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 20:21 | Done | No | 100% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Permission Document creation | Tanu Gupta,Kiran Shrivastav | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 11:10 | To Do | Yes | 0% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Three-Implementation of Zoho People | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 790157522,791842987 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | 3CDN AMC Support | Sai Krishna | None | 2024-02-01 09:30 | 2024-02-29 19:00 | 2024-03-04 14:25 | Done | No | 100% | AMC - VAlign | CTW Systems Private Limited ¦ Zoho One ¦ 27-09-2023 ¦ 26-092024 | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 4 | Late | 33 | 33 | 21 | days
7.4981e+17 | Project Management Demo 4.03 | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 12:46 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288,844784545 | 10 | Late | 11 | 11 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Convert WordPress Lead to Deal and Assign Owner to Deal(Guwahati and Mohali) | Sachin Patil | None | 2024-03-07 09:30 | 2024-03-07 19:00 | 2024-03-07 09:33 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Contact Information Validation | Subash Samuthirapandiyan | None |  |  | 2024-03-06 21:22 | Ready for QC | No | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 770263143 | 770263143 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Ecovinal Customer Concern-D | Devaraju S J | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-06 18:48 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Air Hoist and EDC BOM | Kalyanasundaram L | None | 2024-03-29 09:30 | 2024-03-29 19:00 | 2024-03-06 13:00 | To Do | No | 0% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | -11 | On Time | -10 | -10 | 1 | days |  | Not Clear
7.4981e+17 | Integration Fixes | Shavi Thakur | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-04 23:22 | To Do | Yes | 0% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Four-Financial Accounting Management System | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 13 | Late | 14 | 14 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Employee_API_Creation | unassigned | None |  |  | 2024-03-05 13:37 | In Progress | No | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 845321609 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | AWS knowledge Transfer by freelancer | Mohak Tripathi | None |  |  | 2024-03-05 13:20 | In Progress | No | 10% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 843614429 | 843614429 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Implementing text search on drop down | Anas Ahmed | None |  |  | 2024-03-05 10:26 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Project Overview Call - New Joinee | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 11:46 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288,844784545 | 10 | Late | 11 | 11 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Update Stock to Zoho Creator Inventory from Zoho Books Bills, Invoice, Vendor Credit and Credit Note | Sachin Patil | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 19:23 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 13 | Late | 14 | 14 | 1 | days |  | Clear
7.4981e+17 | Expense details functions for ICAC and CCO | Mary Nisha | High | 2024-02-28 09:30 | 2024-02-29 19:00 | 2024-03-05 15:35 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 18 | Late | 20 | 20 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Zoho Project standard app re-demo to ozone | Mohammed Yusha,Tanu Gupta | High | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-05 12:24 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | MOM Preparation Meeting dated 4.3.2024 | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 09:57 | Done | No | 100% | FarmIndia_Zoho One | Milestone Three-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288,844784545 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | ACL Integration and BDM Remarks Flow | Anusha V | High | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-03-05 09:37 | Done | No | 100% | IIFL Samasta: Shop Keeper Onboarding CR | Milestone One-Configuration, Development, Testing and Go-Live of Shopkeeper Onboarding CR | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | Release/Testing/Internal KT/Calls | Selva Bharathi | None | 2023-09-25 09:30 | 2023-12-30 19:00 | 2024-03-04 22:33 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573 | 79 | Late | 176 | 176 | 70 | days |  | Not Clear
7.4981e+17 | Presentation with CEO/S | Shiwani Kumari | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 19:02 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Bug Fixing | unassigned | None | 2024-04-01 09:30 | 2024-04-03 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | - | -16 | On Time | -13 | -13 | 3 | days
7.4981e+17 | Creation of reports | Twinkle Gupta | None | 2024-03-18 09:30 | 2024-03-29 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -11 | On Time | 1 | 1 | 10 | days
7.4981e+17 | Bug Fixing | Twinkle Gupta | None | 2024-04-01 09:30 | 2024-04-03 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -16 | On Time | -13 | -13 | 3 | days
7.4981e+17 | Validation of all Notifications concerning with Desk Audit | Twinkle Gupta | None | 2024-03-18 09:30 | 2024-03-28 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -10 | On Time | 1 | 1 | 9 | days
7.4981e+17 | Validation of application paused and expired | Twinkle Gupta | None | 2024-03-21 09:30 | 2024-03-22 19:00 | 2024-03-04 21:27 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | -4 | On Time | -2 | -2 | 2 | days
7.4981e+17 | Completion of Key Employee table | Aman Kumar | None | 2024-03-12 09:30 | 2024-03-13 19:00 | 2024-03-04 21:27 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 839251991 | 5 | Late | 7 | 7 | 2 | days
7.4981e+17 | Internal Escalations | Twinkle Gupta | None | 2024-03-13 09:30 | 2024-03-14 19:00 | 2024-03-04 21:27 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | 4 | Late | 6 | 6 | 2 | days
7.4981e+17 | Update Comment option and Insert into Comment Logs | Twinkle Gupta | None | 2024-03-09 09:30 | 2024-03-15 20:00 | 2024-03-04 21:27 | Development Complete | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | 3 | Late | 10 | 10 | 58 | hrs
7.4981e+17 | Version creation On Edit after Submission for all forms | Maninder Singh | None | 2024-03-06 09:30 | 2024-03-10 20:00 | 2024-03-04 21:27 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 782721491 | 8 | Late | 13 | 13 | 39 | hrs
7.4981e+17 | KT To Desk Audit Team | Twinkle Gupta | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-04 21:27 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 848014979 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Creation of Email Templates | Aman Kumar | None | 2024-03-11 09:30 | 2024-03-12 19:00 | 2024-03-04 21:27 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 839251991 | 6 | Late | 8 | 8 | 2 | days
7.4981e+17 | Validation for CS Manager to allocate application | Aman Kumar | None |  |  | 2024-03-04 21:27 | In Progress | No | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 839251991 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Creation of open work queue for CS | Aman Kumar | None | 2024-03-06 09:30 | 2024-03-06 19:00 | 2024-03-04 21:27 | Development Complete | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 839251991 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Juspay Issue Regarding User Access and Bill Integration | Shavi Thakur | None | 2024-03-05 11:30 | 2024-03-05 14:00 | 2024-03-05 21:18 | To Do | Yes | 0% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 13 | Late | 14 | 14 | 2.5 | hrs
7.4981e+17 | Change status of TE - 202400191 tour claim form SBU approved to Draft and also removed form the payment approval and ledger reports. | Maninder Singh | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-05 10:50 | In Progress | Yes | 0% | AMC - VAlign | EI - Zoho One Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | #6010 : Ticket not creating in zoho desk | Ayush Singh | None | 2024-03-01 09:30 | 2024-03-04 19:00 | 2024-03-04 20:04 | Done | No | 100% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 3 | Late | 7 | 7 | 2 | days
7.4981e+17 | Page for Quotation with Pdf integration | Aishwarya T | None | 2024-03-01 09:30 | 2024-03-15 19:00 | 2024-03-04 12:28 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 3 | Late | 18 | 18 | 11 | days |  | Clear | Sai Krishna
7.4981e+17 | New Field creation in Employee form | Kiran Shrivastav | None | 2024-03-05 09:30 | 2024-03-05 19:00 | 2024-03-04 11:00 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Internal Zoho Creator to Books Integration Demo | Shavi Thakur | None | 2024-03-01 15:30 | 2024-03-01 19:00 | 2024-03-03 21:26 | To Do | Yes | 0% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Four-Financial Accounting Management System | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 17 | Late | 18 | 18 | 3.5 | hrs |  | Clear | Mohammed Yusha
7.4981e+17 | API'S testing through Postman and Zoho Bill integration against Debit note | Vaikuntam Chowdary | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-01 18:17 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | Purchase Order Version | Ranjana Poojari | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-03-01 09:04 | Done | No | 100% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | MBE search R&D for aws and catalyst | Anas Ahmed | None |  |  | 2024-03-04 10:03 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | HO Team & FCU Team Remark Option Flow | Anusha V | High | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-03-02 12:39 | Done | No | 100% | IIFL Samasta: Shop Keeper Onboarding CR | Milestone One-Configuration, Development, Testing and Go-Live of Shopkeeper Onboarding CR | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | Vendor Bill Configuration | Aishwarya T | None | 2024-02-28 09:30 | 2024-02-29 19:00 | 2024-03-01 10:31 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 7 | Late | 9 | 9 | 2 | days |  | Clear | Sai Krishna
7.4981e+17 | On submission of purchase requisition form the user should be auto direct to all purchase requisition report, and Add Send For Approval Button on Purchase requisition report | Sai Krishna,Aishwarya T | None | 2024-02-27 09:30 | 2024-02-29 19:00 | 2024-03-01 10:24 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 7 | Late | 10 | 10 | 3 | days |  | Clear | Sai Krishna
7.4981e+17 | BDM Partial Save Flow | Anusha V | High | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-03-01 09:33 | Done | No | 100% | IIFL Samasta: Shop Keeper Onboarding CR | Milestone One-Configuration, Development, Testing and Go-Live of Shopkeeper Onboarding CR | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 17 | Late | 18 | 18 | 1 | days
7.4981e+17 | Vendor Management Prog Demo 4.3.2024 | Stuti S. Kulshrestha,Shiwani Kumari | None | 2024-03-04 09:30 | 2024-03-04 19:00 | 2024-03-04 10:48 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288,844784545 | 10 | Late | 11 | 11 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Import or update COA master. | Vignesh R,Basavaraj Patil | None | 2024-02-01 09:30 | 2024-03-08 19:00 | 2024-03-01 16:58 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | None | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 704175602,781564441 | 10 | Late | 47 | 47 | 27 | days |  | Clear | Waheeba Khan
7.4981e+17 | UAT release 2 Bug Fixes | Dharanidharan C | None | 2024-02-01 09:30 | 2024-02-29 19:00 | 2024-03-01 12:45 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 18 | Late | 47 | 47 | 21 | days |  | Clear
7.4981e+17 | UAT release 1 and updates | Dharanidharan C | None | 2024-02-01 09:30 | 2024-02-29 19:00 | 2024-03-01 12:40 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 18 | Late | 47 | 47 | 21 | days |  | Clear
7.4981e+17 | Requirement Gathering | Rishikesh Gogha | None | 2024-02-21 09:30 | 2024-02-22 19:00 | 2024-03-04 10:19 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 25 | Late | 27 | 27 | 2 | days
7.4981e+17 | Custom function for validation of allocation, resources to be hired, and user input of allocation and monthly allocation | Tanu Gupta | High | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-02 15:58 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 6 | Late | 7 | 7 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Healthplix - Zoho CRM Demo call | Tanu Gupta | High | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-02 15:45 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | In the Sales Order, add Tax and Amount fields, and perform the calculation after adding items in the item details | Sachin Patil | None | 2024-03-01 09:30 | 2024-03-01 19:00 | 2024-03-01 19:29 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | Zoho Desk Custom Function From Thirdy Party Intgration | Monik Chettiyar | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 20:29 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Project Budgeting & Internal Solutioning | Mohammed Yusha | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 19:01 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 1 | Late | 2 | 2 | 1 | days |  | Clear
7.4981e+17 | Internal Meeting | Avinash Sah | None |  |  | 2024-03-04 10:23 | In Progress | No | 10% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | System Testing | M S Satya | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-03-01 09:53 | To Do | Yes | 0% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 18 | Late | 19 | 19 | 1 | days |  | Clear
7.4981e+17 | Support for Issue in multi line item sale return and credit note | Tanu Gupta | High | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 21:44 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Delete Duplicate Item-D | Devaraju S J | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-02-29 17:54 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 18 | Late | 19 | 19 | 1 | days
7.4981e+17 | Solution Demo | Rishikesh Gogha | None | 2024-02-29 09:30 | 2024-02-29 19:00 | 2024-03-01 09:53 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 18 | Late | 19 | 19 | 1 | days
7.4981e+17 | Weekly Project status Creation WE 03/01 | Supreeth R Kalluraya | None |  |  | 2024-02-29 19:58 | Development Complete | No | 30% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 788577227 | 788577227 |  | On Time |  | 0 | 0 | days |  | Clear | Christ Bellarmine
7.4981e+17 | Implementing search on drop down | Anas Ahmed | None |  |  | 2024-02-29 19:34 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Ledger Block Release and Invoice Block Release | Vaikuntam Chowdary | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-02-29 19:30 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 17 | Late | 19 | 19 | 2 | days
7.4981e+17 | UI completion with CSS | Anas Ahmed | None |  |  | 2024-02-29 19:05 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | None | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | File handling in Redux for Level 2 & 3 of Tree Structure | Anas Ahmed | None |  |  | 2024-02-29 18:52 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | UI for Level 3 - Tree Structure | Anas Ahmed | None |  |  | 2024-02-29 18:44 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Component for Tree nodes | Anas Ahmed | None |  |  | 2024-02-29 18:38 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 842755527 | 842755527 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Tree Structure - MBE Certification | Anas Ahmed | None | 2024-02-01 09:30 | 2024-04-17 19:00 | 2024-02-29 18:30 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 842755527 | 842755527 | -40 | On Time | 37 | 37 | 55 | days
7.4981e+17 | New field is required – Aadhar PAN link – option yes/no – access to all employees. | Kiran Shrivastav | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-02-29 14:21 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 19 | 19 | 2 | days
7.4981e+17 | 3 Shift settings required to Jaipur Location | Kiran Shrivastav | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-02-29 14:18 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 19 | 19 | 2 | days
7.4981e+17 | Vikram Singh self appraisal issue | Kiran Shrivastav | None | 2024-02-29 09:30 | 2024-03-01 19:00 | 2024-02-29 14:18 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 17 | Late | 19 | 19 | 2 | days
7.4981e+17 | Zoho Analytics Sync Issue | Siddharth Sharma | None |  |  | 2024-02-29 09:18 | To Do | No | 0% | AMC - VAlign | Agappe Tickets | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Configure Holiday List | Tanu Gupta | High | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 23:42 | Done | No | 100% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Requirement Gathering/S | Shiwani Kumari | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 18:22 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Employee details Mapping in Zoho One | Kiran Shrivastav | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 11:08 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Airowire/S | Shiwani Kumari | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 09:37 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | SO Import Functionality & Discount in SO | Anusha V | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-27 21:50 | To Do | Yes | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Client Visit on 27-Feb-2024 | Vignesh R | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 10:38 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Gantt Chart and TSD | Tanu Gupta | High | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 19:30 | Done | No | 100% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Auto assign the user to approver profile | Tanu Gupta | High | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 19:23 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Email Template Configurations | Shavi Thakur,Tanu Gupta | High | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-26 19:04 | Done | No | 100% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 773081417,790157522 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Share capital entry-D | Devaraju S J | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 18:29 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Testing | Rishikesh Gogha | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-29 09:46 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Ledger Summary and Object Block Creation | Vaikuntam Chowdary | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-28 19:11 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Invoice Module, Bill Module Creation and Books Integration | Vaikuntam Chowdary | None | 2024-02-19 09:30 | 2024-02-21 19:00 | 2024-02-28 18:58 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 26 | Late | 29 | 29 | 3 | days
7.4981e+17 | Ledger Summary Zoho Books Integration and Ledger Block Modeling & Automations | Vaikuntam Chowdary | None | 2024-02-26 09:30 | 2024-02-27 19:00 | 2024-02-28 09:28 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 20 | Late | 22 | 22 | 2 | days
7.4981e+17 | Visits not getting locked after 7 days | Nikita Srivastava | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-27 18:20 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | Local claims not pushed to zoho books LE - 2024_02_0283LE - 2024_02_0286 | Maninder Singh | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-27 11:40 | Done | No | 100% | AMC - VAlign | EI - Zoho One Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | Import Customer to Zoho Creator and Update ID | Sachin Patil | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 20:18 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 19 | Late | 20 | 20 | 1 | days |  | Clear
7.4981e+17 | Explanation of Item master and Vendor master | Rishikesh Gogha | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-28 09:38 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Big Query Discussion and Discussion on configurinq oauth on google script | Anusuyadevi V | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-28 09:30 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Client Meeting For Zoho Desk``` | Monik Chettiyar | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-27 19:20 | Done | No | 100% | AMC - VAlign | Non AMC Project Tasks | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Weekly Scrum call | Kiran Shrivastav | None | 2024-02-27 09:30 | 2024-03-29 19:00 | 2024-02-27 18:55 | To Do | No | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | -11 | On Time | 21 | 21 | 24 | days
7.4981e+17 | Custom API creation | Anusuyadevi V | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-27 09:25 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Star Agile ¦ OBD Integration meeting | Maninder Singh | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 17:26 | Done | No | 100% | AMC - VAlign | StarAgile - Zoho CRM Plus Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Client Meetings & Demos | Waheeba Khan,Anusha V | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-29 09:38 | To Do | Yes | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 671373250,795545761 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Add estiamte's primary contact's phone number and quote number in deals (on create) | M S Satya | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-29 08:59 | To Do | Yes | 0% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 19 | Late | 20 | 20 | 1 | days |  | Clear
7.4981e+17 | Requirement Gathering-D | Devaraju S J | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 18:02 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | Airowir-D | Devaraju S J | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-28 09:36 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Meeting to integrate Kolkata Franchise form with Zoho CRM | Sachin Patil | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 19:24 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 15 | Late | 16 | 16 | 1 | days
7.4981e+17 | Doc field-level mapping | Prableen Kaur | None | 2024-02-26 09:30 | 2024-02-28 19:00 | 2024-02-26 17:52 | In Progress | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 19 | Late | 22 | 22 | 3 | days
7.4981e+17 | Exit Checklist Delivery Checklist Process | Monik Chettiyar | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-29 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | At every stage "Rework" option should be enabled. | Swetha K | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 19:31 | Hold | Yes | 0% | IIFL SAMASTA - IMS Enhancement 3.5 | Milestone Two-Zoho Creator: Customization, Configuration, Testing and Go-Live of IMS enhancement | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 19 | Late | 20 | 20 | 1 | days
7.4981e+17 | change the status back to "SBU approved" for the claim number LE-2024_02_0286. | Maninder Singh | None | 2024-02-28 09:30 | 2024-02-28 19:00 | 2024-02-28 11:15 | Done | No | 100% | AMC - VAlign | EI - Zoho One Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Client call regarding user permissions and Domain Authentication | Tanu Gupta | High | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-28 09:31 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Approval Process | Rishikesh Gogha | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-27 15:58 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Enable search option and disable add record for all reports, sorting all reports - latest record at the top | Swetha K | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 17:29 | Done | No | 100% | IIFL SAMASTA - IMS Enhancement 3.5 | Milestone Two-Zoho Creator: Customization, Configuration, Testing and Go-Live of IMS enhancement | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | In activity tracker of the case of the report, "Name of the person", "Employee code", "Email ID", "Date and time of response", should be mentioned. | Swetha K | None | 2024-02-26 09:30 | 2024-02-26 19:00 | 2024-02-26 09:58 | Done | No | 100% | IIFL SAMASTA - IMS Enhancement 3.5 | Milestone Two-Zoho Creator: Customization, Configuration, Testing and Go-Live of IMS enhancement | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | Exit Checklist Changes Work As by Team and Testing | Monik Chettiyar | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-23 21:21 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 39 | Late | 40 | 40 | 1 | days
7.4981e+17 | Exit Checklist Custom Function For Stakeholder Update | Monik Chettiyar | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-23 21:08 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 40 | Late | 41 | 41 | 1 | days
7.4981e+17 | Create P&I Button in Quote Module | Shavi Thakur | None | 2024-02-22 09:30 | 2024-02-22 11:00 | 2024-02-22 21:00 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 0 | Late | 1 | 1 | 1.5 | hrs
7.4981e+17 | Client Meeting - Scrum Call, Zoho Book & POC Audit | Mohammed Yusha | None | 2024-02-23 09:30 | 2024-02-26 19:00 | 2024-02-23 20:41 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | -3 | On Time | 1 | 1 | 2 | days |  | Clear
7.4981e+17 | Imports of credit note-D | Devaraju S J | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 18:06 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | Add task list and task | Aishwarya T | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-26 09:56 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 13 | Late | 14 | 14 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Requirement Discovery Session 1 | Stuti S. Kulshrestha | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 10:48 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Four-Implementation of Zoho Books - Financial Accounting System | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 13 | Late | 14 | 14 | 1 | days |  | Clear | Stuti S. Kulshrestha
7.4981e+17 | Bank feeds not fetching | Rishikesh Gogha | None | 2024-02-22 09:30 | 2024-02-23 19:00 | 2024-02-23 09:37 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 24 | Late | 26 | 26 | 2 | days
7.4981e+17 | PostMan Testing for zoho desk | Monik Chettiyar | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-26 11:26 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Zoho People User account issue | Monik Chettiyar | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-26 11:17 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-22 09:30 | 2024-02-23 19:00 | 2024-02-26 09:48 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 10 | Late | 12 | 12 | 2 | days
7.4981e+17 | Work on COA of Ozone Inc | Shiwani Kumari | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 18:09 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | Auto check-out function implementation after UAT | Kiran Shrivastav | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 12:38 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | Ozone Requirement gathering/S | Shiwani Kumari | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 18:28 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Client call for rundown branch queries | Tanu Gupta | High | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-26 09:56 | In Progress | Yes | 10% | IIFL Samasta Zoho Creator Score Card Enhancement | Milestone One-Implementation of Score Card Enhancement | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 24 | Late | 25 | 25 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Demo and Testing along with customer | Vignesh R | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 18:47 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 24 | Late | 25 | 25 | 1 | days |  | Clear
7.4981e+17 | Issue in Material Consumption | Vignesh R | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 16:05 | In Progress | Yes | 10% | KSport_Zoho Creator | Milestone Two-Implementation of Zoho Creator – Custom App Development | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 24 | Late | 25 | 25 | 1 | days |  | Clear
7.4981e+17 | #5981 Invitation: Zoho Issues Discussion @ Thu Feb 22, 2024 4pm - 4:30pm (IST) | Tanu Gupta | High | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 23:30 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Requirement gathering session | Mohammed Yusha,Tanu Gupta,Kiran Shrivastav | None | 2024-02-27 09:30 | 2024-02-27 19:00 | 2024-02-26 11:01 | Discovery Phase | Yes | 0% | CTW Systems - People, Payroll, Expense, Desk, Projects | Milestone Three-Implementation of Zoho People | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 701373265,790157522,791842987 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | Internal Meeting 3 | Aishwarya T | None | 2024-02-12 09:30 | 2024-02-22 19:00 | 2024-02-23 18:31 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 25 | Late | 36 | 36 | 9 | days |  | Clear | Sai Krishna
7.4981e+17 | Requirement Gathering Session 4 | Sai Krishna,Aishwarya T | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-23 16:20 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 28 | Late | 29 | 29 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Open the inventory page in edit mode if its present in creator | Nikita Srivastava | None | 2024-02-23 09:30 | 2024-02-23 19:00 | 2024-02-23 11:04 | Development | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | Email replies | Kiran Shrivastav | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 15:31 | To Do | Yes | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Add Item Category to Zoho Creator from Books, When Creation of Item in Books | Sachin Patil | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 19:07 | To Do | Yes | 0% | KSport_Zoho Creator | Milestone Three-Implementation of Zoho Creator – Creation of BOM | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 25 | Late | 26 | 26 | 1 | days |  | Clear
7.4981e+17 | Data Migration | Anusha V | High | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-22 09:39 | To Do | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Machani Dedicated Resource. | Mohan Kumar | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-22 10:24 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | User Manual Training Video Page creation | Kalyanasundaram L | None | 2024-02-21 09:30 | 2024-02-22 19:00 | 2024-02-22 09:48 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 25 | Late | 27 | 27 | 2 | days |  | Clear | Selva Bharathi
7.4981e+17 | Data migrations | Dharanidharan C,Mary Nisha | None | 2024-02-20 09:30 | 2024-02-22 19:00 | 2024-02-21 13:01 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 701371504,775643568 | 25 | Late | 28 | 28 | 3 | days |  | Clear
7.4981e+17 | Import Invoice/S | unassigned | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 09:33 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | - | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Post Go Live : Support for Items and Transactions sync | Tanu Gupta | Medium | 2024-02-20 09:30 | 2024-02-23 19:00 | 2024-02-21 09:42 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | -1 | On Time | 3 | 3 | 4 | days
7.4981e+17 | HTML Template & Automations for P&L | Tanu Gupta | Medium | 2024-02-21 09:30 | 2024-02-22 19:00 | 2024-02-21 17:32 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 6 | Late | 8 | 8 | 2 | days
7.4981e+17 | Go Live (Full Launch) MBE's W.1 | Kris Oswold | None | 2024-03-08 09:30 | 2024-03-08 19:00 | 2024-02-20 22:41 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 824545238 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Aggregation in Excel-D | Devaraju S J | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 18:09 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Bo to HR to Finance Report Isssue | Achyuth T M | None | 2024-02-21 09:30 | 2024-02-23 19:00 | 2024-02-22 09:42 | In Progress | Yes | 10% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 24 | Late | 27 | 27 | 3 | days |  | Clear
7.4981e+17 | Import sales order-D | Devaraju S J | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-22 09:29 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | 2 Wheeler & 4 Wheeler Demo Meeting With Client & Internal Testing | Mohammed Yusha | None | 2024-02-20 09:30 | 2024-02-21 19:00 | 2024-02-20 19:09 | Done | No | 100% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | -1 | On Time | 1 | 1 | 2 | days |  | Clear
7.4981e+17 | Email Notification to Finance if Expense added in the CRM | Ayush Singh | None | 2024-02-21 09:30 | 2024-02-21 19:00 | 2024-02-21 19:39 | In Progress | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 26 | Late | 27 | 27 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Territory issue | Nikita Srivastava | None |  |  | 2024-02-21 15:36 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 |  | On Time |  | 0 | 0 | days
7.4981e+17 | New WordPress Form (Door Pop-Up and Furniture Pop-Up) Enquiries Ccnvert to to Deal | Sachin Patil | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 19:28 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Function to trigger email for task allocation for template project creation | M S Satya | None |  |  | 2024-02-21 17:53 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Issue in Production activity log | Vignesh R | None | 2024-02-19 09:30 | 2024-02-21 19:00 | 2024-02-20 18:50 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 26 | Late | 29 | 29 | 3 | days
7.4981e+17 | Import of Customer & Vendor master/S | Shiwani Kumari | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 18:33 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | New Report Requirement Call | Monik Chettiyar | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-02-22 10:24 | To Do | Yes | 0% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 25 | Late | 26 | 26 | 1 | days
7.4981e+17 | Inventory Selection Sync with Zoho Com Deal Module | Supril Jain,Nikita Srivastava | None | 2024-01-05 09:30 | 2024-01-10 19:00 | 2024-02-21 10:58 | Done | No | 100% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914,774653652 | 61 | Late | 67 | 67 | 4 | days
7.4981e+17 | Page creation For External User | Mallesh M S | None | 2024-02-14 09:30 | 2024-03-13 19:00 | 2024-02-21 10:33 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 5 | Late | 34 | 34 | 21 | days |  | Clear
7.4981e+17 | Support request on Re: Appraisee View | Kiran Shrivastav | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 13:57 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | UI Developed for Budget Version | Rahul S S | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 17:55 | Done | No | 100% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 830176551 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Task List creations | Aishwarya T | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 19:00 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 17 | Late | 18 | 18 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Field level automation for debit note | Aishwarya T | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-19 12:01 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 27 | Late | 28 | 28 | 1 | days |  | Clear
7.4981e+17 | Approval process setup for purchase requisition | Sai Krishna,Aishwarya T | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-19 11:57 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 31 | Late | 32 | 32 | 1 | days |  | Clear
7.4981e+17 | Approval process for vendor registration | Aishwarya T | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-19 11:49 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 33 | Late | 34 | 34 | 1 | days |  | Clear
7.4981e+17 | Button automation for activation/deactivation of vendor on vendor registration | Sai Krishna,Aishwarya T | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-19 11:01 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 753339779,772989157 | 34 | Late | 35 | 35 | 1 | days |  | Clear
7.4981e+17 | Approval Master Form | Aishwarya T | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-19 10:39 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 34 | Late | 35 | 35 | 1 | days |  | Clear
7.4981e+17 | File Upload in Exit Checklist Form | Monik Chettiyar | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 16:58 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Document's data refinement | Prableen Kaur | None | 2024-02-20 09:30 | 2024-02-21 19:00 | 2024-02-20 12:42 | To Do | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 26 | Late | 28 | 28 | 2 | days
7.4981e+17 | Data Migration to Item Master and Inventory for Samsung Electronic City, Remove the old Data and add portal users | Sachin Patil | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 18:40 | To Do | Yes | 0% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 31 | Late | 32 | 32 | 1 | days |  | Clear
7.4981e+17 | Add the client script in demo and polite module | Nikita Srivastava | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 17:29 | In Progress | Yes | 0% | AMC - VAlign | Better Place Support Activity | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | Dashboard Walkthrough and Changes | Achyuth T M | None | 2024-02-16 09:30 | 2024-02-20 19:00 | 2024-02-19 18:11 | In Progress | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 27 | Late | 32 | 32 | 3 | days
7.4981e+17 | Re: Paternity leave added wrongly | Kiran Shrivastav | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 13:24 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Attendance module error | Kiran Shrivastav | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-02-20 10:43 | Development | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 48 | Late | 49 | 49 | 1 | days
7.4981e+17 | New WordPress Form (Door Pop-Up and Furniture Pop-Up) Deals Assign to Owners | Sachin Patil | None | 2024-02-19 09:30 | 2024-02-20 19:00 | 2024-02-19 19:08 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 21 | Late | 23 | 23 | 2 | days
7.4981e+17 | Meeting with Rishi/S | Shiwani Kumari | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 18:42 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Rejection Entry only for supplier rejection allow decimal (only for Scrap) | Sachin Patil | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 10:36 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 22 | Late | 23 | 23 | 1 | days
7.4981e+17 | Change date in the activity - Based on that re-allocate the efforts | Vignesh R | None | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-16 20:03 | In Progress | Yes | 10% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 27 | Late | 28 | 28 | 1 | days |  | Clear
7.4981e+17 | Stepper, siderbar and footer development. | unassigned | None |  |  | 2024-02-16 19:43 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176551 | - |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Ozone Inc Invoice template/S | Shiwani Kumari | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 18:21 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | Zoho CRM New Changes 03 | Rajesh Shindagi | None | 2024-02-16 09:30 | 2024-02-29 19:00 | 2024-02-18 14:11 | In Progress | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 18 | Late | 32 | 32 | 10 | days
7.4981e+17 | Go Live Activities | Vignesh R,Tanu Gupta | High | 2024-03-15 09:30 | 2024-03-15 19:00 | 2024-02-16 19:07 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 704175602,790157522 | 3 | Late | 4 | 4 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Journal Entry Integration with zoho books | Vignesh R,Tanu Gupta | High | 2024-02-28 09:30 | 2024-02-29 19:00 | 2024-02-16 18:56 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 704175602,790157522 | 18 | Late | 20 | 20 | 2 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Log Timesheet against activities | Vignesh R,Tanu Gupta | High | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-16 18:48 | To Do | Yes | 0% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 704175602,790157522 | 28 | Late | 29 | 29 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Demo -D | Devaraju S J | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-16 18:21 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 31 | Late | 32 | 32 | 1 | days
7.4981e+17 | Data Migration and Call with Support | Mohammed Yusha,Tanu Gupta | High | 2024-02-20 09:30 | 2024-02-20 19:00 | 2024-02-20 10:21 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Issue in mail functionality triggers | unassigned | High | 2024-02-14 09:30 | 2024-03-01 19:00 | 2024-02-19 19:14 | In Progress | Yes | 0% | Prodevans - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 795545761 | - | 17 | Late | 34 | 34 | 13 | days
7.4981e+17 | Re: Not able to submit the report | Rishikesh Gogha | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 18:24 | To Do | Yes | 0% | AMC - VAlign | AMC Airowire Networks_Zoho CRM, Books, Projects, Expense & Analytics _29-12-2023 to 28-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Audit-logs-D | Devaraju S J | None | 2024-02-19 09:30 | 2024-02-19 19:00 | 2024-02-19 18:34 | In Progress | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 28 | Late | 29 | 29 | 1 | days
7.4981e+17 | Credit Operations - Creator report and google sheet integration issue fixing | Anusuyadevi V | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-02-19 11:12 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Analytics Changes | Achyuth T M | High | 2024-02-15 09:30 | 2024-02-29 19:00 | 2024-02-16 10:20 | In Progress | Yes | 0% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 18 | Late | 33 | 33 | 11 | days
7.4981e+17 | Create PDF for Order Credit Note to Download Credit Note | Sachin Patil | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 19:18 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 26 | Late | 27 | 27 | 1 | days
7.4981e+17 | Currency Adjustment/S | Shiwani Kumari | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 18:14 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Updated Organic Project Template Creation | M S Satya | None |  |  | 2024-02-15 15:31 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Client Visit 15-Feb-2024 | Vignesh R | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 18:50 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Zoho EMail Trigger Setup and testing | Monik Chettiyar | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-15 15:04 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | Puchase Flow Testing | Shavi Thakur | None | 2024-02-15 14:30 | 2024-02-15 19:00 | 2024-02-16 08:00 | To Do | Yes | 0% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 32 | Late | 33 | 33 | 4.5 | hrs |  | Clear | Mohammed Yusha
7.4981e+17 | MBE portal data mapping according to template | Devaraju S J | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 14:48 | In Progress | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 788577227 | 844783967 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Debit Note Form | Aishwarya T | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 19:00 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 15 | Late | 16 | 16 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Purchase Requisition form, Department, Designation | Aishwarya T | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 18:56 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 15 | Late | 16 | 16 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Bank Reconciliation/S | Shiwani Kumari | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:26 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Portal Login - Checkmate automation | Dharanidharan C,Mallesh M S | None | 2024-01-22 09:30 | 2024-02-19 19:00 | 2024-02-13 16:19 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504,778475418 | 28 | Late | 57 | 57 | 21 | days |  | Clear
7.4981e+17 | Member Portal User dashboard - Profile Page | Dharanidharan C | None | 2024-01-22 09:30 | 2024-02-16 19:00 | 2024-02-13 16:16 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 31 | Late | 57 | 57 | 20 | days |  | Clear
7.4981e+17 | Development Organic version 2 | M S Satya | None |  |  | 2024-02-13 15:36 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Map fields from RMSDC to Application module | Prableen Kaur | None | 2024-02-12 09:30 | 2024-02-13 19:00 | 2024-02-13 18:30 | In Progress | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 34 | Late | 36 | 36 | 2 | days
7.4981e+17 | Member Portal users Data Migration | Kalyanasundaram L | None | 2024-02-12 09:30 | 2024-02-13 19:00 | 2024-02-13 10:13 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 819676542 | 819676542 | 34 | Late | 36 | 36 | 2 | days |  | Clear
7.4981e+17 | Testing Masters and Integrations and Test case preparation | Anusuyadevi V | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 20:42 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Currency adjustment-D | Devaraju S J | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 18:15 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Meeting with Vignesh for allocation data sources | Vignesh R,Tanu Gupta | High | 2024-02-14 09:30 | 2024-02-15 19:00 | 2024-02-14 20:47 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 704175602,790157522 | 8 | Late | 10 | 10 | 2 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Digital Voucher Flow & Client Meeting | Mohammed Yusha | None | 2024-02-14 09:30 | 2024-02-15 19:00 | 2024-02-14 19:40 | Done | No | 100% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 1 | Late | 3 | 3 | 2 | days |  | Clear
7.4981e+17 | Effort Estimations for Defspace | Tanu Gupta | High | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:34 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Realized gain or Loss/S | Shiwani Kumari | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 18:11 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Physical stock need to add in Primary UOM report | Vignesh R | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 19:18 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Verification report - remove/disable the credit card payment option | Swetha K | None | 2024-02-15 09:30 | 2024-02-16 19:00 | 2024-02-15 19:05 | Done | No | 100% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 20 | Late | 22 | 22 | 2 | days |  | Clear | Waheeba Khan
7.4981e+17 | Documentation and Solutioning | unassigned | None |  |  | 2024-02-14 10:47 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Three-Payment for February 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Third party payment gateway integration - Customers-D | Devaraju S J | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:24 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Unique ID functionality(14/02/24) | Anusha V | High | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-15 15:04 | In Progress | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Subform population in Tour request and tour claim - Requirement analysis | Swetha K | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 19:05 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 29 | Late | 30 | 30 | 1 | days
7.4981e+17 | Automated Accounting Transactions in Zoho Books and Inventory-D | Devaraju S J | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 17:53 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Solutioning demo and Requirements discovery | Mohammed Yusha,Vignesh R,Tanu Gupta | High | 2024-02-13 09:30 | 2024-02-14 19:00 | 2024-02-13 17:33 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,704175602,790157522 | 6 | Late | 8 | 8 | 2 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Zoho Books - Internal discussion | Mohammed Yusha,Tanu Gupta | None | 2024-02-15 09:30 | 2024-02-15 19:00 | 2024-02-15 19:02 | Development | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 32 | Late | 33 | 33 | 1 | days
7.4981e+17 | Create Report on individual & company searches | Albert Diaz | None | 2024-02-26 19:00 | 2024-02-26 19:00 | 2024-02-13 23:42 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 828527327 | 809116687 | -6 | On Time | -5 | -5 | 0 | days
7.4981e+17 | Project Budget - Process Testing & TSD review | Mohammed Yusha,Tanu Gupta | None | 2024-02-12 09:30 | 2024-02-13 19:00 | 2024-02-12 19:27 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,790157522 | 1 | Late | 3 | 3 | 2 | days |  | Clear
7.4981e+17 | Quote Management-D | Devaraju S J | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:24 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Error Invoice School Code-5184 | Swetha K | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:40 | In Progress | Yes | 0% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 35 | Late | 36 | 36 | 1 | days
7.4981e+17 | Configuration of Credit Notes Module and Fields | Rajesh Shindagi | None | 2024-02-12 09:30 | 2024-02-14 19:00 | 2024-02-12 16:26 | In Progress | Yes | 0% | Dr Reddy’s - Zoho CRM, Desk, SalesIQ | Milestone One-Advance payment for Zoho project initiation [Zoho Desk & Zoho SalesIQ, Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 33 | Late | 36 | 36 | 3 | days
7.4981e+17 | Configuration of Customer Module and Fields | Rajesh Shindagi | None | 2024-02-12 09:30 | 2024-02-14 19:00 | 2024-02-12 16:26 | Done | No | 100% | Dr Reddy’s - Zoho CRM, Desk, SalesIQ | Milestone One-Advance payment for Zoho project initiation [Zoho Desk & Zoho SalesIQ, Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 14 | Late | 17 | 17 | 3 | days
7.4981e+17 | Quotes - A | Akshay Parameshwara Hegde | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:30 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784261 | 844784261 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Quote Management/S | Shiwani Kumari | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:18 | To Do | Yes | 0% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 35 | Late | 36 | 36 | 1 | days
7.4981e+17 | External Call With Shankar for Service Invoice and Defected PO | Sachin Patil | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 18:11 | To Do | Yes | 0% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 34 | Late | 35 | 35 | 1 | days |  | Clear
7.4981e+17 | Call with Haqdarshak on PMS | Kiran Shrivastav | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 14:21 | Done | No | 100% | AMC - VAlign | Haqdarshaq AMC and Support | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Push Bill BA and Department to zoho books for all current financial year | Vignesh R | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 21:09 | To Do | Yes | 0% | Trimble Group_Zoho Books & Zoho Creator | Zoho Purchase and Inventory | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 35 | Late | 36 | 36 | 1 | days |  | Clear
7.4981e+17 | New change requirement of ZOho Recruit | Kiran Shrivastav | None | 2024-02-14 09:30 | 2024-02-16 19:00 | 2024-02-14 15:23 | To Do | Yes | 0% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 31 | Late | 34 | 34 | 3 | days
7.4981e+17 | Books Sync(Item Master Creator to Books) | Shavi Thakur | None | 2024-02-13 09:30 | 2024-02-13 13:00 | 2024-02-13 10:24 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 1 | Late | 2 | 2 | 3.5 | hrs
7.4981e+17 | ZOHO CRM ¦ Quotes Templates New updates | Monik Chettiyar | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 18:48 | QA level 1 Completed | Yes | 10% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 35 | Late | 36 | 36 | 1 | days |  | Clear
7.4981e+17 | Check Production Activity Log - update consumed QTY as primary UOM QTY in Zoho Books | Vignesh R | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 21:31 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Validation on Bills - On Adjusted Qty, TDS and TCS | Sachin Patil | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 19:16 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Hide, Show, Enabled and Disabled Quality Check Fields | Sachin Patil | None | 2024-02-14 09:30 | 2024-02-14 19:00 | 2024-02-14 18:59 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 27 | Late | 28 | 28 | 1 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-01 09:30 | 2024-02-15 19:00 | 2024-02-14 10:56 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 19 | 19 | 11 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-01 09:30 | 2024-02-15 19:00 | 2024-02-14 10:56 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 19 | 19 | 11 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-01 09:30 | 2024-02-15 19:00 | 2024-02-14 10:56 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 19 | 19 | 11 | days
7.4981e+17 | Machani Dedicated Resource | Mohan Kumar | None | 2024-02-01 09:30 | 2024-02-15 19:00 | 2024-02-14 10:56 | Done | No | 100% | Machani Dedicated Resource | Milestone Twelve-February 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 4 | Late | 19 | 19 | 11 | days
7.4981e+17 | Data Accounts status updation (Inactive) | Mary Nisha | None | 2024-02-13 09:30 | 2024-02-14 19:00 | 2024-02-13 15:24 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 33 | Late | 35 | 35 | 2 | days |  | Clear
7.4981e+17 | Vendor Registration form | Aishwarya T | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-13 10:30 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 16 | Late | 17 | 17 | 1 | days |  | Clear | Sai Krishna
7.4981e+17 | Filter for Open & closed Po based on SBU | Swetha K | None | 2024-02-13 09:30 | 2024-02-14 19:00 | 2024-02-12 12:15 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 6 | Late | 8 | 8 | 2 | days
7.4981e+17 | Item and inventory management-D | Devaraju S J | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 18:40 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Module Creation and Data migration - Invoices and Payments | Ayush Singh | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 21:35 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 4 | Late | 5 | 5 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Project - A | Akshay Parameshwara Hegde | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 18:49 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784261 | 844784261 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Legal Workflow Changes - 09-02-2024 | Ranjana Poojari | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 17:32 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Load Chain and Hand Chain corrections - 09-02-2024 | Ranjana Poojari | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 11:07 | Done | No | 100% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 6 | Late | 7 | 7 | 1 | days |  | Clear
7.4981e+17 | Scrum call with thoucentric team | Kiran Shrivastav,Monik Chettiyar | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-09 11:56 | In Progress | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987,792262192 | 39 | Late | 40 | 40 | 1 | days
7.4981e+17 | Discussion on Changes | Vignesh R | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 00:07 | In Progress | Yes | 10% | Ecovinal Project 3 - Farmer Management | Milestone Two-Zoho Creator – Farmer Operations: Configuration and customisation, Software demo | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 38 | Late | 39 | 39 | 1 | days |  | Clear
7.4981e+17 | Zoho Recruit Offer Letter Corrections and Changes | Monik Chettiyar | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-12 01:15 | Done | No | 100% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Create Stock based location report | Maninder Singh | None | 2024-02-16 09:30 | 2024-02-19 19:00 | 2024-02-09 11:35 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 21 | Late | 25 | 25 | 2 | days |  | Clear
7.4981e+17 | Feasibility Check User creation in zoho one through API | Ranjana Poojari | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 18:21 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | TSD of CEEW Flow | Aishwarya T | None | 2024-02-08 09:30 | 2024-02-09 19:00 | 2024-02-08 12:41 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 27 | Late | 29 | 29 | 2 | days |  | Clear | Sai Krishna
7.4981e+17 | Welcome Email Template | Nikita Srivastava | None | 2024-02-12 09:30 | 2024-02-15 19:00 | 2024-02-12 10:16 | In Progress | Yes | 0% | Accorian - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 774653652 | 32 | Late | 36 | 36 | 4 | days
7.4981e+17 | Update UOM from Zoho Creator for those items for which there is no UOM in Zoho Books | Sachin Patil | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 19:17 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 33 | Late | 34 | 34 | 1 | days
7.4981e+17 | Exit checklist call with Thoucentric team | Kiran Shrivastav,Monik Chettiyar | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 15:16 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987,792262192 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | Budget Version Comparison | Ranjana Poojari | None | 2024-02-12 09:30 | 2024-02-12 19:00 | 2024-02-12 10:43 | Done | No | 100% | AMC - VAlign | Machani_AMC_Books_27-11-2023 to 26-11-2024 | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Opportunity and CCO,PMD Non Day Templates Devlopments | Mary Nisha | High | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 12:52 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 38 | Late | 39 | 39 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Test and fix issues for Project Discovery and Budget | Tanu Gupta | High | 2024-02-09 09:30 | 2024-02-12 19:00 | 2024-02-09 19:43 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 24 | Late | 28 | 28 | 2 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Agent Performance Report | Tanu Gupta | High | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 19:27 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Four-Implementation of Zoho CRM Application | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 38 | Late | 39 | 39 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Reports Views and Custom fields addition | Aishwarya T,Ayush Singh | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-08 12:00 | In Progress | Yes | 0% | AMC - VAlign | VSI-Estore | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772989157,772908679 | 41 | Late | 42 | 42 | 1 | days
7.4981e+17 | Requirement gathering call | Rishikesh Gogha | None | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-12 09:58 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 38 | Late | 39 | 39 | 1 | days
7.4981e+17 | Data Import & Testing | Anusha V | High | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-09 19:39 | In Progress | Yes | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 41 | Late | 42 | 42 | 1 | days
7.4981e+17 | Import Functionality for WH#PO | Aishwarya T,Anusha V | High | 2024-02-09 09:30 | 2024-02-09 19:00 | 2024-02-09 10:38 | In Progress | Yes | 0% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 772989157,795545761 | 38 | Late | 39 | 39 | 1 | days
7.4981e+17 | #5918 VMS Issues | Mohammed Yusha,Tanu Gupta | High | 2024-02-08 09:30 | 2024-02-15 19:00 | 2024-02-08 23:33 | In Progress | Yes | 0% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 32 | Late | 40 | 40 | 6 | days
7.4981e+17 | Subform field size reduction | Swetha K | None | 2024-02-08 09:30 | 2024-02-08 19:00 | 2024-02-08 13:46 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Byron Support Request - feb | M S Satya | None | 2024-02-01 09:30 | 2024-02-29 19:00 | 2024-02-08 10:57 | Done | No | 100% | AMC - VAlign | Byron Medical Pty Ltd ¦ Zoho One ¦ 01-10-2023 ¦ 30-09-2024 | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 4 | Late | 33 | 33 | 21 | days
7.4981e+17 | UAT Correction & Internal Meeting | unassigned | None | 2024-02-07 09:30 | 2024-02-09 19:00 | 2024-02-07 19:31 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Five-Advance Reports & Analytics | 7.4981e+17 | 7.4981e+17 |  | 701373265 | - | 10 | Late | 13 | 13 | 3 | days |  | Clear
7.4981e+17 | Establish Roles (Finance Team) | Leahanne Thomas | None | 2024-02-06 09:30 | 2024-02-09 19:00 | 2024-02-07 04:04 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 811824969 | 30 | Late | 34 | 34 | 4 | days
7.4981e+17 | Client Meeting | Vaikuntam Chowdary | None | 2024-02-06 09:30 | 2024-02-09 19:00 | 2024-02-07 11:37 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Five-Payment for April 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 38 | Late | 42 | 42 | 4 | days
7.4981e+17 | A - Basic Navigation | Akshay Parameshwara Hegde | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:33 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784261 | 844784261 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Rename of Quotation subform field and calls | Swetha K | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:41 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 41 | Late | 42 | 42 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Vendor Master API Creation for Create/Update using PostMan | Vaikuntam Chowdary | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-07 11:30 | In Progress | Yes | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 778472746 | 41 | Late | 42 | 42 | 1 | days
7.4981e+17 | Item Master API Documentation - Creator | Anusuyadevi V | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-07 10:40 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Export and Import DS File | Tanu Gupta | High | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 21:01 | Done | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Two-Implementation of Zoho Creator - Donor, Funder, Grants, Project Management | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 18 | Late | 19 | 19 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Contacts and Customers/S | Shiwani Kumari | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 18:36 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Summary Form Business Description | Nawaz Sharief | None |  |  | 2024-02-05 18:26 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 841115370 | 841115370 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Call on Zoho HRMS_Timeline Discussion | Kiran Shrivastav | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 21:57 | Done | No | 100% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Service call scheduler | Nikita Srivastava | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 17:22 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 31 | Late | 32 | 32 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Customer class issue for all the module | Nikita Srivastava | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:12 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Issue in Duplicate books id in zoho creator | Vignesh R | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 18:40 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 42 | Late | 43 | 43 | 1 | days
7.4981e+17 | Create Associate , Member and Pracharak field details sheet | Maninder Singh | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 16:58 | In Progress | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 40 | Late | 41 | 41 | 1 | days |  | Clear
7.4981e+17 | Introduction to ZOHO Books | Devaraju S J | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:11 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Vendors-D | Devaraju S J | None | 2024-02-07 19:00 | 2024-02-07 19:00 | 2024-02-07 18:40 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844783967 | 844783967 | 5 | Late | 6 | 6 | 0 | days
7.4981e+17 | HTML Pages - User Profile page | Ayush Singh | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-07 09:43 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 7 | Late | 8 | 8 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Client Visit 06-Feb-2023 | Vignesh R | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 22:19 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 41 | Late | 42 | 42 | 1 | days
7.4981e+17 | Create New Meeting | unassigned | None |  |  | 2024-02-06 19:54 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 701371504 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Acknowledgement Email sent to lead email id after successful Lead Creation | unassigned | None |  |  | 2024-02-06 19:54 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 701371504 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Summary Form UI | Avinash Sah | None |  |  | 2024-02-05 18:37 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Vendors - A | Akshay Parameshwara Hegde | None | 2024-02-07 09:30 | 2024-02-07 19:00 | 2024-02-07 18:38 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784261 | 844784261 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Feedback Points - 06-02-2024 | Ranjana Poojari | None |  |  | 2024-02-07 15:25 | Done | No | 100% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | For Service Indent in Purchase Indent, vendor should be selected after selecting DC | Sachin Patil | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:57 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 35 | Late | 36 | 36 | 1 | days
7.4981e+17 | Introduction to Zoho Books | Shiwani Kumari | None | 2024-02-06 09:30 | 2024-02-06 19:00 | 2024-02-06 18:10 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 844784545 | 844784545 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Discovery Search | Selva Bharathi | None | 2024-02-01 19:00 | 2024-02-01 19:00 | 2024-02-05 18:30 | Development Complete | Yes | 80% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573 | 46 | Late | 47 | 47 | 0 | days |  | Clear
7.4981e+17 | Integration with creator | Selva Bharathi | None | 2024-02-13 09:30 | 2024-02-13 19:00 | 2024-02-05 18:19 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573 | 34 | Late | 35 | 35 | 1 | days |  | Clear
7.4981e+17 | Migration of Wave 1 council data to Zoho | Prableen Kaur | None | 2024-02-10 09:30 | 2024-02-14 19:00 | 2024-02-05 18:16 | To Do | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 33 | Late | 38 | 38 | 4 | days
7.4981e+17 | Task Blueprint Creation | M S Satya | None |  |  | 2024-02-07 10:27 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Project Template Creation | M S Satya | None |  |  | 2024-02-07 10:18 | In Progress | No | 0% | Ocimum Botanicals - Zoho Projects Implementation | Milestone Two-Completion of Zoho Projects Implementation | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Exit Checklist Demo | Monik Chettiyar | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-06 01:56 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Request For Call Back In ZOho CRM not Working | Monik Chettiyar | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-06 01:45 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Exit Checklist corrections | Monik Chettiyar | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-06 01:27 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | When Create Invoice, Fetch Customer GST No and Update | Sachin Patil | None | 2024-02-05 09:30 | 2024-02-07 19:00 | 2024-02-05 19:13 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 34 | Late | 37 | 37 | 3 | days
7.4981e+17 | Report column realignment for RM and SBU approval report for both of the claim | Swetha K | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 18:58 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | Testing | Anusha V | High | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-06 09:33 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | Big Query API study | Anusuyadevi V | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-06 09:07 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Meeting with Client | Anusuyadevi V | None | 2024-02-05 09:30 | 2024-02-05 19:00 | 2024-02-05 20:34 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Zoho CRM integration issues | unassigned | None |  |  | 2024-02-02 17:51 | To Do | No | 0% | LONGITUDE - AMC - Zoho People, Zoho Payroll & Zoho CRM | None | 7.4981e+17 | 7.4981e+17 |  | 839251991 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Upcoming Appointments View for Portal User | Dharanidharan C | None | 2024-02-06 09:30 | 2024-02-20 19:00 | 2024-02-02 17:17 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504 | 2 | Late | 17 | 17 | 11 | days
7.4981e+17 | On lead to deal conversion expected revenue field is not populating correctly | Aishwarya T | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 15:41 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 45 | Late | 46 | 46 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | Data Import | Ranjana Poojari | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 18:34 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-25 09:30 | 2024-02-02 19:00 | 2024-02-02 10:48 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 17 | Late | 26 | 26 | 7 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-25 09:30 | 2024-02-02 19:00 | 2024-02-02 10:48 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 17 | Late | 26 | 26 | 7 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-02-02 10:36 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-02-02 10:36 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Creating Column header for the Catalyst Data Upload | Kalyanasundaram L | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-04 20:10 | Development Complete | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 46 | Late | 47 | 47 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Video Manuals | Rishikesh Gogha | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-05 09:43 | To Do | Yes | 0% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 45 | Late | 46 | 46 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | GRN and VB from PO - row 82 | Swetha K | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 19:07 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 45 | Late | 46 | 46 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | All payment related pages - mark as paid | Swetha K | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 16:30 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 45 | Late | 46 | 46 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Go-Live Migration Check & UAT | Mohammed Yusha | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 19:05 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | #5900 Working Call with Janani | Tanu Gupta | High | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-04 22:08 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Website UI Changes | Tanu Gupta | High | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 19:28 | Development Complete | Yes | 10% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 790157522 | 790157522 | 46 | Late | 47 | 47 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Requirement discovery sessions | Dharanidharan C,Rajesh Shindagi | None | 2024-02-02 09:30 | 2024-02-09 19:00 | 2024-02-05 07:26 | Done | No | 100% | Dr Reddy’s - Zoho CRM, Desk, SalesIQ | None | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 701371504,758002363 | 3 | Late | 11 | 11 | 6 | days
7.4981e+17 | Support request on Work Anniversary Message not triggered | Kiran Shrivastav | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 16:44 | Done | No | 100% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 18 | Late | 19 | 19 | 1 | days
7.4981e+17 | RE: ZOHO people corrections | Kiran Shrivastav | None | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 10:54 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | NMSDC Permissions excel | Mary Nisha | High | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-01 19:02 | Done | No | 100% | AMC - VAlign | FARM INDIA IMPEX ¦ Books, Creator, People, Payroll & Analytics ¦ 8-12-23 to 7-12-24 | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | KT/Testing / Assistance to dev/ Internal Meetings/Client Calls | Selva Bharathi | None | 2023-09-25 09:30 | 2023-12-30 19:00 | 2024-02-01 23:34 | In Progress | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 701368573 | 701368573 | 79 | Late | 176 | 176 | 70 | days |  | Not Clear
7.4981e+17 | Training and Flow Test on Sales Order Management. | Basavaraj Patil | None | 2024-01-15 09:30 | 2024-01-17 19:00 | 2024-02-02 17:13 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 61 | Late | 64 | 64 | 3 | days |  | Not Clear | Waheeba Khan
7.4981e+17 | Demo on Pr, PO, GRN, Put Away and Bill. | Basavaraj Patil | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-02-02 16:48 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 56 | Late | 57 | 57 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Import Item Master -Client Visit | Basavaraj Patil | None | 2024-01-16 09:30 | 2024-02-02 19:00 | 2024-02-02 16:38 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 781564441 | 781564441 | 45 | Late | 63 | 63 | 14 | days |  | Clear | Waheeba Khan
7.4981e+17 | Data Push to Creator Functionality & Import Testing of Bills | Anusha V | High | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-02-02 20:26 | Done | No | 100% | SPERA - Zoho Creator | Milestone Two-Implementation of Zoho Creator - Warehouse Management Application | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 12 | Late | 13 | 13 | 1 | days
7.4981e+17 | Zoho Creator and Books API document Preparation | Anusuyadevi V | None | 2024-02-01 09:30 | 2024-02-01 19:00 | 2024-02-02 10:00 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Go Live Implementations | Anusuyadevi V,Tanu Gupta | High | 2024-01-31 09:30 | 2024-02-01 19:00 | 2024-01-31 21:59 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 786479121,790157522 | 14 | Late | 16 | 16 | 2 | days
7.4981e+17 | Data Migration Into CRM | unassigned | High | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-02-01 09:48 | In Progress | Yes | 0% | Prodevans - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 795545761 | - | 49 | Late | 50 | 50 | 1 | days
7.4981e+17 | Discussion and Study on BigQuery and Zoho Creator Integrations | Anusuyadevi V | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-02-01 10:06 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Client call for Live UAT | Tanu Gupta | High | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 21:47 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Change Email Templates Content All Follow-Up Email Templates | Sachin Patil | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 18:36 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | PO Creation - GST Rate option | Swetha K | None | 2024-01-31 09:30 | 2024-02-01 19:00 | 2024-01-31 18:24 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 46 | Late | 48 | 48 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Create Sales Invoice summary report in analytics and embed into zoho creator | Maninder Singh | Medium | 2024-02-01 09:30 | 2024-02-12 19:00 | 2024-02-01 09:22 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 28 | Late | 40 | 40 | 8 | days |  |  | Supril Jain
7.4981e+17 | refactor ui using redux | Avinash Sah | None |  |  | 2024-01-31 19:36 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Specility Functionalities | Mary Nisha | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 11:48 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 47 | Late | 48 | 48 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Payroll requirement Discussion | Kiran Shrivastav | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 15:49 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 20 | Late | 21 | 21 | 1 | days
7.4981e+17 | fetching data from leaves and update leave count of user | Monik Chettiyar | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 16:11 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 48 | Late | 49 | 49 | 1 | days
7.4981e+17 | Linking PO to SO in create sales order. | Maninder Singh | None | 2024-01-30 09:30 | 2024-02-12 19:00 | 2024-01-30 09:32 | Done | No | 100% | Farm India: Zoho Creator Change Request | Milestone One-Development / Configuration / Testing / go-live of Zoho Creator Change | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 28 | Late | 42 | 42 | 10 | days |  | Clear | Supril Jain
7.4981e+17 | Calculate Invoice Amount and Line Item Amount based on Rate for Samsung Warehouse | Sachin Patil | None | 2024-01-29 09:30 | 2024-01-30 19:00 | 2024-01-29 18:26 | Development Complete | Yes | 10% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 48 | Late | 50 | 50 | 2 | days |  | Clear | Waheeba Khan
7.4981e+17 | Email Trigger Setup | Monik Chettiyar | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 13:23 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 49 | Late | 50 | 50 | 1 | days
7.4981e+17 | RHI - API validation | Anusuyadevi V | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-31 09:44 | Done | No | 100% | Non Billable Activities | Inspire | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | #5882 Company Name - training | Tanu Gupta | High | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 20:19 | Done | No | 100% | AMC - VAlign | Synup Digital Pvt Ltd - Zoho CRM & Desk ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Voucher, Cycle , Two Wheeler & Four Wheeler Flow Check | Mohammed Yusha | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 19:06 | Done | No | 100% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 23 | Late | 24 | 24 | 1 | days |  | Clear
7.4981e+17 | Profiles Creation and Data Sharing Settings | unassigned | High | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-29 09:30 | Done | No | 100% | Prodevans - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 795545761 | - | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Terms and Condition page creation in - ZOHO Creator | Ayush Singh | None | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-31 09:48 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 13 | Late | 15 | 15 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Refactor UI Using Redux | Avinash Sah | None | 2024-01-29 09:30 | 2024-01-30 19:00 | 2024-01-29 19:02 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 | 6 | Late | 8 | 8 | 2 | days |  | Clear
7.4981e+17 | Catalyst ConvoKraft Seminar with zoho partner team | Prableen Kaur | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 18:33 | Done | No | 100% | RPA Master Plan | IIFL RPA Project | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | Disable the SBU email filed in SBU split up subform | Swetha K | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 18:57 | Done | No | 100% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Field Customizations in modules | unassigned | High | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-30 10:19 | Done | No | 100% | Prodevans - Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 795545761 | - | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | UAT Demo | Mohammed Yusha,Tanu Gupta | High | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 21:31 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Weekly Status | Waheeba Khan | None | 2024-01-18 09:30 | 2024-01-19 19:00 | 2024-01-29 19:38 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Two-Payment for January2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 46 | Late | 48 | 48 | 2 | days
7.4981e+17 | UAT Issue On Analytics Reports | Mohammed Yusha | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 18:54 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Five-Advance Reports & Analytics | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 2 | Late | 3 | 3 | 1 | days |  | Clear
7.4981e+17 | Layout Rule for warranty | Supril Jain | None | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-31 09:29 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914 | 36 | Late | 38 | 38 | 2 | days |  | Clear
7.4981e+17 | Deparment,TDS,Tax,COA Form Creation and import | Mary Nisha | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 12:01 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Client Visit on 29-Jan-2024 | Vignesh R | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 18:29 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 49 | Late | 50 | 50 | 1 | days
7.4981e+17 | when deal is created the record should be created SOW | Aishwarya T | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 10:26 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 47 | Late | 48 | 48 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | Oracle Report Discussion | Vignesh R,Achyuth T M | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 21:13 | In Progress | Yes | 10% | Trimble Group_Zoho Books & Zoho Creator | Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602,708853094 | 48 | Late | 49 | 49 | 1 | days |  | Clear
7.4981e+17 | Customer Bill - Issue Find Out | Mallesh M S | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 09:59 | In Progress | Yes | 0% | All Time Support - CR - Billing Operations | Milestone Two-Change request on Zoho Creator & Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 48 | Late | 49 | 49 | 1 | days |  | Clear
7.4981e+17 | Data Migration - Data formatting in the excel files | Ayush Singh | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 21:46 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 15 | Late | 16 | 16 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Support Call and People Demo | Monik Chettiyar | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-28 18:06 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Support Call | Monik Chettiyar | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-28 17:42 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 9 | Late | 10 | 10 | 1 | days
7.4981e+17 | ZOho Support Call | Monik Chettiyar | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-28 17:34 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Add Validation on Rate field for Manually Entered Rate in Invoice(Samsung Warehouse) | Sachin Patil | None | 2024-01-25 09:30 | 2024-01-29 19:00 | 2024-01-25 19:12 | Development Complete | Yes | 10% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 49 | Late | 54 | 54 | 3 | days |  | Clear | Waheeba Khan
7.4981e+17 | Appointment letter template | Kiran Shrivastav | None | 2024-01-31 09:30 | 2024-01-31 19:00 | 2024-01-31 09:34 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 47 | Late | 48 | 48 | 1 | days
7.4981e+17 | Project status Mail | Kiran Shrivastav | None | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-30 10:01 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 19 | Late | 21 | 21 | 2 | days
7.4981e+17 | Performance module call | Kiran Shrivastav | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 14:01 | Done | No | 100% | AMC - VAlign | Longitude Exports Pvt Ltd - Zoho CRM, Zoho People & Zoho Payroll ¦ 09-08-2023 ¦ 08-02-2024 | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 24 | Late | 25 | 25 | 1 | days
7.4981e+17 | QA Testing - MBE Search Rel 1/25 | Stuti S. Kulshrestha | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 13:02 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 53 | Late | 54 | 54 | 1 | days |  | Clear
7.4981e+17 | Purchase requisition,Vendor,PO Form Creation | Mary Nisha | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 12:59 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Shopkeeper Onboarding Points(30/01/24) | Anusha V | None | 2024-01-30 09:30 | 2024-02-05 19:00 | 2024-01-31 09:24 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 31 | Late | 38 | 38 | 5 | days
7.4981e+17 | Internal Team meeting and bulk mail feature enhancement for donation receipts | Sai Krishna,Tanu Gupta | High | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-30 20:32 | In Progress | Yes | 10% | Namma Sampradaya_Zoho One | Milestone Two- Zoho Creator : Donor Management System | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 790157522 | 753339779,790157522 | 48 | Late | 49 | 49 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Create Credit Note and Refund for unfulfilled item | Anusuyadevi V | None | 2024-01-27 09:30 | 2024-01-27 19:00 | 2024-01-27 20:04 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Study on Incoming payment requirements | Anusuyadevi V | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-26 21:27 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | #5860- VMS Software modification-22-01-2024 | Tanu Gupta | High | 2024-01-29 09:30 | 2024-01-30 19:00 | 2024-01-26 20:52 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | P&I - Issues | Swetha K | None | 2024-02-08 09:30 | 2024-02-15 19:00 | 2024-01-30 13:03 | Ready for QC | Yes | 0% | Educational Initiatives - P&I CR | Milestone Two-Zoho Creator - Improvisation of the Zoho Purchase and Inventory system | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 32 | Late | 40 | 40 | 6 | days
7.4981e+17 | Disable subform delete entry if RM rejected more than twice | Swetha K | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-29 09:31 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Quality parameters are not visible for soya bean seed and DORBin PO/SO | Maninder Singh | None | 2024-01-29 09:30 | 2024-01-29 19:00 | 2024-01-24 11:36 | In Progress | Yes | 0% | AMC - VAlign | FARM INDIA IMPEX ¦ Books, Creator, People, Payroll & Analytics ¦ 8-12-23 to 7-12-24 | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 49 | Late | 50 | 50 | 1 | days
7.4981e+17 | Ability to mark a PO / SO as closed and to archive it | Maninder Singh | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-24 11:31 | In Progress | Yes | 0% | AMC - VAlign | FARM INDIA IMPEX ¦ Books, Creator, People, Payroll & Analytics ¦ 8-12-23 to 7-12-24 | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 54 | Late | 55 | 55 | 1 | days
7.4981e+17 | PDF Level customization | Ayush Singh | None | 2024-01-23 09:30 | 2024-01-24 19:00 | 2024-01-23 20:37 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 54 | Late | 56 | 56 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | field level validation page 2 | Avinash Sah | None |  |  | 2024-01-23 19:01 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Create test product in shopify and sync with zoho inventory and follow up with zoho team for issue during sync | Mohammed Yusha,Tanu Gupta | High | 2024-01-24 09:30 | 2024-01-25 19:00 | 2024-01-24 20:31 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701373265,790157522 | 27 | Late | 29 | 29 | 2 | days
7.4981e+17 | CRM Integration Changes | Vaikuntam Chowdary | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 18:27 | In Progress | Yes | 10% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Three-Zoho Creator –Purchase & InventoryManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 55 | Late | 56 | 56 | 1 | days |  | Clear
7.4981e+17 | ABMPL-Zoho Creator Purchase Flow Bug Fixing and Testing | Vaikuntam Chowdary | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-23 09:27 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 56 | Late | 57 | 57 | 1 | days |  | Clear
7.4981e+17 | Prepare RPA Plan for NMSDC | Prableen Kaur | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-24 18:39 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Joining date and Content Changes error in new offer letter in zoho Recruit | Monik Chettiyar | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-24 10:48 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 8 | Late | 9 | 9 | 1 | days
7.4981e+17 | Create Bill After All GRN Items are Converted to Actual Quantity Check | Sachin Patil | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-24 19:17 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Client Call | Aishwarya T | None | 2024-01-23 09:30 | 2024-01-31 19:00 | 2024-01-24 17:54 | Terminated/Cancelled | No | 100% | CEEW - Zoho ONE - ERP Implementation | Milestone Three-Implementation of Zoho Creator - Vendor & Purchase Management | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 30 | Late | 39 | 39 | 7 | days |  | Clear | Sai Krishna
7.4981e+17 | Decimal needs to be checked in Quotes as it is taking more than 2 decimals | Aishwarya T | None | 2024-01-24 09:30 | 2024-01-25 19:00 | 2024-01-24 10:50 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Clarified Points | Ranjana Poojari | None | 2024-01-25 09:30 | 2024-01-25 19:00 | 2024-01-25 10:58 | Done | No | 100% | IIFL Samasta: Zoho Creator Employee House Visit (EHV) Change Request | Milestone One- Advance Payment Zoho Creator Employee House Visit (EHV) Change Request | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | ZIng Retry Method - 23-01-2024 | Ranjana Poojari | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 14:45 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 16 | Late | 17 | 17 | 1 | days
7.4981e+17 | Advance Status update customization | Anusuyadevi V | None | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-25 09:41 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | KRI Mail Trigger Manually for hods(22/01/24) | Anusha V | None | 2024-01-22 09:30 | 2024-01-31 19:00 | 2024-01-22 20:15 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 36 | Late | 46 | 46 | 8 | days
7.4981e+17 | Adding Inbuild Componets | Avinash Sah | None |  |  | 2024-01-24 19:19 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Build script to download documents from Microsoft teams using APIs | Prableen Kaur | None | 2024-01-29 09:30 | 2024-01-30 19:00 | 2024-01-24 11:15 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 1 | Late | 3 | 3 | 2 | days
7.4981e+17 | Data Analysis for certification module | Prableen Kaur | None | 2023-10-10 09:30 | 2024-01-12 19:00 | 2024-01-23 16:07 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 11 | Late | 106 | 106 | 69 | days
7.4981e+17 | Import new items, Inventories and push to books (And Support) | Sachin Patil | None | 2024-01-22 09:30 | 2024-01-23 19:00 | 2024-01-22 19:07 | Terminated/Cancelled | No | 100% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 7 | Late | 9 | 9 | 2 | days |  | Clear
7.4981e+17 | User Manual Videos for member management- Application Users and Portal Users | Dharanidharan C,M S Satya,Deepa Hireholi | None | 2024-01-22 09:30 | 2024-01-31 19:00 | 2024-01-22 17:32 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504,789497933,800651184 | 13 | Late | 23 | 23 | 8 | days |  | Clear
7.4981e+17 | Dashboard Creation for Member View | Dharanidharan C,Mallesh M S | None | 2024-01-22 09:30 | 2024-02-02 19:00 | 2024-01-22 17:32 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 701371504 | 701371504,778475418 | 11 | Late | 23 | 23 | 10 | days |  | Clear
7.4981e+17 | Status update meet | Kiran Shrivastav | None | 2024-01-22 09:30 | 2024-01-25 19:00 | 2024-01-22 21:40 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 25 | Late | 29 | 29 | 4 | days
7.4981e+17 | Application form Integration - Contacts | Mallesh M S | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-22 13:32 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 21 | Late | 22 | 22 | 1 | days |  | Not Clear
7.4981e+17 | Re: Project mapping error- Zoho people | Kiran Shrivastav | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 23:49 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 55 | Late | 56 | 56 | 1 | days
7.4981e+17 | Zoho CRM to Books Issues | Monik Chettiyar | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-22 23:00 | Development Complete | Yes | 0% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 66 | Late | 67 | 67 | 1 | days |  | Clear | Irshad Pasha
7.4981e+17 | Client Meeting ¦ Boldfit ¦ Data Templates for Journals and Payments | Waheeba Khan,Tanu Gupta | High | 2024-01-24 09:30 | 2024-01-24 19:00 | 2024-01-24 18:58 | In Progress | Yes | 10% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 671373250,790157522 | 54 | Late | 55 | 55 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Reversal of Invoice for school code - 904530 (Inv No. INV/3464) | Swetha K | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 16:13 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | #5811 Survey is sent (If the Do Not Send Survey box is Ticked) | Tanu Gupta | High | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-23 12:26 | Done | No | 100% | AMC - VAlign | Synup Digital Pvt Ltd - Zoho CRM & Desk ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Prepaid Expense Report | Achyuth T M | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-22 19:12 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Five-Advance Reports & Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | Profile permissions of modules | Aishwarya T | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 13:08 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 59 | Late | 60 | 60 | 1 | days
7.4981e+17 | Changes in Email Notification Templates | Sachin Patil | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 18:37 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Support request on Re: Deactivate Exit Interview Form on Zoho People | Kiran Shrivastav | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 14:46 | Done | No | 100% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Resolve python compatibility issue with UI Path | Prableen Kaur | None | 2024-01-22 09:30 | 2024-01-25 19:00 | 2024-01-18 18:33 | In Progress | Yes | 0% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 53 | Late | 57 | 57 | 4 | days
7.4981e+17 | SO creation from CRM Deal and Blueprint changes | Vaikuntam Chowdary | None | 2024-01-26 09:30 | 2024-01-26 19:00 | 2024-01-22 09:53 | In Progress | Yes | 10% | Kito Zoho Creator - OM, P&I &PPC, Zoho Books | Milestone Two-Zoho Creator – OrderManagementApplication | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 52 | Late | 53 | 53 | 1 | days |  | Clear
7.4981e+17 | Send out Invitation emails to Corp Members and RMSDC's on Go-Live (12PM EST) | Selva Bharathi,Albert Diaz | None | 2024-02-22 09:30 | 2024-02-22 19:00 | 2024-01-20 05:46 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 701368573,809116687 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Create Email Content for RMSDC | stefan bradham | None | 2024-01-19 09:30 | 2024-01-22 19:00 | 2024-01-20 05:27 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 836353936 | 1 | Late | 5 | 5 | 2 | days
7.4981e+17 | Auto Create Sale Return Receipt | Tanu Gupta | High | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-19 20:03 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Activation of Journal Reporting tag | Swetha K | None | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 15:28 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Testing of webform and Support Calls | Anusha V | High | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-19 15:05 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 66 | Late | 67 | 67 | 1 | days
7.4981e+17 | Update all Journals from Nov with reporting tags for TE | Swetha K | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-22 11:14 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Update Excel | Shavi Thakur | None | 2024-01-19 17:30 | 2024-01-19 19:00 | 2024-01-19 17:51 | Done | No | 100% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 0 | Late | 1 | 1 | 1.5 | hrs
7.4981e+17 | Zoho CRM - Zoho Support Team Call regarding Blueprint issue for IT Asset Move | Tanu Gupta | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 20:18 | Done | No | 100% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Update Primary contacts related to the estimate in deal record in Zoho CRM | Rajesh Shindagi,Aishwarya T | Medium | 2024-01-23 09:30 | 2024-02-01 16:30 | 2024-01-19 17:43 | Development Complete | Yes | 10% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363,772989157 | 46 | Late | 56 | 56 | 73.5 | hrs |  | Clear | Dharanidharan C
7.4981e+17 | User Manual for Quote Management Application | Anusuyadevi V,Tanu Gupta | High | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 23:06 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 786479121,790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Data mapping from Application module PDFs to excel | Prableen Kaur,Pannaga H | None | 2024-01-19 09:30 | 2024-01-22 19:00 | 2024-01-19 18:30 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644,795342015 | 1 | Late | 5 | 5 | 2 | days
7.4981e+17 | Function email upadtion changes | Mary Nisha | High | 2024-01-19 09:30 | 2024-01-19 19:00 | 2024-01-19 14:55 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Inventory Report for primary UOM | Vignesh R | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 19:23 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 60 | Late | 61 | 61 | 1 | days
7.4981e+17 | Send Follow-Up Email Notification to Customer, Once ticket is changed to In-Progress | Sachin Patil | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 19:10 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Data Management | Avinash Sah | None |  |  | 2024-01-20 23:23 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | UAT and Client Review | Sai Krishna | None | 2024-01-23 09:30 | 2024-01-24 19:00 | 2024-01-19 09:54 | Done | No | 100% | QUICK HEAL - Zoho CRM & Zoho Marketing Automation | Milestone Two-Implementation of Zoho CRM – API Integrations | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 15 | Late | 17 | 17 | 2 | days
7.4981e+17 | Permission Access Modifications | Mary Nisha | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 15:53 | Development Complete | Yes | 10% | Educational Initiatives - P&I CR | None | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 60 | Late | 61 | 61 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | New website content | unassigned | None |  |  | 2024-01-19 10:15 | To Do | No | 0% | V-Align Marketing Activites | None | 7.4981e+17 | 7.4981e+17 |  | 800651184 | - |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Creating Data Migration Templates | Rishikesh Gogha | None | 2024-01-18 09:30 | 2024-01-19 19:00 | 2024-01-19 10:00 | To Do | Yes | 0% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 59 | Late | 61 | 61 | 2 | days |  | Clear | Waheeba Khan
7.4981e+17 | Payment deletion and approval | Swetha K | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 16:01 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Digitalization of order hard copies(Sales order/Service order/POB) (OTP) - Blueprint in SJP Reporting | Vishnu D A | None | 2024-01-17 09:30 | 2024-01-17 16:30 | 2024-01-17 11:55 | In Progress | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 838472289 | 838472289 | 61 | Late | 62 | 62 | 7 | hrs |  | Clear | Siddharth Sharma
7.4981e+17 | UI screen for Onsite interview | Supreeth R Kalluraya | None | 2024-01-31 19:00 | 2024-01-31 19:00 | 2024-01-18 12:56 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | Milestone Four : Development completion and Go Live of CS Certification Portal. | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 788577227 | 788577227 | 47 | Late | 48 | 48 | 0 | days |  | Clear
7.4981e+17 | UI screen for update requested | Supreeth R Kalluraya | None | 2024-01-12 09:30 | 2024-01-31 19:00 | 2024-01-17 16:58 | Development Complete | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | Milestone Four : Development completion and Go Live of CS Certification Portal. | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 788577227 | 788577227 | 47 | Late | 67 | 67 | 14 | days |  | Clear | Christ Bellarmine
7.4981e+17 | ABMPL-Zoho Creator Order management Flow bugs fixing | Vaikuntam Chowdary | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-18 09:29 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 61 | Late | 62 | 62 | 1 | days |  | Clear
7.4981e+17 | Accounts to zoho Books ID update in CRM | Monik Chettiyar | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 12:54 | To Do | Yes | 0% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 60 | Late | 61 | 61 | 1 | days |  | Clear
7.4981e+17 | In the alert message the mandatory field for call closure should be shown | Nikita Srivastava | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 13:29 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 50 | Late | 51 | 51 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Create Scheduler for Bill and PO to remind the Approval Pending Records | Shavi Thakur | None | 2024-01-17 09:30 | 2024-01-17 12:00 | 2024-01-17 10:45 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 773081417 | 1 | Late | 2 | 2 | 2.5 | hrs
7.4981e+17 | Support request on Error in Quarterly Check in form (Oct-Dec '23) | Kiran Shrivastav | None | 2024-01-16 09:30 | 2024-01-17 19:00 | 2024-01-16 19:24 | Done | No | 100% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 2 | Late | 4 | 4 | 2 | days
7.4981e+17 | Changes in Purchase Information | Sachin Patil | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 18:24 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Synup ¦ Client Call ¦ Zoho Desk | Tanu Gupta | High | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 23:37 | Done | No | 100% | AMC - VAlign | Synup Digital Pvt Ltd - Zoho CRM & Desk ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Send Communication Letter to Corp Members About Rollout and Wave Allocation | Stefan Bradham | None | 2024-01-17 09:30 | 2024-02-09 19:00 | 2024-01-18 01:03 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 1. MBE Search | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 836353936 | 11 | Late | 35 | 35 | 18 | days
7.4981e+17 | Train the Trainer (Finance) | Christ Bellarmine | None |  |  | 2024-01-17 23:56 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 81581486 |  | On Time |  | 0 | 0 | days
7.4981e+17 | #5844 Meetings count for each sales team member | Tanu Gupta | High | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 23:44 | Done | No | 100% | AMC - VAlign | HAPPY RELIABLE SURGERIES PRIVATE LIMITED - Zoho CRM and Zoho Form ¦ 16-08-2023 ¦ 15-08-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 7 | Late | 8 | 8 | 1 | days
7.4981e+17 | Namma Sampradaya - website edits | unassigned | None |  |  | 2024-01-18 09:56 | To Do | No | 0% | V-Align Marketing Activites | None | 7.4981e+17 | 7.4981e+17 |  | 800651184 | - |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Client Meeting | Monik Chettiyar | None | 2024-01-10 09:30 | 2024-01-19 19:00 | 2024-01-17 20:22 | In Progress | Yes | 10% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 59 | Late | 69 | 69 | 8 | days |  | Clear
7.4981e+17 | Validation for call creation to be removed | Nikita Srivastava | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 18:55 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 50 | Late | 51 | 51 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Daily Standup | Supreeth R Kalluraya | None | 2024-01-16 09:30 | 2024-01-31 19:00 | 2024-01-17 09:32 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 788577227 | 788577227 | 47 | Late | 63 | 63 | 12 | days |  | Clear
7.4981e+17 | Registration and login issue in arya samaj website issue | Maninder Singh | None | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-18 12:40 | QA level 1 Completed | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 60 | Late | 61 | 61 | 1 | days |  | Clear
7.4981e+17 | Client Script for LEads and Deals module for Picklist and to add validations for sections should not get save if empty | Aishwarya T | None | 2024-01-17 09:30 | 2024-01-18 19:00 | 2024-01-18 10:35 | To Do | Yes | 0% | Thoucentric Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 60 | Late | 62 | 62 | 2 | days |  | Clear | Irshad Pasha
7.4981e+17 | Management & Controls Screen UI | Avinash Sah | None | 2024-01-18 09:30 | 2024-01-19 19:00 | 2024-01-18 10:09 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176894 | 48 | Late | 50 | 50 | 2 | days |  | Clear
7.4981e+17 | #5835 Activation of Zoho CRM ID | Maninder Singh | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-16 16:12 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | -1 | On Time | 0 | 0 | 1 | days
7.4981e+17 | External Meeting with Stellar Team | Sachin Patil | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-17 19:02 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Presales call with Sonic Bolt | Kiran Shrivastav | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 12:32 | Done | No | 100% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Dharani feedback points 12-01-24 | M S Satya | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 11:20 | QA level 1 Completed | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 66 | Late | 67 | 67 | 1 | days |  | Clear
7.4981e+17 | Item Detail Page Version 2 Creation | Ayush Singh | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 18:49 | Development Complete | Yes | 10% | VSINTERCONNECT CR for Estore | Milestone Two-Development, UAT & Go Live of Estore CR | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 66 | Late | 67 | 67 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Steerworld task | Ayush Singh,Mary Nisha | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 18:26 | Done | No | 100% | AMC - VAlign | STEER Engineering Private Limited - Zoho CRM And Analytics ¦ 05-07-2023 ¦ 04-07-2024 | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679,775643568 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Solution for Auto Knock off PM | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Solution for Auto Knock off PR | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Integration with Books | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | With Credit Blocks | Waheeba Khan | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Vendor Master integration Testing | Waheeba Khan | None |  |  | 2024-01-16 10:36 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Two-Payment for January2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Payin Integration with Zoho Books | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Payin Form and Work Flows | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Payout Integration with Zoho Books | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Payout Form and Work Flows | Rishikesh Gogha | None |  |  | 2024-01-16 10:36 | To Do | No | 0% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone Four-Payment for March 2024 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 745115006 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Client call - bills for unregistered vendor | Tanu Gupta | High | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-15 18:17 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Client Meeting For Reports Discussion | Mohammed Yusha | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 19:50 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Five-Advance Reports & Analytics | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | Vendor Payments Migration | Rishikesh Gogha | None | 2024-01-22 09:30 | 2024-01-22 19:00 | 2024-01-12 09:49 | To Do | Yes | 0% | Furnishka - Zoho Books | Milestone Two-Zoho Books Improvisation Services | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 56 | Late | 57 | 57 | 1 | days
7.4981e+17 | Field Level Validation | Avinash Sah | None | 2024-02-02 19:00 | 2024-02-02 19:00 | 2024-01-16 11:44 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 830176894 | 830176894 | 34 | Late | 35 | 35 | 0 | days |  | Clear | Uday Desai
7.4981e+17 | Open PO Details with Ageing | Mohammed Yusha,Shavi Thakur | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-16 09:22 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Five-Advance Reports & Analytics | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 701373265,773081417 | 1 | Late | 2 | 2 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Ensure Website Content leads to all Prequalification and Certification Types | Kris Oswold | None | 2024-01-12 09:30 | 2024-04-08 19:00 | 2024-01-15 23:06 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 824545238 | -21 | On Time | 67 | 67 | 62 | days
7.4981e+17 | Stock Ageing | Achyuth T M,Shavi Thakur | None | 2024-01-12 12:30 | 2024-01-12 16:00 | 2024-01-12 11:42 | Terminated/Cancelled | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Five-Advance Reports & Analytics | 7.4981e+17 | 7.4981e+17 |  | 773081417 | 708853094,773081417 | 6 | Late | 7 | 7 | 3.5 | hrs |  | Clear | Mohammed Yusha
7.4981e+17 | Dashboard - Backend | Nawaz Sharief | None | 2024-02-16 09:30 | 2024-02-16 19:00 | 2024-01-11 19:15 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 841115370 | 20 | Late | 21 | 21 | 1 | days |  | Not Clear
7.4981e+17 | Backend Validation Rules -references | Nawaz Sharief | None | 2024-01-31 09:30 | 2024-02-15 19:00 | 2024-01-11 18:58 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 841115370 | 21 | Late | 37 | 37 | 12 | days |  | Not Clear
7.4981e+17 | Backend -Business Info Screen | Nawaz Sharief | None | 2024-01-31 09:30 | 2024-02-05 19:00 | 2024-01-11 18:49 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 841115370 | 31 | Late | 37 | 37 | 4 | days |  | Not Clear
7.4981e+17 | Header banner | Nawaz Sharief | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 18:14 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 841115370 | 841115370 | 25 | Late | 26 | 26 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Issue solving for Address and flowcon demo and solving issues with client | Aishwarya T | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 14:45 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 13 | Late | 14 | 14 | 1 | days
7.4981e+17 | Dharani Feedback points - 16-01-24 | M S Satya | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-16 10:53 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 62 | Late | 63 | 63 | 1 | days |  | Clear
7.4981e+17 | for new installation warrenty status should active | Nikita Srivastava | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-12 09:42 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 55 | Late | 56 | 56 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | "Invalid file type" popup showing even after form submitted and payment done. | Maninder Singh | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 16:43 | QA level 1 Completed | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 67 | Late | 68 | 68 | 1 | days |  | Clear
7.4981e+17 | Create Edit/View Button In Batches To Open Record In Edit Mode | Aaftab Ahmad | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-12 17:07 | Development Complete | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 776475994 | 776475994 | 67 | Late | 68 | 68 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Machani dedicated Resource | Mohan Kumar | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-12 10:29 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Set up of Data Flow & Research | Stuti S. Kulshrestha | None | 2024-01-11 09:30 | 2024-01-12 19:00 | 2024-01-11 16:49 | Done | No | 100% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 54 | Late | 56 | 56 | 2 | days
7.4981e+17 | Dashboard Configuration | Achyuth T M | High | 2024-01-25 09:30 | 2024-01-29 19:00 | 2024-01-12 13:41 | To Do | Yes | 0% | Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 49 | Late | 54 | 54 | 3 | days
7.4981e+17 | Cash Flow Report | Achyuth T M | High | 2024-01-18 09:30 | 2024-01-19 19:00 | 2024-01-12 13:36 | To Do | Yes | 0% | Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 59 | Late | 61 | 61 | 2 | days
7.4981e+17 | CPL Vendors API Issues | Anusha V | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-12 09:14 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 | 56 | Late | 57 | 57 | 1 | days
7.4981e+17 | Client Meeting for upload achievements issues | Selva Bharathi,Tanu Gupta | High | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 19:18 | Done | No | 100% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701368573,790157522 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Create A Reminder Scheduler For Pending Tour Request To Claim. | Aaftab Ahmad | High | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 17:58 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 776475994 | 776475994 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Tag multiple potential to Order Approval | Nikita Srivastava | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 11:22 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | UI Validation Rules -Buiness Description | Nawaz Sharief | None | 2024-01-17 09:30 | 2024-01-23 19:00 | 2024-01-11 12:44 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 841115370 | 44 | Late | 51 | 51 | 5 | days |  | Clear
7.4981e+17 | UI Validation Rules & Dependent Fields & Map Dependencies | Avinash Sah | None | 2024-01-17 09:30 | 2024-01-23 19:00 | 2024-01-11 12:36 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176894 | 13 | Late | 20 | 20 | 5 | days |  | Clear
7.4981e+17 | Sidebar Development | Avinash Sah | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 12:28 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 830176894 | 830176894 | 22 | Late | 23 | 23 | 1 | days |  | Clear
7.4981e+17 | Stock Adjustment - For FG and SFG need to fetch the rate from last Production entry per unit Production Cost | Sachin Patil | None | 2024-01-10 09:30 | 2024-01-12 19:00 | 2024-01-10 09:33 | Done | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 0 | Late | 3 | 3 | 3 | days
7.4981e+17 | Add Email Template follow-Up for Status is In Progress (3rd, 5th and 7th Business Day) | Sachin Patil | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 20:06 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Client meeting and template alignment | Aishwarya T | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 10:48 | To Do | Yes | 0% | AMC - VAlign | Non AMC Project Tasks | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 67 | Late | 68 | 68 | 1 | days
7.4981e+17 | For installation activity Engineer 2 is not required. (Pre Installation) | Nikita Srivastava | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 10:08 | Done | No | 100% | Innovation Imaging - Zoho Creator - Service Tool Management Application | Milestone Two-Implementation of Zoho Creator –Service Tool Management Application | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 57 | Late | 58 | 58 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | IDatalytics-Data Cleaning | Pannaga H | None |  |  | 2024-01-11 09:56 | In Progress | No | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 795342015 | 795342015 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Meeting to discuss Admin Management and people Management issues | Maninder Singh | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 12:19 | Done | No | 100% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | Scheduler to Raise invoice based on Payment date | Swetha K | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-11 09:41 | To Do | Yes | 0% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 774026088 | 774026088 | 67 | Late | 68 | 68 | 1 | days
7.4981e+17 | Zoho Creator - Clone Job Costing and version if Negotiation for deal in zoho crm | Tanu Gupta | High | 2024-01-17 09:30 | 2024-01-18 19:00 | 2024-01-10 21:45 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 60 | Late | 62 | 62 | 2 | days |  | Clear | Supril Jain
7.4981e+17 | Dynamic tax master | Mohammed Yusha,Anusuyadevi V | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-10 08:47 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 701373265,786479121 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Call with CPL Vendor Team on APIS(08/01/24) | Anusha V | None |  |  | 2024-01-09 23:19 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | 795545761 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Auto Create Manual Journals | Anusuyadevi V,Tanu Gupta | High | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-10 19:42 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 786479121,790157522 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Internal Testing The Entire Flow -Zoho Creator, Books & Desk | Mohammed Yusha | None | 2024-01-09 09:30 | 2024-01-10 19:00 | 2024-01-09 19:51 | Done | No | 100% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 2 | 2 | 2 | days |  | Clear
7.4981e+17 | MBE Form Creation and Integration with CRM | Sai Krishna | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-11 09:45 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 002 - Milestone Three : Development completion of Certification Portal | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 68 | Late | 69 | 69 | 1 | days |  | Clear
7.4981e+17 | Call with Bhavani | Kiran Shrivastav | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 19:14 | Done | No | 100% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Changes | Ranjana Poojari | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-10 14:44 | Done | No | 100% | IIFL Samasta: Zoho Creator Employee House Visit (EHV) Change Request | Milestone One- Advance Payment Zoho Creator Employee House Visit (EHV) Change Request | 7.4981e+17 | 7.4981e+17 |  | 778475421 | 778475421 | 2 | Late | 3 | 3 | 1 | days |  | Clear
7.4981e+17 | Client Call - Scorecard | Selva Bharathi,Tanu Gupta | High | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 19:40 | Done | No | 100% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701368573,790157522 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Weekly Meetings | Monik Chettiyar | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 19:21 | Done | No | 100% | AMC - VAlign | Healthplix | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Custom validation | Monik Chettiyar | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-09 19:11 | In Progress | Yes | 10% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 73 | Late | 74 | 74 | 1 | days |  | Clear
7.4981e+17 | Template Creation and Zoho CRM Changes in quotes module | Monik Chettiyar | None | 2024-01-04 09:30 | 2024-01-05 19:00 | 2024-01-09 18:42 | In Progress | Yes | 10% | Airowire Zoho CRM, Zoho Books and Zoho Projects | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 73 | Late | 75 | 75 | 2 | days |  | Clear
7.4981e+17 | high priority - Sick Leaves issue | Kiran Shrivastav | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 15:09 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | All four WhatsApp messages are sent for both Online and Offline deals | Sachin Patil | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 19:07 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 10 | Late | 11 | 11 | 1 | days
7.4981e+17 | Subject Is Not Coming In Mail | Aaftab Ahmad | Medium | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-09 18:20 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 776475994 | 776475994 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Send Bulk Approval for PO and Bills | Shavi Thakur,Tanu Gupta | Medium | 2024-01-09 09:30 | 2024-01-10 19:00 | 2024-01-09 11:01 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 773081417,790157522 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Profit and Loss Report | Achyuth T M | High | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-09 17:22 | In Progress | Yes | 0% | Airowire - Zoho Analytics | Milestone Two-Implementation of Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 66 | Late | 67 | 67 | 1 | days
7.4981e+17 | Revised Roles and permissions for Zoho Creator, Desk, CRM and Books | Tanu Gupta | High | 2024-02-02 09:30 | 2024-02-02 19:00 | 2024-01-09 18:38 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 45 | Late | 46 | 46 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Zoho Creator - Update Quote Template (T&C, Client Logos etc) | Tanu Gupta | High | 2024-01-18 09:30 | 2024-01-18 19:00 | 2024-01-09 18:30 | In Progress | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 60 | Late | 61 | 61 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Zoho Mail Training | Irshad Pasha | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-09 15:40 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 701341459 | 4 | Late | 5 | 5 | 1 | days
7.4981e+17 | Client Visit on 09-Jan-2024 | Vignesh R | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 10:15 | Terminated/Cancelled | No | 100% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Push items imported from Creator's item master to Books item master | Sachin Patil | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-09 09:26 | Terminated/Cancelled | No | 100% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 1 | Late | 2 | 2 | 1 | days |  | Clear
7.4981e+17 | ZI and Shopify Test Cases | Anusuyadevi V | None | 2024-01-08 09:30 | 2024-01-09 19:00 | 2024-01-09 09:25 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 1 | Late | 3 | 3 | 2 | days
7.4981e+17 | Field mapping and assignment | Swetha K | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 14:22 | Done | No | 100% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Testing of Flow | Mohammed Yusha,Anusuyadevi V | None | 2024-01-30 09:30 | 2024-01-31 19:00 | 2024-01-08 09:39 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 701373265,786479121 | -12 | On Time | -10 | -10 | 2 | days
7.4981e+17 | Zoho Creator - Remove the fields and revise automation in Job costing | Tanu Gupta | High | 2024-01-08 09:30 | 2024-01-09 19:00 | 2024-01-08 21:10 | Development Complete | Yes | 10% | Verto_Zoho One | None | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 69 | Late | 71 | 71 | 2 | days |  | Clear | Supril Jain
7.4981e+17 | Member Management Feedback Changes | Sai Krishna | None |  |  | 2024-01-08 09:46 | To Do | No | 0% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 |  | On Time |  | 0 | 0 | days |  | Clear
7.4981e+17 | Dashboards Permission set with reports | Aishwarya T | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 12:13 | Done | No | 100% | Ensavior_Zoho CRM | Milestone Two-Implementation of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772989157 | 772989157 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Call with Zoho Support for Payroll queries_IITPL | Kiran Shrivastav | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 19:39 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Internal Meeting/ Standup Call | Kalyanasundaram L | None | 2024-01-03 09:30 | 2024-01-15 19:00 | 2024-01-05 16:50 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 63 | Late | 76 | 76 | 9 | days |  | Clear
7.4981e+17 | Daily Standup Call / Internal Discussion | Kalyanasundaram L | None | 2024-01-05 09:30 | 2024-01-15 19:00 | 2024-01-06 19:34 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 819676542 | 819676542 | 63 | Late | 74 | 74 | 7 | days |  | Clear
7.4981e+17 | Data Sharing and Roles issue fixing | Anusuyadevi V | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 21:53 | Done | No | 100% | Captain Fresh - Zoho CRM | None | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 25 | Late | 26 | 26 | 1 | days |  | Clear | Mohammed Yusha
7.4981e+17 | Send Quotation Template to Customer via Email | Anusuyadevi V,Tanu Gupta | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 09:18 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121,790157522 | 5 | Late | 6 | 6 | 1 | days
7.4981e+17 | Zoho Books Query resolution | Waheeba Khan | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 12:49 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | None | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 | 0 | Late | 1 | 1 | 1 | days |  | Clear
7.4981e+17 | Configuration of Deal Module and Field configurations | Rajesh Shindagi | None | 2024-01-11 09:30 | 2024-01-12 19:00 | 2024-01-04 19:16 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 66 | Late | 68 | 68 | 2 | days |  | Not clear
7.4981e+17 | Configuration of Analytics Dashboards | Rajesh Shindagi | None | 2024-01-24 09:30 | 2024-01-25 19:00 | 2024-01-04 18:47 | In Progress | Yes | 10% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 53 | Late | 55 | 55 | 2 | days |  | Clear
7.4981e+17 | Contact Role automations | Mary Nisha | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 15:41 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 70 | Late | 71 | 71 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | form customization for Annual appraisal process | Kiran Shrivastav | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 12:40 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Automations and PDF devlopmentation | Mary Nisha | None | 2024-01-10 09:30 | 2024-01-10 19:00 | 2024-01-08 11:13 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 775643568 | 775643568 | 68 | Late | 69 | 69 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Opportunity CCO Automations and functions | Mary Nisha | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-08 09:54 | QA level 1 Completed | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 775643568 | 67 | Late | 68 | 68 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Lal10 Client Call on Preffered Currency option Sync | Sai Krishna,Ayush Singh | None | 2024-01-04 09:30 | 2024-01-05 19:00 | 2024-01-05 09:44 | Done | No | 100% | AMC - VAlign | LAL 10 - Zoho Creator and Zoho Books | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 753339779 | 753339779,772908679 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Boldfit ¦ Zoho Books ¦ Manual Journal Entries - Client call | Waheeba Khan,Tanu Gupta | High | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 20:37 | Done | No | 100% | (BoldFit) Sasvat_Zoho One | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 671373250,790157522 | 6 | Late | 7 | 7 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Quotation User Manual Creation | Anusuyadevi V | None | 2024-01-18 09:30 | 2024-01-19 19:00 | 2024-01-08 09:27 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | -1 | On Time | 1 | 1 | 2 | days
7.4981e+17 | Deal Module Blueprint Changes | Anusuyadevi V | None | 2024-01-10 09:30 | 2024-01-11 19:00 | 2024-01-08 09:20 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 786479121 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Zoho Project Process Customization | Mohammed Yusha | None | 2024-01-29 09:30 | 2024-01-30 19:00 | 2024-01-05 16:15 | To Do | Yes | 0% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 48 | Late | 50 | 50 | 2 | days
7.4981e+17 | Solution Testing | Mohammed Yusha,Anusuyadevi V,Tanu Gupta | High | 2024-01-22 09:30 | 2024-01-23 19:00 | 2024-01-05 16:10 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,786479121,790157522 | 1 | Late | 3 | 3 | 2 | days
7.4981e+17 | Inventory valuation for 31st DEC | Waheeba Khan,Rishikesh Gogha | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-05 09:51 | Done | No | 100% | Genesis IT - Applications Training and query clarification on Zoho Books and Inventory | Milestone Two-Applications training and query clarifications | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 671373250,745115006 | 3 | Late | 4 | 4 | 1 | days
7.4981e+17 | Issue Qty Report | Achyuth T M | High | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 10:41 | Done | No | 100% | Ecovinal Project 3 - Farmer Management | Milestone Two-Zoho Creator – Farmer Operations: Configuration and customisation, Software demo | 7.4981e+17 | 7.4981e+17 |  | 708853094 | 708853094 | 4 | Late | 5 | 5 | 1 | days |  | Clear
7.4981e+17 | UAT Feedbacks | Tanu Gupta | High | 2024-01-04 09:30 | 2024-01-10 19:00 | 2024-01-04 22:35 | Development Complete | Yes | 10% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 68 | Late | 75 | 75 | 5 | days |  | Clear | Selva Bharathi
7.4981e+17 | Add the code to create the associate id by using Unique id form | Nikita Srivastava | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 18:38 | QA level 1 Completed | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 70 | Late | 71 | 71 | 1 | days |  | Clear
7.4981e+17 | Calculation Changes in Issue Slip | Mallesh M S | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-08 17:13 | QA level 1 Completed | Yes | 10% | Ecovinal Project 3 - Farmer Management | Milestone Two-Zoho Creator – Farmer Operations: Configuration and customisation, Software demo | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 778475418 | 69 | Late | 70 | 70 | 1 | days |  | Clear
7.4981e+17 | Develop RMSDC User Interface | Supreeth R Kalluraya | None | 2024-01-05 09:30 | 2024-03-12 19:00 | 2024-01-06 02:34 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 3. Certification | 7.4981e+17 | 7.4981e+17 |  | 828527327 | 788577227 | -5 | On Time | 63 | 63 | 48 | days
7.4981e+17 | MBE Search Issue Testing | Stuti S. Kulshrestha | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 16:57 | Done | No | 100% | iDatalytics - Zoho One Implementation_201123 | 001 - Milestone Two : Development completion and Go Live of MBE Search | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 808004288 | 5 | Late | 6 | 6 | 1 | days |  | Clear
7.4981e+17 | Zoho Survey fesiability check | M S Satya | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 10:54 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 70 | Late | 71 | 71 | 1 | days |  | Clear
7.4981e+17 | Changes in Stock Adjustment - Adjust Stock after submit | Vignesh R | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 13:16 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 73 | Late | 74 | 74 | 1 | days
7.4981e+17 | Lead Notification Mails for Sam P | Nikita Srivastava | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 19:37 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Meeting on Zoho Payroll issues | Kiran Shrivastav | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-05 20:14 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | For few deals, contact not created or associate | Sachin Patil | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 18:50 | Done | No | 100% | AMC - VAlign | Durian - Zoho CRM Support | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Scrum Call - 01--01-2024 | unassigned | None |  |  | 2024-01-09 09:17 | In Progress | No | 0% | AMC - VAlign | Samasta AMC | 7.4981e+17 | 7.4981e+17 |  | 795545761 | - |  | On Time |  | 0 | 0 | days
7.4981e+17 | Internal Meeting for Disbursement challenge | Selva Bharathi,Tanu Gupta | High | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-08 18:42 | Done | No | 100% | IIFL SAMASTA - Scorecard AM & Above | Milestone One-Implementation of Enhancement for Score Card for AM & Above | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 701368573,790157522 | 0 | Late | 1 | 1 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | CF to update the deal on revision of an estimate: product line item updation in CRM | Rajesh Shindagi | Medium | 2024-01-10 09:30 | 2024-01-10 14:00 | 2024-01-04 18:16 | Development Complete | Yes | 10% | Dhyanventures - TnM - Zoho CRM / Books / Analytics | Milestone Two-Implementation of Zoho CRM, Zoho Books, Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 68 | Late | 69 | 69 | 4.5 | hrs |  | Clear | Dharanidharan C
7.4981e+17 | UAT points(4/1/2024) | Swetha K | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 13:22 | Done | No | 100% | IIFL SAMASTA -Zoho Creator_Helpdesk CR | Milestone One-Customization and Development of Change Request for Zoho Help Desk | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 8 | Late | 9 | 9 | 1 | days |  | Clear | Selva Bharathi
7.4981e+17 | Employee Database | Kiran Shrivastav | None | 2024-01-30 09:30 | 2024-01-30 19:00 | 2024-01-04 14:17 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Salary template | Kiran Shrivastav | None | 2024-01-26 09:30 | 2024-01-29 19:00 | 2024-01-04 14:17 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 22 | Late | 26 | 26 | 2 | days
7.4981e+17 | Department, Designation and location | Kiran Shrivastav | None | 2024-01-22 09:30 | 2024-01-24 19:00 | 2024-01-04 14:12 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 26 | Late | 29 | 29 | 3 | days
7.4981e+17 | Workflows and Email Automation | Kiran Shrivastav | None | 2024-01-15 09:30 | 2024-01-19 19:00 | 2024-01-04 14:00 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 31 | Late | 36 | 36 | 5 | days
7.4981e+17 | Location and Shift Mapping | Kiran Shrivastav | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-04 13:58 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 34 | Late | 35 | 35 | 1 | days
7.4981e+17 | Employee Onboarding | Kiran Shrivastav | None | 2024-01-15 09:30 | 2024-01-15 19:00 | 2024-01-04 13:58 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 35 | Late | 36 | 36 | 1 | days
7.4981e+17 | User Acceptance Testing | Kiran Shrivastav | None | 2024-01-17 09:30 | 2024-01-23 19:00 | 2024-01-04 13:33 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 55 | Late | 62 | 62 | 5 | days
7.4981e+17 | Testing | Kiran Shrivastav | None | 2024-01-15 09:30 | 2024-01-16 19:00 | 2024-01-04 13:30 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 62 | Late | 64 | 64 | 2 | days
7.4981e+17 | Candidate Stages | Kiran Shrivastav | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-04 13:30 | To Do | Yes | 0% | Proclime- Zoho One - TnM | Milestone Two-Implementation of Zoho One | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 67 | Late | 68 | 68 | 1 | days
7.4981e+17 | unique id not coming correct for member ,guest and associate | Maninder Singh | None | 2024-01-09 09:30 | 2024-01-10 19:00 | 2024-01-04 12:39 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 68 | Late | 70 | 70 | 2 | days |  | Clear | Supril Jain
7.4981e+17 | All the field Names must have Hindi Text along with English.(Some of the fields does not have Hindi Labels)retest | Nikita Srivastava | None | 2024-01-09 09:30 | 2024-01-09 19:00 | 2024-01-04 12:32 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 774653652 | 69 | Late | 70 | 70 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Data Analysis Tristate, Western Regional | Prableen Kaur,Pannaga H | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-04 14:04 | Terminated/Cancelled | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 792886644 | 792886644,795342015 | 11 | Late | 12 | 12 | 1 | days
7.4981e+17 | Data Analysis of Dallas | Pannaga H | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 13:41 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 792886644 | 795342015 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | Update Bill Date Manually in Creator and Books | Vignesh R | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 17:18 | Development Complete | Yes | 10% | Trimble Group_Zoho Books & Zoho Creator | Zoho Purchase and Inventory | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 74 | Late | 75 | 75 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Support Activity as on 5 Jan 2024 | Mohammed Yusha,Shavi Thakur,Tanu Gupta | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-04 12:15 | Done | No | 100% | AMC - VAlign | Juspay AMC - 10-12-2023 to 09-12-2024 | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265,773081417,790157522 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Configuration of Customize Home Page | Rajesh Shindagi | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-04 12:08 | To Do | Yes | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | 758002363 | 55 | Late | 56 | 56 | 1 | days |  | Not clear
7.4981e+17 | Configuration of Pipelines | unassigned | None |  |  | 2024-01-04 12:08 | To Do | No | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | - |  | On Time |  | 0 | 0 | days |  | Not clear
7.4981e+17 | Configuration of Segmentation | unassigned | None |  |  | 2024-01-04 12:07 | To Do | No | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | - |  | On Time |  | 0 | 0 | days |  | Not clear
7.4981e+17 | Configuration of Assignment Rules | unassigned | None |  |  | 2024-01-04 12:07 | To Do | No | 0% | Surya Enterprises - Zoho CRM Plus | Milestone Two-Solution Development & Go Live of Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 758002363 | - |  | On Time |  | 0 | 0 | days |  | Not clear
7.4981e+17 | RCA and solutioning of Customer Reference issue | Prableen Kaur | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-04 11:24 | Done | No | 100% | iDATALYTCS UI PATH | Milestone Two-Upon the completion of GoLive confirmation from iDatalytics | 7.4981e+17 | 7.4981e+17 |  | 792886644 | 792886644 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Login via Email -> Email field should not be case sensitive while login with "Email". | Maninder Singh | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-04 12:15 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 70 | Late | 71 | 71 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Update Mobile -> if i remove Mobile Number and clicks on "Send OTP" popup shows "Please check your mobile for OTP" instead of " Please enter valid Mobile Number".Retest | Maninder Singh | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-04 11:06 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 73 | Late | 74 | 74 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Letters_2gethr | Kiran Shrivastav | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 10:34 | In Progress | Yes | 0% | AMC - VAlign | 2GETHR HUB PRIVATE LIMITED - Zoho People, Zoho Recruit & Zoho Payroll ¦ 15-05-2023 ¦ 14-05-2024 | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 74 | Late | 75 | 75 | 1 | days
7.4981e+17 | PMD and Opportunity Templates - Grouping tables and customization | Ayush Singh,Mary Nisha | None | 2024-01-04 09:30 | 2024-01-09 19:00 | 2024-01-04 09:38 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679,775643568 | 69 | Late | 75 | 75 | 4 | days |  | Clear | Dharanidharan C
7.4981e+17 | Access for the user based on the vendor - Need to add the multi-select lookup in user master | Vignesh R | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-03 22:00 | To Do | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 67 | Late | 68 | 68 | 1 | days |  | Clear
7.4981e+17 | Client Visit on 11-Jan-2024 | Vignesh R | None | 2024-01-11 09:30 | 2024-01-11 19:00 | 2024-01-03 21:48 | In Progress | Yes | 0% | AMC - VAlign | Stanzen | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 67 | Late | 68 | 68 | 1 | days
7.4981e+17 | Sales Quantity - Show 90 Days avg qty in PO | Vignesh R | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-03 21:40 | In Progress | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 70 | Late | 71 | 71 | 1 | days |  | Clear
7.4981e+17 | Put Away sheet field level changes in subform | Vignesh R,Ranganatha K | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-03 21:31 | In Progress | Yes | 10% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602,772021671 | 73 | Late | 74 | 74 | 1 | days |  | Clear
7.4981e+17 | No of boxes and Surplus quantity to be renamed in all the modules | Vignesh R | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-03 21:23 | Development Complete | Yes | 10% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 704175602 | 704175602 | 74 | Late | 75 | 75 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Admin SLA configuration state wise | Aishwarya T | None | 2024-01-03 09:30 | 2024-01-04 19:00 | 2024-01-03 12:14 | Done | No | 100% | IIFL SAMASTA -Zoho Creator_Helpdesk CR | Milestone One-Customization and Development of Change Request for Zoho Help Desk | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 772989157 | 772989157 | 4 | Late | 6 | 6 | 2 | days
7.4981e+17 | Debit Note Books Integration | Aaftab Ahmad | None | 2024-01-12 09:30 | 2024-01-12 19:00 | 2024-01-04 10:24 | Development Complete | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 776475994 | 66 | Late | 67 | 67 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | TDS Books Integration | Aaftab Ahmad | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 10:24 | Terminated/Cancelled | No | 100% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 776475994 | 4 | Late | 5 | 5 | 1 | days |  | Not Clear | Waheeba Khan
7.4981e+17 | Item Master Books Integration | Aaftab Ahmad | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-04 10:24 | Development Complete | Yes | 0% | Atlas - Zoho Creator - P & I, And OMS | Milestone Two-Development and Customization of Zoho Creator - P&I and OMS And Testing with two | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 776475994 | 73 | Late | 74 | 74 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Many roles introduced after widget development do not have permission to view CRM data from the widget. As a result, admin profiles are enabled for these roles, giving them more access than they need. | Siddharth Sharma | None | 2024-01-12 09:30 | 2024-01-17 19:00 | 2024-01-04 09:56 | To Do | Yes | 0% | Agappe - Zoho CRM Revamp Project | None | 7.4981e+17 | 7.4981e+17 |  | 756762742 | 756762742 | 61 | Late | 67 | 67 | 4 | days |  | Clear
7.4981e+17 | EI; PAYROLL ACCESS | Rishikesh Gogha | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-04 08:49 | Done | No | 100% | AMC - VAlign | EI - Zoho One Implementation Support | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 14 | Late | 15 | 15 | 1 | days
7.4981e+17 | iDatalytics Scrum Meeting | Selva Bharathi | None | 2024-01-04 11:30 | 2024-01-04 12:30 | 2024-01-03 16:52 | To Do | Yes | 0% | iDatalytics - Zoho One Implementation_201123 | None | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 701368573 | 74 | Late | 75 | 75 | 1 | hrs |  | Clear
7.4981e+17 | UAT - R4 | Christ Bellarmine | None | 2024-01-19 09:30 | 2024-03-22 19:00 | 2024-01-03 18:43 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 81581486 | -4 | On Time | 60 | 60 | 46 | days
7.4981e+17 | Creation of Email templates - Membership renewal | Christina Santos | None | 2024-01-11 09:30 | 2024-02-16 19:00 | 2024-01-03 17:33 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 825341377 | 24 | Late | 61 | 61 | 27 | days
7.4981e+17 | Integration of Payment Gateway to Creator | Dharanidharan C | None | 2024-01-11 09:30 | 2024-01-17 19:00 | 2024-01-03 17:24 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 12 | Late | 19 | 19 | 5 | days
7.4981e+17 | Access to Member Portal | Dharanidharan C | None | 2024-01-09 09:30 | 2024-01-17 19:00 | 2024-01-03 17:19 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 12 | Late | 21 | 21 | 7 | days
7.4981e+17 | Workflow & Automations- Feedback Mechanism | Dharanidharan C | None | 2024-01-03 09:30 | 2024-01-17 19:00 | 2024-01-03 17:15 | Terminated/Cancelled | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 12 | Late | 27 | 27 | 11 | days
7.4981e+17 | Integration of Auth.net to Zoho Books | Albert Diaz | None |  |  | 2024-01-03 17:11 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 809116687 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Workflow & Automations- Invoice & Payment | Dharanidharan C | None | 2023-12-26 09:30 | 2024-01-05 19:00 | 2024-01-03 17:08 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 5 | Late | 16 | 16 | 9 | days
7.4981e+17 | Integration of CRM to Application form | Dharanidharan C | None | 2024-01-01 09:30 | 2024-04-04 19:00 | 2024-01-03 17:06 | In Progress | No | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | -17 | On Time | 78 | 78 | 69 | days
7.4981e+17 | Configure Member Opportunity Layout in CRM (i.e. Deals Module) | Dharanidharan C | None | 2023-12-21 09:30 | 2024-03-15 19:00 | 2024-01-03 16:56 | In Progress | Yes | 0% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 3 | Late | 89 | 89 | 62 | days
7.4981e+17 | Integration CRM with Zoho Books | Dharanidharan C | None |  |  | 2024-01-03 16:09 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Create Email templates - Member Onboarding | christina santos | None |  |  | 2024-01-03 16:06 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 825341377 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Create Aggregate Reports to Validate Migration into CRM | Dharanidharan C | High | 2024-01-09 09:30 | 2024-03-13 19:00 | 2024-01-03 15:44 | Done | No | 100% | iDatalytics - Zoho Devt(NMSDC)- Roll Out | 2. Member Management | 7.4981e+17 | 7.4981e+17 |  | 808004288 | 701371504 | 3 | Late | 68 | 68 | 47 | days
7.4981e+17 | Appraisal cycle implementation | Kiran Shrivastav | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 12:36 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Testing - Leads Conversion Changes and development | M S Satya | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-04 12:12 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 73 | Late | 74 | 74 | 1 | days |  | Clear
7.4981e+17 | Research for Zoho Bookings issue | Rajesh Shindagi,M S Satya | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-04 11:38 | In Progress | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 758002363,789497933 | 74 | Late | 75 | 75 | 1 | days |  | Clear
7.4981e+17 | design issue no need to show "cross icon" & dropdown icon for "Your relation with the student" &"Guardian" fields. | Maninder Singh | None | 2024-01-05 09:30 | 2024-01-05 19:00 | 2024-01-03 11:05 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 73 | Late | 74 | 74 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | design issue "Guardian" no need to show "cross icon" & "Your relation with the student". | Maninder Singh | None | 2024-01-04 09:30 | 2024-01-04 19:00 | 2024-01-03 11:00 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 74 | Late | 75 | 75 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | "Submit Guardian's Authentic Financial Statement." field name is not same for Hindi language. | Maninder Singh | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 10:54 | Development Complete | Yes | 10% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 782721491 | 782721491 | 75 | Late | 76 | 76 | 1 | days |  | Clear | Supril Jain
7.4981e+17 | Issue slip changes | Mallesh M S | None | 2024-01-17 09:30 | 2024-01-17 19:00 | 2024-01-04 10:06 | In Progress | Yes | 10% | Ecovinal Project 3 - Farmer Management | None | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 61 | Late | 62 | 62 | 1 | days |  | Clear
7.4981e+17 | Project Status Meeting | Supril Jain,Maninder Singh | None | 2024-01-04 09:30 | 2024-01-24 19:00 | 2024-01-03 23:48 | To Do | Yes | 0% | Arya Samaj - Zoho One | Milestone Three-Phase 1 - Implementation of Zoho Creator, Zoho People & Zoho Subscription – Peop | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 756836914,782721491 | 54 | Late | 75 | 75 | 15 | days |  | Clear
7.4981e+17 | Follow Up Workflow - Enquiry | Nikita Srivastava | None | 2024-01-11 09:30 | 2024-01-12 19:00 | 2024-01-03 23:27 | To Do | Yes | 0% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 756836914 | 774653652 | 66 | Late | 68 | 68 | 2 | days
7.4981e+17 | Internal QC Of Landed Costed | Mohammed Yusha | None | 2024-01-04 09:30 | 2024-01-05 19:00 | 2024-01-03 19:24 | Done | No | 100% | Voxelgrids_Zoho Creator_Zoho Books | Milestone Four-Financial Accounting Management System | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | -1 | On Time | 1 | 1 | 2 | days |  | Clear
7.4981e+17 | Calculate Invoice amount on Successful submission of invoice. Recalculate invoice TGS/2324/02615 amount. | Sachin Patil | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 18:48 | Development Complete | Yes | 0% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 75 | Late | 76 | 76 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Send notifications to lead owner after the lead from the desk ticket | Sachin Patil | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 18:23 | Done | No | 100% | Stellar - Zoho Desk | Milestone Two-Implementation of Zoho Desk | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Zoho Books Solutioning - A& C | Supril Jain,Stuti S. Kulshrestha | None | 2024-01-09 11:00 | 2024-03-05 13:00 | 2024-01-03 17:32 | Done | No | 100% | EMERGING MARKET SOLUTIONS | Milestone Two-Zoho Solution Architect Resource - Zoho Books, ZohoCRM, Zoho Creator & Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 701341459 | 756836914,808004288 | 0 | Late | 57 | 57 | 382 | hrs
7.4981e+17 | Meeting with Cliet | Ayush Singh | None | 2024-01-16 09:30 | 2024-01-16 19:00 | 2024-01-03 16:52 | Done | No | 100% | AMC - VAlign | First Meridian - Start Date - 01-05-2023 and End Date - 30-04-2024 | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679 | 21 | Late | 22 | 22 | 1 | days
7.4981e+17 | Open points of Continuous Review Q3- (Oct-Dec 2023) | Kiran Shrivastav | None | 2024-01-03 09:30 | 2024-01-04 19:00 | 2024-01-03 10:31 | Done | No | 100% | AMC - VAlign | Educational Initiatives | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 2 | 2 | 2 | days
7.4981e+17 | Import data to inventory | Mohan Kumar | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-04 12:43 | Done | No | 100% | Machani Dedicated Resource | Milestone Eleven-January 2024 | 7.4981e+17 | 7.4981e+17 |  | 778473538 | 778473538 | 2 | Late | 3 | 3 | 1 | days
7.4981e+17 | Re: Local claim Giving Error + Change The SBU Email | Aaftab Ahmad | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-04 09:32 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 776475994 | 776475994 | 6 | Late | 7 | 7 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | Zoho Books, Zoho Desk and Zoho Creator Integration Testing | Mohammed Yusha,Vaikuntam Chowdary | None | 2024-01-08 09:30 | 2024-01-08 19:00 | 2024-01-03 17:22 | Done | No | 100% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 701373265,778472746 | 15 | Late | 16 | 16 | 1 | days |  | Clear
7.4981e+17 | Books Integration testing. | Vaikuntam Chowdary | None | 2024-01-04 09:30 | 2024-01-04 14:00 | 2024-01-03 17:19 | In Progress | Yes | 10% | Alphabetic Business Machines Pvt. Ltd. - Zoho One | Order Booking Management | 7.4981e+17 | 7.4981e+17 |  | 778472746 | 778472746 | 74 | Late | 75 | 75 | 4.5 | hrs |  | Clear
7.4981e+17 | Additional user License - CRM | Nikita Srivastava | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 10:16 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 1 | Late | 2 | 2 | 1 | days
7.4981e+17 | Ledger Entries Documentation | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Discussion on API's and Usage and Kep points issues with internal team | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | ERP Vs Zoho Call | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Masters discussion with Internal Team on PUBSUB and analysing the options | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Integration Touch points | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Solutioning V1 | Waheeba Khan | None |  |  | 2024-01-02 18:02 | Done | No | 100% | JSW One Platforms - Zoho Creator & Zoho Books ¦ Dedicated Resource | Milestone One-Payment for December 2023 of the Dedicated Resource | 7.4981e+17 | 7.4981e+17 |  | 671373250 | 671373250 |  | On Time |  | 0 | 0 | days
7.4981e+17 | Samasta Complementary (XML to Excel) | Pannaga H | None |  |  | 2024-01-03 09:19 | To Do | No | 0% | Non Billable Activities | None | 7.4981e+17 | 7.4981e+17 |  | 795342015 | 795342015 |  | On Time |  | 0 | 0 | days |  | Clear | Prableen Kaur
7.4981e+17 | LAL10 AMC Support Jan 24 FF | Sai Krishna | None | 2024-01-02 09:30 | 2024-01-15 19:00 | 2024-01-03 09:28 | In Progress | Yes | 0% | AMC - VAlign | LAL 10 - Zoho Creator and Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 63 | Late | 77 | 77 | 10 | days
7.4981e+17 | HESPL AMC Support Jan 24 FF | Sai Krishna | None | 2024-01-02 09:30 | 2024-01-15 19:00 | 2024-01-03 09:23 | Done | No | 100% | AMC - VAlign | HESPL AMC - 2023 - 24 | 7.4981e+17 | 7.4981e+17 |  | 753339779 | 753339779 | 49 | Late | 63 | 63 | 10 | days
7.4981e+17 | Zoho Books & Inventory setup | Tanu Gupta | High | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 23:29 | Done | No | 100% | GOFIBO JEWELRY - Zoho Books | Milestone Two-Implementation of Zoho Books | 7.4981e+17 | 7.4981e+17 |  | 790157522 | 790157522 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Not able to approve the Visits of Aditya Raghav (north 4) | Nikita Srivastava | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-03 10:13 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Approval Process Issue | Nikita Srivastava | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 18:58 | Done | No | 100% | AMC - VAlign | Elmeasure India Private Limited | 7.4981e+17 | 7.4981e+17 |  | 774653652 | 774653652 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Call on Holiday List addition | Kiran Shrivastav | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 18:31 | Done | No | 100% | AMC - VAlign | Longitude Exports Pvt Ltd - Zoho CRM, Zoho People & Zoho Payroll ¦ 09-08-2023 ¦ 08-02-2024 | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Support request : Mail is not triggered to the respective stakeholders to clear the checklist | Kiran Shrivastav | None | 2024-01-02 09:30 | 2024-01-04 19:00 | 2024-01-02 14:42 | Done | No | 100% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 791842987 | 791842987 | 1 | Late | 4 | 4 | 3 | days
7.4981e+17 | Return incorrect field engineer inventory stock to warehouse inventory stock (IM/TGS/2324/02772) | Sachin Patil | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 18:42 | Development Complete | Yes | 10% | Atlas_Zoho Creator | Milestone Two-Zoho Creator –Purchase and Inventory Management & Service Module1. Completi | 7.4981e+17 | 7.4981e+17 |  | 776725592 | 776725592 | 76 | Late | 77 | 77 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | SLA configuration for Admin state wise and Vigilance department | Swetha K | None | 2024-01-03 09:30 | 2024-01-03 19:00 | 2024-01-02 16:16 | Done | No | 100% | IIFL SAMASTA -Zoho Creator_Helpdesk CR | Milestone One-Customization and Development of Change Request for Zoho Help Desk | 7.4981e+17 | 7.4981e+17 | 7.4981e+17 | 774026088 | 774026088 | 0 | Late | 1 | 1 | 1 | days
7.4981e+17 | Renewal Contract Workflow Changes Automation | Mohammed Yusha | None | 2024-01-02 09:30 | 2024-01-03 19:00 | 2024-01-02 19:19 | Done | No | 100% | Mitsubishi Elevator: Zoho Creator | Sales Module | 7.4981e+17 | 7.4981e+17 |  | 701373265 | 701373265 | 0 | Late | 2 | 2 | 2 | days |  | Clear
7.4981e+17 | Assistance Required for Payroll Adjustment and Earnings Addition ¦ Mrunali Rajemahadik | Rishikesh Gogha | None | 2023-12-29 09:30 | 2023-12-29 19:00 | 2024-01-02 15:22 | Done | No | 100% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 6 | Late | 7 | 7 | 1 | days
7.4981e+17 | Urgent: Correction Needed in FNF Calculation for Employee Divyang Pastagiya | Rishikesh Gogha | None | 2023-12-13 09:30 | 2023-12-13 19:00 | 2024-01-02 14:40 | Done | No | 100% | AMC - VAlign | CyberNXT AMC | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 22 | Late | 23 | 23 | 1 | days
7.4981e+17 | Queries Clarifications | Rishikesh Gogha | None | 2023-12-08 09:30 | 2023-12-08 19:00 | 2024-01-02 14:21 | Done | No | 100% | Trimble Group_Zoho Books & Zoho Creator | Zoho Analytics | 7.4981e+17 | 7.4981e+17 |  | 745115006 | 745115006 | 27 | Late | 28 | 28 | 1 | days |  | Clear | Waheeba Khan
7.4981e+17 | FAQ update in Zoho People | Monik Chettiyar | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 10:41 | To Do | Yes | 0% | AMC - VAlign | None | 7.4981e+17 | 7.4981e+17 |  | 792262192 | 792262192 | 76 | Late | 77 | 77 | 1 | days
7.4981e+17 | Fulfillment - Mapping | Mallesh M S | None | 2024-01-23 09:30 | 2024-01-23 19:00 | 2024-01-02 10:27 | To Do | Yes | 0% | The Yarn Bazar - TYBZ - CR001 | Milestone Two-Completion of Solution Development, Testing and Zoho Creator CR Go - Live | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 55 | Late | 56 | 56 | 1 | days |  | Clear
7.4981e+17 | Fulfillment changes - HTML | Mallesh M S | None | 2024-01-02 09:30 | 2024-01-03 19:00 | 2024-01-02 10:26 | Done | No | 100% | The Yarn Bazar - TYBZ - CR001 | Milestone Two-Completion of Solution Development, Testing and Zoho Creator CR Go - Live | 7.4981e+17 | 7.4981e+17 |  | 778475418 | 778475418 | 0 | Late | 2 | 2 | 2 | days |  | Clear | Dharanidharan C
7.4981e+17 | Leads - Annual Revenue cannot be less than 0 - Validation | M S Satya | None | 2023-12-25 09:30 | 2023-12-29 19:00 | 2024-01-01 23:19 | QA level 1 Completed | Yes | 10% | iDatalytics - Zoho One Implementation_201123 | 003 - Milestone Seven : Development completion and Go Live of Member Management, Grants & Funding | 7.4981e+17 | 7.4981e+17 |  | 789497933 | 789497933 | 80 | Late | 85 | 85 | 5 | days |  | Clear
7.4981e+17 | Quote Module Automation | Mohammed Yusha,Anusuyadevi V,Tanu Gupta | None | 2024-01-02 09:30 | 2024-01-04 19:00 | 2024-01-02 10:35 | Done | No | 100% | Ozone Entertainment - Zoho ONE | Milestone Two-Implementation of Zoho One Applications (. Zoho CRM, Zoho Campaigns, Zoho Creato | 7.4981e+17 | 7.4981e+17 |  | 786479121 | 701373265,786479121,790157522 | 6 | Late | 9 | 9 | 3 | days
7.4981e+17 | PDF Fields data fetch from the CRM Submittal and Deals | Ayush Singh,Mary Nisha | None | 2024-01-02 09:30 | 2024-01-02 19:00 | 2024-01-02 10:30 | Development Complete | Yes | 10% | StaffDocs | Zoho CRM | 7.4981e+17 | 7.4981e+17 |  | 772908679 | 772908679,775643568 | 76 | Late | 77 | 77 | 1 | days |  | Clear | Dharanidharan C
7.4981e+17 | Create 2 forms Subscription +Training | Aaftab Ahmad | None | 2023-12-29 09:30 | 2023-12-29 19:00 | 2024-01-02 09:30 | Done | No | 100% | AMC - VAlign | Educational Initiative | 7.4981e+17 | 7.4981e+17 |  | 776475994 | 776475994 | 11 | Late | 12 | 12 | 1 | days |  | Clear | Waheeba Khan